## Manage Task to Role Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | OUM WORK PRODUCT NAME | PAD | PM | Project Lead(s) | Functional Lead(s) | Technical Lead(s) | Team Members
PS Project Start Up
PS.ACT.RBC Review Bid and Contract
|  | PS.BT.010 | Review and Analyze Bid Material | Reviewed and Analyzed Bid Material | 15 | 85
|  | PS.BT.020 | Review and Confirm Business Case | Confirmed Business Case | 15 | 85
|  | PS.BT.030 | Identify Project Stakeholders | Identified Project Stakeholders | 15 | 85
|  | PS.BT.040 | Review and Accept Project Budget | Accepted Project Budget | 15 | 85
|  | PS.RKM.020 | Conduct Baseline Risk Assessment | Baseline Risk Assessment | 15 | 85
PS.ACT.RPAC Review Project Assets with Customer
|  | PS.BT.050 | Review Contract with Customer | Reviewed Contract | 25 | 75
|  | PS.BT.060 | Review Project Approach with Customer | Reviewed Project Approach | 25 | 75
|  | PS.BT.070.1 | Create Project Management Plan | Project Management Framework | 25 | 75
PS.ACT.VSSOS Validate Scope, Stakeholders and OCM Strategy
|  | PS.SM.010 | Define and Confirm Scope | Validated Scope | 10 | 60 | 30
|  | PS.CMM.010 | Conduct Project Stakeholder Analysis | Project Stakeholder Analysis | 15 | 85
|  | PS.OCHM.010 | Understand Customer's Organizational Change Management Strategy | Customer's Organizational Change Management Strategy | 15 | 85
PS.ACT.DW Develop Workplan
|  | PS.WM.010 | Develop Baseline Project Workplan | Baseline Project Workplan | 10 | 65 | 25
PS.ACT.DSPB Develop Staff Plan and Budget
|  | PS.FM.010 | Refine Project Budget | Approved Project Budget | 15 | 85
|  | PS.STM.010 | Plan Resource Requirements | Resource Plan | 15 | 85
|  | PS.STM.030 | Staff Project | Staffed Project | 15 | 85
|  | PS.STM.040 | Prepare Orientation Guide(s) | Orientation Guide | 15 | 85
|  | PS.QM.030 | Conduct Project Team Quality Management Orientation | Project Team Quality Management Orientation | 15 | 85
PS.ACT.EG Establish Governance
|  | PS.SM.020 | Develop Scope Change Management Processes | Scope Change Management Procedures | 10 | 70 | 20
|  | PS.FM.020 | Develop Financial Management Plan | Financial Management Plan | 15 | 85
|  | PS.WM.020 | Develop Work Management Execution and Control Processes and Policies | Work Management Plan | 15 | 85
|  | PS.RKM.010 | Develop Risk Management Plan | Risk Management Plan | 15 | 85
|  | PS.IPM.010 | Develop Issue Management Strategy | Issue Management Strategy | 15 | 85
|  | PS.IPM.020 | Develop Problem Management Strategy | Problem Management Strategy | 15 | 85
|  | PS.STM.020 | Develop Staff Management Plan | Staff Management Plan | 15 | 85
|  | PS.CMM.020 | Develop Project Team Communication Plan | Project Team Communication Plan | 15 | 85
|  | PS.QM.010 | Develop Quality Management Plan | Quality Management Plan | 15 | 85
|  | PS.QM.020 | Develop and Document Quality Control and Reporting Process | Quality Control and Reporting Process | 15 | 85
|  | PS.CM.010 | Develop Configuration Management Strategy and Processes | Configuration Management Plan and Processes | 15 | 80 |  |  | 5
|  | PS.CM.030 | Create Project Documentation Management Plan | Documentation Management Plan | 15 | 85
|  | PS.IFM.010 | Develop Infrastructure Management Plan | Infrastructure Management Plan | 15 | 80 |  |  | 5
|  | PS.PCM.010 | Develop Procurement Strategy and Process | Procurement Strategy and Process | 15 | 85
|  | PS.OCHM.020 | Identify Change Management Warning Signs | Change Management Warning Signs | 15 | 85
|  | PS.BT.070.2 | Create Project Management Plan | Project Management Framework | 25 | 75
PS.ACT.EPI Establish Project Infrastructure
|  | PS.FM.030 | Set Up Time and Expense Tracking | Time and Expense Tracking | 15 | 85
|  | PS.RKM.030 | Develop Risk Management System | Risk Management System | 15 | 85
|  | PS.IPM.030 | Develop Issue and Problem Management System | Issue and Problem Management System | 15 | 85
|  | PS.CM.020 | Obtain Configuration Management Tools | Configuration Management Plan | 5 | 15 |  |  | 80
|  | PS.IFM.020 | Establish Team Work Environment | Team Work Environment | 15 | 85
|  | PS.IFM.030 | Establish Technical Infrastructure | Established Technical Infrastructure | 15 | 85
|  | PS.PCM.020 | Procure Goods and Contracted Services | Service Orders | 15 | 85
PEC Project Execution and Control
PEC.ACT.MSAA Manage Scope, Acceptance and Approvals
|  | PEC.SM.030 | Manage Scope | Managed Scope | 15 | 85
|  | PEC.SM.040 | Manage Acceptance | Managed Acceptance | 15 | 85
PEC.ACT.MPF Manage Project Finances
|  | PEC.FM.040 | Manage Project Finances | Managed Project Finances | 10 | 40 |  |  |  | 50
PEC.ACT.MPW Manage Project Workplan
|  | PEC.WM.030 | Manage Project Workplan | Project Workplan | 15 | 85
|  | PEC.WM.040 | Track Schedule Performance | Scheduled Performance | 15 | 85
|  | PEC.WM.070 | Schedule Workshop(s) |  | 15 | 85
PEC.ACT.MRIP Manage Risks, Issues and Problems
|  | PEC.RKM.040 | Manage Risk | Managed Risk | 15 | 85
|  | PEC.RKM.050 | Monitor and Control Risk | Assessed Risk | 15 | 85
|  | PEC.IPM.040 | Manage Issues and Problems | Managed Issues and Problems | 15 | 85
PEC.ACT.OMT Orient and Manage Team
|  | PEC.STM.050 | Conduct Team Orientation(s) | Oriented Team | 15 | 85
|  | PEC.STM.060 | Manage Project Team | Managed Project Team | 15 | 85
PEC.ACT.MCOP Manage Communications and OCM Plans
|  | PEC.CMM.030 | Manage Project Team Communication | Managed Project Team Communication | 10 | 65 |  |  |  | 25
|  | PEC.OCHM.030 | Execute Change and Communication Plan | Executed Change and Communication Plan | 15 | 85
PEC.ACT.MPQ Manage Project Quality
|  | PEC.QM.040 | Manage Quality Control | Quality Control | 15 | 85
|  | PEC.QM.050 | Perform Quality Assurance | Managed Quality Assurance | 15 | 85
PEC.ACT.CECRM Create and Execute Configuration and Release Management
|  | PEC.CM.040 | Create and Execute Software Configuration Management Plan | Software Configuration Management Plan | 15 | 75 |  | 5 | 5
|  | PEC.CM.050 | Create and Execute Software Release Management Plan | Software Release Management Plan | 15 | 75 |  | 5 | 5
|  | PEC.CM.060 | Create and Execute Environment and Patch Management Plan | Environment and Patch Management Plan | 5 | 15 |  | 30 | 50
|  | PEC.CM.070 | Create and Execute Configuration Management Control Plan | Configuration Management Control Plan | 15 | 75 |  | 5 | 5
PEC.ACT.MMI Manage and Maintain Infrastructure
|  | PEC.IFM.040 | Manage and Maintain Infrastructure | Maintained Infrastructure | 15 | 85
PEC.ACT.APGCS Administer Procurement of Goods and Contracted Services (Alternative Task Name) Specify Business Data for Configuration This is an Analysis and Design Activity
|  | PEC.PCM.030 | Administer Procurement of Goods and Contracted Services | Managed Procurement of Goods and Services | 15 | 85
PC Project Closure
PC.ACT.GA Gain Acceptance
|  | PC.SM.050 | Gain Acceptance | Final Acceptance Certificate | 15 | 85
PC.ACT.CPC Close Processes and Contract
|  | PC.SM.060 | Close Scope Management | Closed Scope Management | 15 | 85
|  | PC.SM.070 | Identify Future System Enhancements | Future System Enhancements | 15 | 85
|  | PC.FM.050 | Close Project Financials | Closed Project Financials | 15 | 85
|  | PC.WM.060 | Close Work Management | Closed Work Management | 15 | 85
|  | PC.RKM.060 | Conduct Post-Production Risk Assessment | Post-Production Risk Assessment | 15 | 85
|  | PC.IPM.050 | Produce Final Issue and Problem Report and Close Log(s) | Closed Issue and Problem Log | 15 | 85
|  | PC.STM.070 | Release Staff | Released Staff | 15 | 85
|  | PC.QM.060 | Conduct Post Production Quality Review | Post-Production Quality Review | 15 | 85
|  | PC.CM.080 | Close Configuration Management | Closed Configuration Management | 5 | 45 |  |  | 50
|  | PC.IFM.050 | Close Infrastructure | Closed Infrastructure | 15 | 85
|  | PC.PCM.040 | Close Contract | Closed Contract | 15 | 85
|  | PC.OCHM.040 | Establish Follow-Up Process | Follow-Up Process | 15 | 85
PC.ACT.DLLAP Document Lessons Learned and Archive Project
|  | PC.CMM.040 | Document Lessons Learned | Lessons Learned | 10 | 65 |  |  |  | 25
|  | PC.CMM.050 | Turn Over Project Documentation (Project Archives) | Project Archives | 15 | 85
|  | PC.CMM.060 | Submit Final Reports | Final Reports | 15 | 85

## Envision Task to Role Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | OUM WORK PRODUCT NAME | CMS | EA | SOLA | PAD | PM | SM | Other | Customer Roles
INIT Initiate
INIT.ACT.PEF Prepare Envision Foundation
|  | INIT.ER.010 | Create Business Case for Envision Engagement | Customer Envision Engagement Strategy |  | 80 |  |  |  | 20 |  | CS
|  | INIT.EA.001 | Justify and Engage Enterprise Architects | Assigned Enterprise Architect |  | 50 |  |  |  | 50
|  | INIT.ER.040 | Gather Enterprise Diagnostic Information | Enterprise Diagnostic Information |  | 50 |  |  |  | 50
|  | INIT.ER.045 | Establish Executive Sponsorship | Committed Executive Sponsorship |  | 100 |  |  |  |  | SM
|  | INIT.BA.010 | Identify Business Strategy | Business Strategy |  | 100 | [5 empty] | CEA, CS
|  | INIT.BA.012 | Define Business Scope | Business Scope |  | 100 | [5 empty] | CEA, CS
|  | INIT.BA.015 | Conduct Enterprise Stakeholder Assessment | Enterprise Stakeholder Inventory |  | 100 | [5 empty] | CEA, CS
|  | INIT.GV.010 | Define Governance Strategy | Governance Strategy |  | 60 (EA) 40 (BAR) | [5 empty] | CEA, CS
|  | INIT.BA.017.1 | Determine Metrics Collection and Reporting Strategy | Metrics Collection and Reporting Strategy |  | 100 | [5 empty] | CEA
|  | INIT.BA.018.1 | Establish Current Baseline Metrics | Current Baseline Metrics |  | 100 | [5 empty] | CEA
|  | INIT.BA.020 | Document Enterprise Organization Structures | Enterprise Organization Structures |  | 100 | [5 empty] | CEA
|  | INIT.BA.025 | Determine Operaing Model | Validated Operating Model |  | 100 | [5 empty] | CS
|  | INIT.EA.002 | Review External Reference Architectures | External Reference Architecture Review |  | 50 | 50
|  | INIT.ER.015 | Conduct Enterprise Maturity Assessment | Maturity Analysis and Recommendations Report |  | 100 | [5 empty] | CS
|  | INIT.ER.020 | Determine Envision Engagement Strategy | Envision Engagement Strategy |  | 80 |  |  |  | 20 | PM | CS
INIT.ACT.PD Prepare for Discovery
|  | INIT.EOCM.010 | Create and Manage Ad Hoc Communications | Ad Hoc Communications | 100 | [5 empty] | PM | CCS
|  | INIT.ER.025 | Educate Enterprise on Area of Focus | Educated Enterprise |  | 10 | 90 |  |  |  |  | CS
|  | INIT.ER.030 | Set and Agree on Plan for Envision Engagement | Envision Engagement Plan |  | 100 |  |  |  |  | PM
|  | INIT.ER.050 | Validate and Agree on Envision Engagement Plan | Agreed on Envision Engagement Plan |  | 100 |  |  |  |  | PM | CPM, CPS
INIT.ACT.CEAWE Conduct Executive Alignment Workshop - Envision
|  | INIT.EOCM.020 | Prepare for Executive Alignment Workshop | Executive Alignment Workshop Materials | 50 | 50 |  |  |  |  | PM | CPM, CPS
|  | INIT.EOCM.030 | Conduct Executive Alignment Workshop | Executive Business Objectives and Governance Rules | 100 | [5 empty] | PM | CPM, CPS
|  | INIT.EOCM.040 | Build and Deploy Sponsorship Program | Sponsorship Program | 70 | 30 |  |  |  |  | PM | CPM, CPS
INIT.ACT.DMCEC Define and Maintain Common Enterprise Concepts
|  | INIT.BA.030.1 | Develop Enterprise Glossary | Enterprise Glossary |  | 100 | [5 empty] | CEA
|  | INIT.EA.010.1 | Review Architecture Principles, Guidelines and Standards | Architecture Principles, Guidelines and Standards |  | 100 | [5 empty] | CEA
|  | INIT.ER.070 | Define Modeling Strategy for the Enterprise | Enterprise Modeling Strategy |  | 100 | [5 empty] | CEA
INIT.ACT.EDGI Execute Discovery - Gather Information (As Is)
|  | INIT.EOCM.050 | Assess Enterprise Change Readiness | Preliminary Enterprise Change Readiness Assessment | 100 | [5 empty] | PM
|  | INIT.EOCM.060 | Prepare Project Team for Enterprise Culture | Prepared Project Team | 100 | [5 empty] | PM
|  | INIT.EOCM.070 | Identify Change Agent Structure | Change Agent Structure | 100 | [5 empty] | PM | CCML, CPM, CPS
|  | INIT.ER.080 | Obtain Existing Reference Material | Existing Reference Material |  | 100
|  | INIT.ER.090 | Conduct Solution Readiness Assessment | Solution Readiness Assessment |  | 100
|  | INIT.GV.015 | Review Current Governance Model | Current Governance Model |  | 100 | [5 empty] | CEA
|  | INIT.GV.020.1 | Determine Regulatory and Business Mandates | Mandate Matrix |  | 100 (BAR) | [5 empty] | CEA
|  | INIT.BA.040 | Create Enterprise Function or Process Model | Enterprise Function or Process Model |  | 100 | [5 empty] | CEA
|  | INIT.BA.050 | Develop Enterprise Domain Model (Business Entities) | Enterprise Domain Model |  | 20 | 80 (IA) |  |  |  |  | CEA
|  | INIT.BA.055 | Develop Enterprise Knowledge Flow | Enterprise Knowledge Flow |  | 20 | 80 (IA) |  |  |  |  | CEA
|  | INIT.BA.058 | Develop Business Architecture | Business Architecture |  | 100 (BAR) | [5 empty] | CEA, CE
|  | INIT.BA.060.1 | Perform High-Level Use Case Discovery | High-Level Use Cases |  | 50 (EA) 50 (BAR) | [5 empty] | CEA
|  | INIT.EA.030 | Identify Current Enterprise Architecture | Current Enterprise Architecture |  | 100 (20-50) | 0 (50-80) |  |  |  |  | CEA
|  | INIT.EA.040 | Analyze Capabilities | Capability Analysis Results |  | 100 | [5 empty] | CEA
|  | INIT.GV.030.1 | Discover or Define Policies | Governance Policies Catalog |  | EA (20) BAR (80) | [5 empty] | CEA
|  | INIT.EA.050 | Identify Current Architectural Challenges | Current Architectural Challenges |  | 100 | [5 empty] | CEA
|  | INIT.GV.092 | Determine Projects Meta Data Description | Projects Meta Data Description |  | 100 | [5 empty] | CEA, CSOLA, CPM, CIO
|  | INIT.IP.010 | Inventory Projects | IT Project Portfolio |  | 100 | [5 empty] | CEA, CIO, CTO, CPMs
|  | INIT.GV.094 | Determine Applications Meta Data Description | Applications Meta Data Description |  | 100 | [5 empty] | CEA, CSOLA, CIO
|  | INIT.IP.012 | Inventory Applications | IT Application Portfolio |  | 80 | 20(AA) |  |  |  |  | CEA, CIO, CSE
|  | INIT.IP.015 | Conduct Portfolio Analysis | Portfolio Analysis Report |  | 100 | [5 empty] | CEA
|  | INIT.BA.065 | Review Business-IT SLA | Business-IT SLA Report |  | 50 (EA) 50 (BAR) | [5 empty] | CEA
|  | INIT.BA.067 | Review Business Volumetrics | Business Volumetrics Report |  | 100 | [5 empty] | CEA
|  | INIT.GV.096 | Determine Services Meta Data Description | Services Meta Data Description |  | 100 | [5 empty] | CEA, CSOLA, CSDLC, CIO
|  | INIT.GV.098 | Determine Other Meta Data Descriptions | Other Meta Data Descriptions |  | 100 | [5 empty] | CEA, CSOLA, CSDLC, CIO
|  | INIT.IP.014 | Inventory Services | Service Portfolio |  | 100 | [5 empty] | CEA, CTO, CSE, CPMs
|  | INIT.ER.100 | Define Supplemental Enterprise Requirements | Supplemental Enterprise Requirements |  | 50 | 50 |  |  |  |  | CEA, CS
|  | INIT.EA.057 | Review Business Capacity Plan | Business Capacity Plan |  | 20 | 80 (TA) |  |  |  |  | CSOLA
INIT.ACT.EDBPD Execute Discovery - Brainstorm, Prioritize and Discover Entry Points
|  | INIT.BA.045 | Develop Enterprise Business Context Diagram | Enterprise Business Context Diagram |  | 100 | [5 empty] | CEA
|  | INIT.GV.040 | Determine Organizational Impact of Governance | Impact Study and List of Proposed Organizational Changes |  | 30 (EA) 70 (BAR) | [5 empty] | CEA
|  | INIT.EA.060 | Identify Architectural Gaps and Improvement Options | Architectural Gaps and Improvement Options |  | 100 | [5 empty] | CEA
|  | INIT.EA.065 | Identify Enterprise IT Strategy | Enterprise IT Strategy |  | 100 | [5 empty] | CEA, CE
|  | INIT.ER.110.1 | Perform Benefit Analysis | Benefit Analysis |  | 100 | [5 empty] | CEA, CPM, CS
|  | INIT.BA.060.2 | Perform High-Level Use Case Discovery | High-Level Use Cases |  | 50 (EA) 50 (BAR) | [5 empty] | CEA
|  | INIT.EA.075 | Develop Technology Reference Architectures | Technology Reference Architectures |  | 20 | 80 (TA) |  |  |  |  | CEA
|  | INIT.BA.070 | Identify Candidate Services | Service Portfolio - Candidate Services |  | 50 | 50 (AA) |  |  |  |  | CSOLA
|  | INIT.IP.020 | Analyze Services | Service Portfolio - Proposed Services |  | 50 | 50 (AA) |  |  |  |  | CEA
|  | INIT.IP.025 | Populate Services Repository | Populated Services Repository |  | 30 | 70 (TA)
|  | INIT.BA.080 | Identify Candidate Enterprise Business Rules | Candidate Business Rules |  | 100 | [5 empty] | CSOLA
|  | INIT.IP.030 | Analyze Business Rules | Business Rules Analysis |  | 70 | 30 (AA) |  |  |  |  | CEA
|  | INIT.BA.090 | Identify Process Improvement Options | Process Improvement Options |  | 50 (EA) 50 (BAR | [5 empty] | CEA
|  | INIT.ER.120.1 | Identify and Mitigate Future State Risks | Future State Risks |  | 100 | [5 empty] | CEA
|  | INIT.ER.130.1 | Produce MoSCoW Improvement List | MoSCoW Improvement List |  | 100 | [5 empty] | CEA, CPS
|  | INIT.EA.095 | Review Enterprise Software Development Process | Enterprise Software Development Process |  | 50 | 50 |  |  |  |  | CSDLC
|  | INIT.IP.040 | Identify Candidate Projects | Candidate Projects |  | 100 | [5 empty] | CEA, CIO
INIT.ACT.EDF Execute Discovery - Finish
|  | INIT.ER.140 | Share Product Strategies with Enterprise | Informed Enterprise |  | 30 | 70 |  |  |  |  | CEA, CS
|  | INIT.ER.150 | Review Discovery Findings | Reviewed Discovery Findings |  | 90 |  |  |  | 10 |  | CEA, CPS
INIT.ACT.DSPC Develop Solution and Present to Customer
|  | INIT.GV.050.1 | Define Policy Implementation Processes | Policy Implementation Processes |  | 60 (EA) 40 (BAR) | [5 empty] | CEA
|  | INIT.GV.060.1 | Define Policy Implementation Tooling | Governance Policy Tooling |  | 20 | 80 |  |  |  |  | CEA
|  | INIT.GV.070.1 | Define Policy Metrics | Measurements Portfolio |  | 100 | [5 empty] | CEA
|  | INIT.GV.080.1 | Define Policy Monitoring Processes | Policy Monitoring Processes |  | 100 | [5 empty] | CEA, CPS
|  | INIT.GV.090.1 | Determine Funding Model | Funding Model |  | 100 (BAR) | [5 empty] | CEA, CPS, CIO
|  | INIT.GV.100.1 | Implement Governance | Governance Implementation |  | 100 | [5 empty] | CEA
|  | INIT.ER.160 | Develop Desired Future State | Desired Future State |  | 50 | 50 |  |  |  |  | CEA, CSOLA
|  | INIT.ER.165 | Identify Capability Challenges | Capability Challenges |  | 100 | [5 empty] | CEA, CS
|  | INIT.ER.167 | Determine Remediation Approaches | Remediation Approaches |  | 100 | [5 empty] | CEA
|  | INIT.EA.110 | Develop Future State Enterprise Architecture | Future State Enterprise Architecture |  | 100 | [5 empty] | CEA
|  | INIT.EA.120 | Develop Information Architecture | Information Architecture |  | 40 | 60 (IA) |  |  |  |  | CSOLA
|  | INIT.EA.130 | Develop Technology Architecture | Technology Architecture |  | 20 | 80 (TA) |  |  |  |  | CSOLA
|  | INIT.EA.140 | Develop Applications Architecture | Applications Architecture |  | 40 | 60 (AA) |  |  |  |  | CSOLA
|  | INIT.EA.150 | Define Transitional Architectures | Transitional Architectures |  | 100 | [5 empty] | CEA, CE
|  | INIT.EA.160 | Define Business Rules Implementation Strategy | Business Rules Implementation Strategy |  | 30 | 70 (TA)
|  | INIT.EA.170 | Identify Integration Requirements | Integration Requirements |  | 30 | 70
|  | INIT.ER.170 | Develop Future State Transition Plan | Future State Transition Plan |  | 60 | 40 |  |  |  |  | CEA
|  | INIT.IP.050.1 | Prioritize Projects | Prioritized Projects |  | 100 | [5 empty] | CEA, CIO
|  | INIT.ER.110.2 | Perform Benefit Analysis | Benefit Analysis |  | 100 | [5 empty] | CEA, CPM, CS
|  | INIT.IP.060 | Develop IT Portfolio Plan | IT Portfolio Plan |  | 40 |  |  | 60 |  |  | CS
|  | INIT.EA.190 | Define Product Implementation Prioritization | Product Implementation Prioritization |  | 40 60 (BAR) | [5 empty] | CEA
|  | INIT.ER.180 | Prepare for and Present Solution Recommendations | Solution Recommendations |  | 100 | [5 empty] | CEA, CS
|  | INIT.EA.200 | Determine Development Framework and Policy Guidelines | Development Framework |  | 100
INIT.ACT.PTI Plan Transition to Implementation
|  | INIT.ER.190 | Review Business Feedback and Identify Opportunities | Opportunities Task List |  | 80 |  |  |  | 20
|  | INIT.ER.200 | Prepare for Transition to Sales or Services | Opportunities Action Plan |  | 70 |  |  |  | 30 | PM
ME Maintain and Evolve
ME.ACT.ME Maintain and Evolve
|  | ME.BA.017.2 | Metrics Collection and Reporting Strategy | Determine Metrics Collection and Reporting Strategy |  | 100 | [5 empty] | CEA
|  | ME.BA.018.2 | Establish Current Baseline Metrics | Current Baseline Metrics |  | 100 | [5 empty] | CEA
|  | ME.BA.100 | Maintain Enterprise Business Models | Maintained Enterprise Business Models |  | 100 | [5 empty] | CEA
|  | ME.BA.110 | Maintain Business Rules | Maintained Business Rules |  | 100
|  | ME.BA.030.2 | Develop Enterprise Glossary | Enterprise Glossary |  | 100 | [5 empty] | CEA
|  | ME.EA.010.2 | Review Architecture Principles, Guidelines and Standards | Architecture Principles, Guidelines and Standards |  | 100 | [5 empty] | CEA
|  | ME.GV.020.2 | Determine Regulatory and Business Mandates | Mandate Matrix |  | 100 (BAR) | [5 empty] | CEA
|  | ME.GV.030.2 | Discover or Define Policies | Governance Policies Catalog |  | 20 (EA) 80 (BAR) | [5 empty] | CEA
|  | ME.GV.050.2 | Define Policy Implementation Processes | Policy Implementation Processes |  | 60 (EA) 40 (BAR) | [5 empty] | CEA
|  | ME.GV.060.2 | Define Policy Implementation Tooling | Governance Policy Tooling |  | 20 | 80 |  |  |  |  | CEA
|  | ME.GV.070.2 | Define Policy Metrics | Measurements Portfolio |  | 100 | [5 empty] | CEA
|  | ME.GV.080.2 | Define Policy Monitoring Procedures | Policy Monitoring Procedures |  | 100 | [5 empty] | CEA, CPS
|  | ME.GV.090.2 | Funding Model | Funding Model |  | 100 (BAR) | [5 empty] | CEA, CPS, CIO
|  | ME.GV.100.2 | Implement Governance | Governance Implementation |  | 100 | [5 empty] | CEA
|  | ME.GV.110 | Monitor, Analyze and Improve Governance Processes | Governance Implementation Improvement Proposal |  | 100 | [5 empty] | CEA
|  | ME.ER.120.2 | Identify and Mitigate Future Enterprise Architecture Risks | Future Architectural Risks |  | 100 | [5 empty] | CEA
|  | ME.ER.130.2 | Produce MoSCoW Improvement List | MoSCoW Improvement List |  | 100 | [5 empty] | CEA, CPS
|  | ME.EA.210 | Maintain Enterprise Architectural Models | Maintained Enterprise Architectural Models |  |  | 100 |  |  |  |  | CEA
|  | ME.IP.050.2 | Prioritize Projects | Prioritized Projects |  | 100 | [5 empty] | CEA, CIO
|  | ME.IP.070 | Execute and Maintain IT Portfolio and Programs | Maintained IT Portfolio and Programs |  | 20 |  |  | 80
|  | ME.IP.080 | Maintain Repository of Artifacts | Maintained Repository of Artifacts |  | 100 | [5 empty] | CERM
|  | ME.ER.210 | Monitor Current Situation and Pursue Relevant Updates | Monitored Current Situation |  | 100 |  |  |  |  | SOLA | CPS

## Implement Task to Role Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | OUM WORK PRODUCT NAME | APS | BA | CMS | DBA | DD | DES | DV | NE | QM | SAD | SAN | SA | TRS | TE | TW | ENV Role | Other | Customer Roles
A Inception
A.ACT.GBRI Gather Business Requirements - Inception
|  | A.RD.001 | Detail Business and System Objectives | Business and System Objectives |  | 100 | [14 empty] | PS | KEY, VS, CPM
|  | A.RD.003 | Identify Viewpoints | Viewpoint List | [15 empty] | 100 (EA) | PM
|  | A.RD.005 | Create System Context Diagram | System Context Diagram |  | 100 | [15 empty] | KEY
|  | A.RD.011.1 | Develop Future Process Model | Future Process Model | 10 | 90 | [14 empty] | PS | BLM, KEY
|  | A.RD.020 | Obtain High-Level Business Descriptions | High-Level Business Descriptions |  | 100 | [15 empty] | KEY, USR,
|  | A.RA.010 | Simulate Business Process | Business Process Simulation |  | 100 | [15 empty] | KEY
|  | A.RA.015 | Develop Business Use Case Model | Business Use Case Model |  | 100 | [15 empty] | KEY
|  | A.RD.065 | Develop Domain Model (Business Entities) (Class Diagram) | Domain Model |  | 100 |  |  |  | Advisory | [11 empty] | KEY
|  | A.RD.012 | Document Present and Future Organization Structures | Present and Future Organization Structures |  | 100 | [15 empty] | KEY, OS
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy | Key Business Strategies and Objectives | 30 | 70 | [15 empty] | CSM, USR
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model | Current Process Model |  | 100 | [14 empty] | PS | BLM, USR
|  | A.RD.034 | Document Current Business Baseline Metrics | Current Business Baseline Metrics |  | 100 | [14 empty] | PS | USR
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary | Glossary |  | 100 | [15 empty] | KEY, SS
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW) | MoSCoW List |  | 100 | [15 empty] | KEY
|  | A.RD.055 | Detail Supplemental Requirements | Supplemental Requirements |  | 80 | [9 empty] | 20 | [5 empty] | KEY
|  | A.RD.130.1 | Develop Baseline Architecture Description | Architecture Description |  | 20 | [9 empty] | 80 | [5 empty] | KEY
|  | A.RA.019 | Define Project Reference Architecture | Project Reference Architecture | [11 empty] | 100
|  | A.RA.021.1 | Tell User Story | User Story |  | 60 | [8 empty] | 40 | [5 empty] | PM | KEY
|  | A.RA.023.1 | Develop Use Case Model | Use Case Model | [10 empty] | 100 | [6 empty] | KEY
|  | A.RA.025.1 | Identify Candidate Services | Service Portfolio - Candidate Services |  | 50 | [9 empty] | 50
|  | A.RA.027.1 | Identify Candidate Business Rules | Candidate Business Rules |  | 100
|  | A.RA.028.1 | Populate Business Rules Repository | Populated Business Rules Repository |  | 100
A.ACT.PSUIA Perform Software Upgrade Impact Analysis
|  | A.TA.004 | Perform Technical Architecture Impact Analysis | Technical Architecture Impact Analysis |  | minimal |  | 10 | [5 empty] | 10 |  | 80
|  | A.RD.134 | Identify New Software Release Changes | Software Release Changes Summary |  | 80 | [7 empty] | minimal |  | 20
|  | A.RD.136 | Perform Custom Extension Impact Analysis | Custom Extension Impact Analysis | 50 | [10 empty] | 50 | [5 empty] | CPM
|  | A.RD.138 | Perform Data Impact Analysis | Data Impact Analysis | 30 | [10 empty] | 70
|  | A.MC.090.1 | Conduct Reporting Fit Analysis | Reporting Fit Analysis | 30 | 45 | [9 empty] | 25 | [5 empty] | KEY
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification | Requirements Specification |  | 80 | [9 empty] | 20 | [5 empty] | KEY
|  | A.RD.150.1 | Review Requirements Specification | Reviewed Requirements Specification |  | 20 |  |  |  | 20 |  |  |  |  | 20 | 40 | [5 empty] | KEY
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype | Conceptual Prototype | [6 empty] | 80 |  |  |  | 20 | [6 empty] | KEY
|  | A.RA.030.1 | Validate Conceptual Prototype | Validated Conceptual Prototype | [6 empty] | 90 |  |  |  | 10 | [6 empty] | KEY
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements | Data Acquisition and Conversion Requirements | 20 | [9 empty] | 80 | [6 empty] | CDA, KEY
|  | A.TE.005.1 | Determine Testing Requirements | Testing Requirements | [10 empty] | 100 | [6 empty] | KEY
|  | A.PT.010 | Conduct Performance Management Workshop | Performance Management Workshop Results |  | 5 |  |  |  |  | 5 |  |  |  |  | 90 | [5 empty] | KEY, CPM, CDA, CSM, OS, SS
|  | A.TA.010 | Conduct Technical Architecture Workshop | Technical Architecture Workshop Results |  | 5 |  |  |  |  | 5 |  |  |  | 5 | 85 | [5 empty] | CPM, KEY, CDA, OS, SS
|  | A.DO.010 | Define Documentation Requirements and Strategy | Documentation Requirements and Strategy |  | 30 | [12 empty] | 70 |  |  | BLM, CPM
|  | A.RD.070 | Determine Audit and Control Requirements | Audit and Control Requirements |  | 100 | [15 empty] | BLM, KEY
A.ACT.SKSD Specify Key Structure Definition
|  | A.MC.010.1 | Define Business Data Structures | Business Data Structures | 20 | 30 | [9 empty] | 50 | [5 empty] | KEY
|  | A.MC.020 | Define Business Data Structure Setups | Business Data Structure Setups |  | 40 | [9 empty] | 60 | [5 empty] | KEY
A.ACT.CMAHC Create and Manage Ad Hoc Communications
|  | A.OCM.010 | Create and Manage Ad Hoc Communications | Ad Hoc Communications |  |  | 100 | [13 empty] | PM | CCS
A.ACT.CEAW Conduct Executive Alignment Workshop
|  | A.OCM.020 | Prepare for Executive Alignment Workshop | Executive Alignment Workshop Materials |  |  | 50 | [8 empty] | 50 |  |  |  |  | PM | CPS, CPM
|  | A.OCM.030 | Conduct Executive Alignment Workshop | Executive Business Objectives and Governance Rules |  |  | 100 | [13 empty] | PM | CPS, CPM
|  | A.OCM.040 | Build and Deploy Sponsorship Program | Sponsorship Program |  |  | 70 | [8 empty] | 30 |  |  |  |  | PM | CPS, CPM
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy | Education and Training Strategy | [12 empty] | 100 |  |  |  |  | BLM, CPM
|  | A.TR.020 | Prepare Project Team Learning Plan | Project Team Learning Plan |  | 30 | [10 empty] | 70 |  |  |  |  | CSM, CPS
|  | A.TR.030 | Prepare Project Team Learning Environment | Project Team Learning Environment |  | 15 |  | 25 | [5 empty] | 35 |  |  | 15 |  |  |  |  | CSM, USR
|  | A.TR.040 | Develop Project Team Learningware | Project Team Learningware |  | 45 | [10 empty] | 30 |  | 25 |  |  | SS, USR
|  | A.TR.050 | Conduct Project Team Learning Events | Skilled Project Team | [12 empty] | 100 |  |  |  |  | USR
A.ACT.CAWI Conduct Alignment Workshops - Inception
|  | A.OCM.050 | Prepare for Team-Building Workshop | Team-Building Workshop Materials |  |  | 100 | [13 empty] | PM
|  | A.OCM.060 | Conduct Team-Building Workshop | Cohesive Project Team |  |  | 100 | [13 empty] | PM
|  | A.OCM.070 | Design Managers Project Alignment Workshop | Managers Project Alignment Workshop Materials |  |  | 100 | [13 empty] | PM | CPM
|  | A.OCM.080 | Conduct Managers Project Alignment Workshop | Aligned Managers |  |  | 100 | [13 empty] | PM | CPM
|  | A.OCM.090 | Design Change Agent Workshop | Change Agent Workshop Materials |  |  | 100 | [13 empty] | PM | CCML, CPM
|  | A.OCM.100 | Conduct Change Agent Workshop | Enabled Change Agents |  |  | 100 | [13 empty] | PM | CPM
A.ACT.CCRA Conduct Change Readiness Assessment
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools | Change Readiness Assessment Strategy and Tools |  |  | 100 | [13 empty] | PM | CPS, CCML, CPM, CAT
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data | Readiness Assessment Analysis and Recommendations |  |  | 100 | [13 empty] | PM | CPS, CCML, CPM, CAT
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap | Communication Strategy and Change Management Roadmap |  |  | 100 | [13 empty] | PM | CPS, CPM
A.ACT.DCMRCCI Deploy Change Management Roadmap and Communication Campaign - Inception
|  | A.OCM.140 | Develop Communication Campaign | Communication Campaign |  |  | 100 | [14 empty] | CCS
|  | A.OCM.150.1 | Conduct Change Management Roadmap and Communication Campaign | Change Management Roadmap and Communication Events |  |  | 100 | [13 empty] | PM | CCS, CPM
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy | Application Extension Strategy |  | 25 | [9 empty] | 75 |  |  |  |  | PS | CPM
|  | B.TE.005.2 | Determine Testing Requirements | Testing Requirements | [10 empty] | 100 | [6 empty] | KEY
|  | B.TE.010 | Develop Testing Strategy | Testing Strategy | [13 empty] | 100
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy | Data Acquisition, Conversion and Data Quality Strategy | 20 | [10 empty] | 80 (IA) | [5 empty] | CDA, CDAR, OS, USR
|  | B.DO.020 | Define Documentation Standards and Procedures | Documentation Standards and Procedures | [14 empty] | 100 |  |  | BLM, CPM
|  | B.TR.010.2 | Define Training Strategy | Education and Training Strategy | [12 empty] | 100 |  |  |  |  | BLM, CPM
|  | B.TS.020.1 | Define Cutover Strategy | Cutover Strategy | [10 empty] | 100 | [6 empty] | BLM, CPM, SS, USR
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy | Technical Architecture Requirements and Strategy |  | 5 | [5 empty] | 5 |  |  |  | 90 | [5 empty] | SS, CPM
|  | B.TA.030 | Define Integration Requirements and Strategy | Integration Architecture Strategy | [11 empty] | 100 | [5 empty] | SS
|  | B.TA.040 | Define Reporting and Information Access Strategy | Reporting and Information Access Strategy |  | 20 | [9 empty] | 80 | [5 empty] | SS
|  | B.TA.050 | Define Disaster Recovery Strategy | Disaster Recovery Strategy | [10 empty] | 10 | 90 | [5 empty] | CPS, OS, SS, KEY
|  | B.TA.060 | Define System Operations and Management Strategy | System Operations and Management Strategy | [11 empty] | 100 | [5 empty] | OS
|  | B.TA.070 | Define Initial Architecture and Application Mapping | Initial Architecture and Application Mapping | [11 empty] | 100 | [5 empty] | SS
|  | B.TA.080 | Define Backup and Recovery Strategy | Backup and Recovery Strategy | [10 empty] | 10 | 90 | [5 empty] | OS, SS
|  | B.TA.090 | Develop Security and Control Strategy | Security and Control Strategy | 20 | [10 empty] | 80 | [5 empty] | AU, SS
B.ACT.PEE Prepare Environments-Elaboration
|  | B.IM.007.1 | Prepare Development Environment | Development Environment |  |  |  | 25 | [5 empty] | 50 |  | 25 | [5 empty] | CSM
|  | B.TE.018.1 | Prepare Static Test Data | Static Test Data |  |  |  |  | 50 | [6 empty] | 50 (IA) | [5 empty] | CDA, KEY
|  | B.TE.038.1 | Prepare Integration Test Environment | Integration Test Environment | [9 empty] | 40 |  | 20 20 (IA) |  | 20 |  |  |  | OS. SS
|  | B.TE.060.1 | Prepare System Test Environment | System Test Environment | [9 empty] | 50 |  | 20 20 (IA) |  | 20 |  |  |  | OS, SS
|  | B.CV.030.1 | Prepare Conversion Environment (Initial Load) | Conversion Environment (Initial Load) |  |  |  | 30 | [5 empty] | 60 |  | 10
|  | B.DO.040 | Prepare Documentation Environment | Documentation Environment | [9 empty] | 80 |  |  |  |  | 20 |  |  | CSM
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Develop Future Process Model | Future Process Model | 10 | 90 | [14 empty] | PS | BLM, KEY
|  | B.RA.055.1 | Document Business Procedures | Business Procedure Documentation |  | 80 |  |  |  |  | 20 | [10 empty] | BLM
|  | B.MC.030 | Map Business Requirements | Mapped Business Requirements | 25 | 50 | [9 empty] | 25 | [5 empty] | BLM, KEY
|  | B.TA.006 | Define Technical Prototype Subprojects | Technical Prototype Approach |  | 15 | [8 empty] | 15 | 70 | [5 empty] | CPM
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan | Integration Test Plan | [13 empty] | 100
|  | B.TE.050.1 | Develop System Test Plan | System Test Plan | [13 empty] | 100
|  | B.TE.080 | Develop Systems Integration Test Plan | Systems Integration Test Plan | [13 empty] | 100
|  | B.TE.082 | Develop Acceptance Test Plan | Acceptance Test Plan | [10 empty] | 25 |  |  | 75 |  |  |  | VC
B.ACT.SSC Specify Software Configuration (Multiply Instantiated) (Alternative Task Name) Specify Business Data for Configuration This is an Analysis and Design Activity
|  | B.MC.010.2 | Define Business Data Structures | Business Data Structures | 20 | 30 | [9 empty] | 50 | [5 empty] | KEY
|  | B.MC.040 | Gather Setup Information | Setup Information | 50 | 50 | [15 empty] | BLM, KEY
|  | B.MC.050.1 | Define Application Setups | Application Setup Documents | 40 | 50 | [7 empty] | 10 | [7 empty] | BLM, KEY
|  | B.MC.055 | Document Application Configuration Changes | Application Configuration Change Document | 40 | 50 | [7 empty] | 10 | [7 empty] | BLM, KEY
|  | B.MC.060 | Document Functional Security | Functional Security Setup Inforamtion | 30 | 60 | [7 empty] | 10
B.ACT.PVC Prototype and Validate Configuration This is an Analysis and Design Activity
|  | B.TE.025.1 | Create System Test Scenarios | System Test Scenarios | [10 empty] | 20 |  |  | 80 |  |  |  | KEY
|  | B.MC.070 | Prepare Configuration Prototype Environment | Configuration Prototype Environment | 30 | 35 |  | 25 | [5 empty] | 10 | [7 empty] | CSM
|  | B.MC.080 | Conduct Configuration Prototyping Workshop | Validated Configuration | 30 | 50 | [7 empty] | 10 |  | 10 | [5 empty] | CSM, KEY
|  | B.MC.090.2 | Conduct Reporting Fit Analysis | Reporting Fit Analysis | 30 | 45 | [9 empty] | 25 | [5 empty] | KEY
B.ACT.PGA Perform Gap Analysis
|  | B.MC.100 | Define and Estimate Application Extensions | Application Extension Definition and Estimates |  | 20 | [9 empty] | 80 |  |  |  |  | PS | BLM, CPM
|  | B.MC.110 | Define Gap Resolutions | Gap Resolutions | 25 | 50 | [9 empty] | 25 | [5 empty] | BLM
B.ACT.DUCM Develop Use Case Model
|  | B.RA.021.2 | Tell User Story | User Story |  | 60 | [8 empty] | 40 | [5 empty] | PM | KEY
|  | B.RA.023.2 | Develop Use Case Model | Use Case Model | [10 empty] | 100 | [6 empty] | KEY
B.ACT.CCPE Create Conceptual Prototype - Elaboration
|  | B.IM.005.2 | Develop Conceptual Prototype | Conceptual Prototype | [6 empty] | 80 |  |  |  | 20 | [6 empty] | KEY
|  | B.RA.030.2 | Validate Conceptual Prototype | Validated Conceptual Prototype | [6 empty] | 90 |  |  |  | 10 | [6 empty] | KEY
B.ACT.CS Consolidate Specification
|  | B.RD.042.2 | Develop Glossary | Glossary |  | 100 | [15 empty] | KEY, SS
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW) | MoSCoW List |  | 100 | [15 empty] | KEY
|  | B.RD.140.2 | Create Requirements Specification | Requirements Specification |  | 80 | [9 empty] | 20 | [5 empty] | KEY
|  | B.RD.150.2 | Review Requirements Specification | Reviewed Requirements Specification |  | 20 |  |  |  | 20 |  |  |  |  | 20 | 40 | [5 empty] | KEY
|  | B.RA.025.2 | Identify Candidate Services | Service Portfolio - Candidate Services |  | 50 | [9 empty] | 50
|  | B.RA.027.2 | Identify Candidate Business Rules | Candidate Business Rules |  | 100
|  | B.RA.028.2 | Populate Business Rules Repository | Populated Business Rules Repository |  | 100
|  | B.RA.180.1 | Review Use Case Model | Reviewed Use Case Model | [6 empty] | 25 |  | 25 |  | 25 | 25
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description | Architecture Description | [10 empty] | 20 | 80 | [5 empty] | KEY
|  | B.AN.040.1 | Develop Analysis Architecture Description | Architecture Description | [6 empty] | 20 |  |  |  |  | 80
|  | B.DS.040.1 | Develop Design Architecture Description | Architecture Description | [6 empty] | 20 |  |  |  |  | 80
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details | Use Case Specification | [10 empty] | 100 | [6 empty] | KEY
B.ACT.AE Analyze - Elaboration
|  | B.AN.035.1 | Update Existing Analysis Specification | Updated Analysis Specification |  | 100 | [15 empty] | KEY
|  | B.AN.050.1 | Analyze Data | Data Analysis | [10 empty] | 40 | 60
|  | B.AN.060.1 | Analyze Behavior | Behavior Analysis | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | B.AN.070.1 | Analyze Business Rules | Business Rules Analysis |  | 100
|  | B.AN.080.1 | Analyze Services | Service Portfolio – Proposed Services |  | 50 | [9 empty] | 50
|  | B.AN.085.1 | Define Service | Service Definition |  | 50 | [9 empty] | 50
|  | B.RA.026.1 | Populate Services Repository | Populated Services Repository | [11 empty] | 100
|  | B.AN.090.1 | Analyze User Interface | User Interface Analysis |  | 100 | [15 empty] | USR
|  | B.AN.100.1 | Prepare Analysis Specification | Analysis Specification |  | 100 | [15 empty] | KEY
|  | B.AN.110.1 | Review Analysis Model | Reviewed Analysis Model | [5 empty] | 20 | 20 |  | 20 |  | 20 | 20 | [5 empty] | KEY
B.ACT.DE Design - Elaboration
|  | B.DS.035.1 | Update Existing Design Specification | Updated Design Specification |  |  |  |  | 10 | 20 | [5 empty] | 70
|  | B.DS.050 | Determine Design and Build Standards | Design and Build Standards | [6 empty] | 100
|  | B.DS.060 | Define Business Rules Implementation Strategy | Business Rules Implementation Strategy | 10 | 55 | [9 empty] | 35
|  | B.DS.070.1 | Define SOA Implementation Strategy | SOA Implementation Strategy | [11 empty] | 100
|  | B.DS.080.1 | Design Software Components | Software Component Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | B.DS.090.1 | Design Data | Component Data Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | B.DS.100.1 | Design Behavior | Component Behavior Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | B.DS.110.1 | Design Business Rules | Business Rules Design |  | 100
|  | B.DS.120.1 | Design Services | Service Design | [5 empty] | 100
|  | B.DS.130.1 | Design User Interface | User Interface Design | [5 empty] | 100 | [11 empty] | KEY
|  | B.DS.140.1 | Prepare Design Specification | Design Specification |  |  |  |  | 10 | 20 | [5 empty] | 70
|  | B.DS.150.1 | Develop Database Design | Logical Database Design |  |  |  |  | 60 |  | 20 |  |  |  |  | 20
|  | B.DS.160.1 | Review Design Model | Reviewed Design Model |  |  |  |  | 25 |  | 25 |  | 25 |  |  | 25 | [5 empty] | KEY
B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration
|  | B.TE.020.1 | Develop Unit Test Scripts | Unit Test Scripts |  | 10 |  |  |  |  | 80 |  |  |  | 10
|  | B.TE.035.1 | Create Integration Test Scenarios | Integration Test Scenarios | [13 empty] | 100
B.ACT.DSTSE Develop System Test Scenarios – Elaboration
|  | B.TE.025.2 | Create System Test Scenarios | System Test Scenarios | [10 empty] | 20 |  |  | 80 |  |  |  | KEY
B.ACT.DVCSP Develop and Validated Custom Software Prototypes
|  | B.IM.010 | Develop Functional Prototype | Functional Prototype | [6 empty] | 80 |  |  |  | 20 | [6 empty] | KEY
|  | B.RA.085 | Validate Functional Prototype | Validated Functional Prototype | [6 empty] | 80 |  |  |  | 20 | [6 empty] | KEY
|  | B.IM.020 | Develop Architectural Foundation | Architectural Foundation | [6 empty] | 60 |  |  |  |  | 40 | [5 empty] | KEY
|  | B.IM.085 | Develop User Interface Standards Prototype | User Interface Standards Prototype | [10 empty] | 20 | 80 | [5 empty] | KEY
|  | B.RA.095 | Validate User Interface Standards Prototype | Validated User Interface Standards Prototype | [6 empty] | 80 |  |  |  | 20 | [6 empty] | KEY
|  | B.IM.040.1 | Implement Database | Implemented Database |  |  |  | 20 | 20 |  | 50 |  |  |  |  | 10 (IA)
|  | B.IM.053.1 | Register Services | Populated Services Registry |  | 100
|  | B.IM.055.1 | Perform Business Rules Implementation (Rules Engine) | Implemented Business Rules (Rules Engine) |  | 100
|  | B.IM.060.1 | Perform Component Review | Component Review Results | [6 empty] | 80 |  | 10 |  |  | 10
B.ACT.PCCTE Perform Custom Component Testing - Elaboration
|  | B.TE.030.1 | Perform Unit Test | Unit-Tested Components | [6 empty] | 80 |  |  |  | 20
|  | B.TE.040.1 | Perform Integration Test | Integration-Tested Components | [13 empty] | 100 |  |  |  | KEY
|  | B.TE.045 | Validate Integration Packages | Validated Integrations | [17 empty] | customer and the consulting organization implementation team share responsibility
B.ACT.PSTE Perform System Test – Elaboration
|  | B.TE.070.1 | Perform System Test | System-Tested Applications | [13 empty] | 100 |  |  |  | KEY
B.ACT.VUPE Validate Upgrade Process - Elaboration
|  | B.TE.072.1 | Test Pre-Upgrade Steps | Pre-Upgrade Checklist | [11 empty] | 100
|  | B.TE.073.1 | Test Packaged Software Upgrade | Packaged Software Upgrade Checklist | [11 empty] | 100
|  | B.TE.074.1 | Test Post-Upgrade Steps | Post-Upgrade Checklist | [11 empty] | 100
|  | B.TE.075.1 | Perform Post-Upgrade Reconciliation Testing | Reconciliation Test Report | [11 empty] | 100
|  | B.TE.076.1 | Review Upgrade Test Results | Upgrade Test Analysis | [11 empty] | 100
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy | Performance Management Requirements and Strategy | [6 empty] | 10 |  |  |  |  | 90 | [5 empty] | KEY
|  | B.PT.030 | Define Performance Testing Strategy | Performance Testing Strategy | [11 empty] | 100 | [5 empty] | KEY
|  | B.PT.040 | Identify Performance Testing Models and Scenarios | Performance Testing Models and Scenarios | [10 empty] | 20 | 80
|  | B.PT.050 | Design Performance Test Scripts and Programs | Performance Test Scripts and Programs Design | [11 empty] | 20 |  | 80
|  | B.PT.060 | Design Performance Test Data and Load Programs | Performance Test Data and Load Programs Design | [11 empty] | 30 10 (IA) |  | 60 |  |  |  | KEY
B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration
|  | B.CV.025 | Define Data Acquisition and Conversion Standards | Data Acquisition and Conversion Standards | [11 empty] | 100 | [5 empty] | ISM
|  | B.RA.160 | Conduct Business Data Source Gap Analysis | Business Data Source Gap Analysis | 20 | [10 empty] | 80 (IA) | [5 empty] | CDA
|  | B.CV.027.1 | Perform Data Mapping | Data Mapping | [11 empty] | 100 (IA) | [5 empty] | CDA
|  | B.RA.170.1 | Conduct Data Quality Assessment | High-Level Data Quality Assessment | [11 empty] | 100 (IA) | [5 empty] | CDA, KEY
|  | B.CV.035.1 | Define Manual Conversion Procedures (Initial Load) | Manual Conversion Procedures (Initial Load) |  | 100 | [15 empty] | CPM, CSM
|  | B.CV.040.1 | Design Conversion Components (Initial Load) | Conversion Component Designs (Initial Load) |  | 80 | [9 empty] | 20 (IA) | [5 empty] | CDA, CSA
|  | B.CV.050.1 | Prepare Conversion Test Plans (Initial Load) | Conversion Test Plans (Initial Load) |  | 20 | [9 empty] | 80
|  | B.CV.055.1 | Implement Conversion Components (Initial Load) | Conversion Componets (Initial Load) | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | OS
|  | B.CV.060.1 | Perform Conversion Component Unit Test (Initial Load) | Unit-Tested Conversion Components (Initial Load) | [6 empty] | 100
|  | B.CV.062.1 | Perform Conversion Component Business Object Test (Initial Load) | Business Object-Tested Conversion Components (Initial Load) | [11 empty] | 10 |  | 90
|  | B.CV.063.1 | Perform Conversion Component Validation Test (Initial Load) | Validation-Tested Conversion Components (Initial Load) |  | 30 | [9 empty] | 10 |  | 60
B.ACT.PBPII Prepare Business Process Impact Inventory
|  | B.OCM.160 | Prepare Business Process Impact Inventory | Business Process Impact Inventory |  | minimal | 100 | [14 empty] | BLM
B.ACT.DCMRCCE Deploy Change Management Roadmap and Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap and Communication Campaign | Change Management Roadmap and Communication Events |  |  | 100 | [13 empty] | PM | CCS, CPM
|  | B.OCM.155.1 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Change Management Roadmap and Communication Campaign Effectiveness Assessment |  |  | 100 | [13 empty] | PM | CCS, CPM
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone | Lifecycle Architecture Milestone
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary | Glossary |  | 100 | [15 empty] | KEY, SS
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW) | MoSCoW List |  | 100 | [15 empty] | KEY
|  | C.RD.130.2 | Develop Baseline Architecture Description | Architecture Description |  | 20 | [9 empty] | 80 | [5 empty] | KEY
|  | C.RA.021.3 | Tell User Story | User Story |  | 60 | [8 empty] | 40 | [5 empty] | PM | KEY
|  | C.RA.023.3 | Develop Use Case Model | Use Case Model | [10 empty] | 100 | [6 empty] | KEY
|  | C.RA.024.2 | Develop Use Case Details | Use Case Specification | [10 empty] | 100 | [6 empty] | KEY
|  | C.RA.025.3 | Identify Candidate Services | Service Portfolio - Candidate Services |  | 50 | [9 empty] | 50
|  | C.RA.027.3 | Identify Candidate Business Rules | Candidate Business Rules |  | 100
|  | C.RA.028.3 | Populate Business Rules Repository | Populated Business Rules Repository |  | 100
|  | C.RA.180.2 | Review Use Case Model | Reviewed Use Case Model | [6 empty] | 25 |  | 25 |  | 25 | 25
C.ACT.AC Analyze - Construction
|  | C.AN.035.2 | Update Existing Analysis Specification | Updated Analysis Specification |  | 100 | [15 empty] | KEY
|  | C.AN.040.2 | Develop Analysis Architecture Description | Architecture Description | [6 empty] | 20 |  |  |  |  | 80
|  | C.AN.050.2 | Analyze Data | Data Analysis | [10 empty] | 40 | 60
|  | C.AN.060.2 | Analyze Behavior | Behavior Analysis | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | C.AN.070.2 | Analyze Business Rules | Business Rules Analysis |  | 100
|  | C.AN.080.2 | Analyze Services | Service Portfolio – Proposed Services |  | 50 | [9 empty] | 50
|  | C.AN.085.2 | Define Service | Service Definition |  | 50 | [9 empty] | 50
|  | C.RA.026.2 | Populate Services Repository | Populated Services Repository | [11 empty] | 100
|  | C.AN.090.2 | Analyze User Interface | User Interface Analysis |  | 100 | [15 empty] | USR
|  | C.AN.100.2 | Prepare Analysis Specification | Analysis Specification |  | 100 | [15 empty] | KEY
|  | C.AN.110.2 | Review Analysis Model | Reviewed Analysis Model | [5 empty] | 20 | 20 |  | 20 |  | 20 | 20 | [5 empty] | KEY
C.ACT.DC Design - Construction
|  | C.DS.035.2 | Update Existing Design Specification | Updated Design Specification |  |  |  |  | 10 | 20 | [5 empty] | 70
|  | C.DS.040.2 | Develop Design Architecture Description | Architecture Description | [6 empty] | 20 |  |  |  |  | 80
|  | C.DS.080.2 | Design Software Components | Software Component Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | C.DS.090.2 | Design Data | Component Data Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | C.DS.100.2 | Design Behavior | Component Behavior Design | [5 empty] | 60 | 20 |  |  |  |  | 20
|  | C.DS.110.2 | Design Business Rules | Business Rules Design |  | 100
|  | C.DS.120.2 | Design Services | Service Design | [5 empty] | 100
|  | C.DS.130.2 | Design User Interface | User Interface Design | [5 empty] | 100 | [11 empty] | KEY
|  | C.DS.140.2 | Prepare Design Specification | Design Specification |  |  |  |  | 10 | 20 | [5 empty] | 70
|  | C.DS.150.2 | Develop Database Design | Logical Database Design |  |  |  |  | 60 |  | 20 |  |  |  |  | 20
|  | C.DS.160.2 | Review Design Model | Reviewed Design Model |  |  |  |  | 25 |  | 25 |  | 25 |  |  | 25 | [5 empty] | KEY
C.ACT.PTP Perform Test Planning
|  | C.TE.015.2 | Develop Integration Test Plan | Integration Test Plan | [13 empty] | 100
|  | C.TE.050.2 | Develop System Test Plan | System Test Plan | [13 empty] | 100
C.ACT.PEC Prepare Environments - Construction
|  | C.IM.007.2 | Prepare Development Environment | Development Environment |  |  |  | 25 | [5 empty] | 50 |  | 25 | [5 empty] | CSM
|  | C.TE.018.2 | Prepare Static Test Data | Static Test Data |  |  |  |  | 50 | [6 empty] | 50 (IA) | [5 empty] | CDA, KEY
|  | C.TE.038.2 | Prepare Integration Test Environment | Integration Test Environment | [9 empty] | 40 |  | 20 20 (IA) |  | 20 |  |  |  | OS. SS
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Develop Unit Test Scripts | Unit Test Scripts |  | 10 |  |  |  |  | 80 |  |  |  | 10
|  | C.TE.035.2 | Create Integration Test Scenarios | Integration Test Scenarios | [13 empty] | 100 |  |  |  | KEY
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios | System Test Scenarios | [10 empty] | 20 |  |  | 80 |  |  |  | KEY
C.ACT.DSITS Develop Systems Integration Test Scenarios
|  | C.TE.090 | Develop Systems Integration Test Scenarios | Systems Integration Test Scenarios | [13 empty] | 100 |  |  |  | KEY
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database | Implemented Database |  |  |  | 20 | 20 |  | 50 |  |  |  |  | 10 (IA)
|  | C.IM.050 | Implement Components | Implemented Components | [6 empty] | 80 |  |  |  |  | 20
|  | C.IM.053.2 | Register Services | Populated Services Registry |  | 100
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine) | Implemented Business Rules (Rules Engine) |  | 100
|  | C.IM.060.2 | Perform Component Review | Component Review Results | [6 empty] | 80 |  | 10 |  |  | 10
|  | C.IM.070 | Assemble Components | Assembled Components | [6 empty] | 80 |  |  |  |  | 20
|  | C.IM.080 | Integrate Services | Integrated Services | [11 empty] | 100
|  | C.IM.090 | Create Installation Routines | Installation Routines | [6 empty] | 100
|  | C.TE.065 | Perform Installation Test | Tested Installation Routines | [6 empty] | 20 |  |  | 80
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test | Unit-Tested Components | [6 empty] | 80 |  |  |  | 20
|  | C.TE.040.2 | Perform Integration Test | Integration-Tested Components | [13 empty] | 100
C.ACT.PST Prepare for System Test
|  | C.MC.050.2 | Define Application Setups | Application Setup Documents | 40 | 50 | [7 empty] | 10
|  | C.TE.060.2 | Prepare System Test Environment | System Test Environment | [9 empty] | 40 |  | 20 20 (IA) |  | 20 |  |  |  | OS, SS
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test | System-Tested Applications | [13 empty] | 100 |  |  |  | KEY
|  | C.RA.055.2 | Document Business Procedures | Business Procedure Documentation |  | 80 |  |  |  |  | 20 | [10 empty] | BLM
|  | C.TE.019.1 | Collect, Assess and Refine KPI Measurements | Key Business Strategies and Objectives |  | 90 | [9 empty] | 10
C.ACT.PSIT Perform Systems Integration Test
|  | C.TE.085 | Prepare Systems Integration Test Environment | Systems Integration Test Environment | [9 empty] | 40 |  | 20 20 (IA) |  | 20 |  |  |  | OS, SS
|  | C.TE.100 | Perform Systems Integration Test | Integration-Tested System | [13 empty] | 100 |  |  |  | KEY
C.ACT.PPT Prepare for Performance Testing
|  | C.PT.070 | Build Performance Test Scripts and Programs | Performance Test Scripts and Programs | [11 empty] | 20 |  | 80
|  | C.PT.080 | Construct Performance Test Environment and Database | Performance Test Environment and Database |  |  |  | 40 | [5 empty] | 40 |  | 20 | [5 empty] | OS, SS
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal | Validated Performance Test and Environment |  |  |  | 20 | [6 empty] | 10 | 10 |  | 60 |  |  |  | OS, SS
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures | System Management Guide | [11 empty] | 100 | [5 empty] | SS
|  | C.TA.110 | Define Operational Testing Plan | Operational Testing Plan | [10 empty] | 80 | 20 | [5 empty] | SS
|  | C.TA.150 | Define Final Platform and Network Architecture | Final Platform and Network Architecture | [10 empty] | 30 | 70 | [5 empty] | OS, SS, ISM
|  | C.TA.160 | Define System Capacity Plan | System Capacity Plan |  |  |  | 10 | [6 empty] | 10 | 80 | [5 empty] | NA
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy | Cutover Strategy | [10 empty] | 100 | [6 empty] | BLM, CPM, SS, USR
|  | C.TS.030 | Develop Installation Plan | Installation Plan |  |  |  | 40 |  |  | 40 |  |  |  |  | 20 | [5 empty] | OS, USR
|  | C.TS.040 | Design Production Support Infrastructure | Production Support Infrastructure Design | [11 empty] | 100 | [5 empty] | CSM, ISM
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing | Operational Test Results |  |  |  | 70 | [7 empty] | 30 | [5 empty] | OS, SS
|  | C.TA.130 | Conduct Backup and Recovery Test | Backup and Recovery Test Results |  |  |  | 70 | [7 empty] | 30 | [5 empty] | OS, SS
|  | C.TA.140 | Conduct Disaster Recovery Test | Disaster Recovery Test Results |  |  |  | 70 | [7 empty] | 30 | [5 empty] | OS, SS
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping | Data Mapping | [11 empty] | 100 (IA) | [5 empty] | CDA
|  | C.RA.170.2 | Conduct Data Quality Assessment | High-Level Data Quality Assessment | [11 empty] | 100 (IA) | [5 empty] | CDA, KEY
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load) | Manual Conversion Procedures (Initial Load) |  | 100 | [15 empty] | CPM, CSM
|  | C.CV.040.2 | Design Conversion Components (Initial Load) | Conversion Component Designs (Initial Load) | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | CDA, CSA
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load) | Conversion Test Plans (Initial Load) |  | 20 | [9 empty] | 80
C.ACT.ACDC Acquire and Convert Data-Construction
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) | Conversion Environment (Initial Load) |  |  |  | 30 | [5 empty] | 60 |  | 10
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) | Conversion Components (Initial Load) | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | OS
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | Unit-Tested Conversion Components (Initial Load) | [6 empty] | 100
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | Business-Object Tested Conversion Components (Initial Load) | [11 empty] | 10 |  | 90
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | Validation-Tested Conversion Components (Initial Load) |  | 30 | [9 empty] | 10 |  | 60
|  | C.CV.064.1 | Install Conversion Components (Initial Load) | Installed Conversion Components (Initial Load) | [9 empty] | 90 |  | 10 | [5 empty] | CSM
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) | Converted and Verified Data (Initial Load) | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | CDA, KEY, CPDBA, IS, SS
|  | C.CV.068.1 | Clean Data | Clean Legacy Data | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | CDA, KEY
C.ACT.VUPC Validate Upgrade Process - Construction
|  | C.TE.072.2 | Test Pre-Upgrade Steps | Pre-Upgrade Checklist | [11 empty] | 100
|  | C.TE.073.2 | Test Packaged Software Upgrade | Packaged Software Upgrade Checklist | [11 empty] | 100
|  | C.TE.074.2 | Test Post-Upgrade Steps | Post-Upgrade Checklist | [11 empty] | 100
|  | C.TE.075.2 | Perform Post-Upgrade Reconciliation Testing | Reconciliation Test Report | [11 empty] | 100
|  | C.TE.076.2 | Review Upgrade Test Results | Upgrade Test Analysis | [11 empty] | 100
C.ACT.PD Produce Documentation
|  | C.DO.060 | Publish User Reference Manual | User Reference Manual |  | 20 | [12 empty] | 80
|  | C.DO.070 | Publish User Guide | User Guide |  | 10 | [9 empty] | 10 |  |  | 80
|  | C.DO.080 | Publish Technical Reference Material | Technical Reference Material | [6 empty] | 10 |  |  |  |  | 20 |  |  | 70
|  | C.DO.100 | Produce Online Help | Online Help | [6 empty] | 30 | [7 empty] | 70 |  |  | CPM, KEY
C.ACT.DCMRCCC Deploy Change Management Roadmap and Communication Campaign - Construction
|  | C.OCM.150.3 | Conduct Change Management Roadmap and Communication Campaign | Change Management Roadmap and Communication Events |  |  | 100 | [13 empty] | PM | CCS, CPM
|  | C.OCM.155.2 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Change Management Roadmap and Communication Campaign Effectiveness Assessment |  |  | 100 | [13 empty] | PM | CCS, CPM
C.ACT.CJIA Conduct Job Impact Analysis
|  | C.OCM.170 | Collect and Analyze Job Change Data | Job Impact Analysis |  | minimal | 100 | [9 empty] | minimal |  |  |  | PM | CHRS, CFS
|  | C.OCM.180 | Determine Impact of Job Changes | Job Impact Diagnosis |  | 10 | 80 | [9 empty] | 10 |  |  |  | PM | CHRS, CFS
|  | C.OCM.190 | Prepare HR Transition Plan | HR Transition Plan |  | minimal | 90 | [9 empty] | 10 |  |  |  | PM | CHRS, CFS
C.ACT.CMAWC Conduct Managers Alignment Workshop - Construction
|  | C.OCM.200 | Design Managers Unit and Department Impact Workshop | Managers Unit and Department Impact Workshop Materials |  |  | 100 | [13 empty] | PM | CPM
|  | C.OCM.210 | Conduct Managers Unit and Department Impact Workshop | Enabled Managers |  |  | 100 | [13 empty] | PM | CPM
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis | User Learning Needs Analysis |  |  | 30 | [9 empty] | 70 |  |  |  |  | BLM, USR, CPS
|  | C.TR.070 | Develop User Learning Plan | User Learning Plan | [12 empty] | 100 |  |  |  |  | CSM, USR
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | User Learningware |  | 10 | [10 empty] | 90 |  |  |  |  | CSM, USR
|  | C.TR.090 | Prepare User Learning Environment | Configured User Learning Environment |  | 20 |  | 25 | [5 empty] | 35 |  |  | 20 |  |  |  |  | CSM, USR
C.ACT.TEUC Train End Users - Construction
|  | C.TR.100.1 | Conduct User learning Events | Skilled Users | [12 empty] | 100 |  |  |  |  | BLM, CSM, USR
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone | Initial Operational Capability Milestone
D Transition
D.ACT.SUAT Support User Acceptance Test
|  | D.TE.105 | Prepare Users for Testing | Prepared Users for Testing |  | 30 | [11 empty] | 70 |  |  |  | VC, USR, BLM, KEY
|  | D.TE.110 | Prepare Acceptance Test Environment | Acceptance Test Environment |  |  |  | 45 | [5 empty] | 45 |  |  |  | 10 |  |  |  | OS, SS, USR, CPM
|  | D.TE.120 | Support Acceptance Test | Acceptance Test Results | [6 empty] | 10 |  |  | 20 | 20 | 20 10 (IA) |  | 20 |  |  |  | SS, CPM, VC, USR
D.ACT.CPTST Conduct Performance Test
|  | D.PT.100 | Execute Performance Test | Performance Test Results |  |  |  | 10 |  |  |  | 5 |  |  |  | 15 |  | 70
|  | D.PT.110 | Create Performance Test Report | Performance Test Report | [11 empty] | 30 |  | 70
D.ACT.PPE Prepare Production Environment
|  | D.TS.050 | Prepare Production Environment | Production Environment |  | 30 |  | 20 | [5 empty] | 30 |  | 20 | [5 empty] | CPM, OS
|  | D.TS.054 | Perform Pre-Upgrade Steps | Pre-Upgrade Checklist | [11 empty] | 100
|  | D.TS.055 | Upgrade Production Environment | Upgraded Production Environment | [11 empty] | 100
|  | D.TS.056 | Perform Post-Upgrade Steps | Post-Upgrade Checklist | [11 empty] | 100
|  | D.TS.057 | Revise Application Setups | Configured Applications | 40 | 50 | [7 empty] | 10
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load) | Installed Conversion Components (Initial Load) | [9 empty] | 90 |  | 10 | [5 empty] | CSM
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) | Converted and Verified Data (Initial Load) | [6 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | CDA, KEY, CPDBA, IS, SS
|  | D.CV.068.2 | Clean Data | [7 empty] | 80 |  |  |  |  | 20 (IA) | [5 empty] | CDA, KEY
D.ACT.DCMRCCT Deploy Change Management Roadmap Communication Campaign - Transition
|  | D.OCM.150.4 | Conduct Change Management Roadmap and Communication Campaign | Change Management Roadmap and Communication Events |  |  | 100 | [13 empty] | PM | CCS, CPM
|  | D.OCM.155.3 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Change Management Roadmap and Communication Campaign Effectiveness Assessment |  |  | 100 | [13 empty] | PM | CCS, CPM
D.ACT.CITA Conduct IT Alignment
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups | IT Alignment Diagnosis Grid |  |  | 100 | [13 empty] | PM | CITD
|  | D.OCM.230 | Prepare IT Transition Plan | IT Transition Plan |  |  | 100 | [13 empty] | PM | CITD, CIO
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events | Skilled Users | [12 empty] | 100 |  |  |  |  | BLM, CSM, USR
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation | Final Documentation Work Products | [6 empty] | 25 |  |  |  |  | 25 |  |  | 50
D.ACT.GP Go Production
|  | D.TS.052 | Implement Production Support Infrastructure | Production Support Infrastructure | Only Customer Roles | [16 empty] | CPM, CSM, ISM
|  | D.TS.058 | Verify Production Readiness | Production-Ready System |  | 5 | [6 empty] | 55 |  |  | 30 | 5 | 5 |  |  |  | CPM, CSM, ISM, USR
|  | D.TS.060 | Go Production | System in Production | [9 empty] | 100 | [7 empty] | USR, SS
|  | D.TS.070 | Shut Down Legacy System | Legacy System Shut Down | [9 empty] | 100
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management | Managed Production Environment |  |  |  | 80 | [5 empty] | 20 | [7 empty] | OS. SS
E.ACT.EPS Evaluate Production System
|  | E.PS.005 | Manage Transition to Steady-State Operations | Steady-State Operations | [17 empty] | customer and the consulting organization implementation team share responsibility
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements | Key Business Strategies and Objectives |  | 90 | [9 empty] | 10
|  | E.PS.010 | Audit System | System Evaluation | [9 empty] | 100 | [7 empty] | IQA, AU, CPS, SPM, USR
E.ACT.RPP Resolve Production Problems
|  | E.PS.050 | Analyze Problems | Fault Corrections | [9 empty] | 100 | [7 empty] | CPM, USR
|  | E.PS.060 | Monitor and Respond to System Problems | Problem Log | [6 empty] | 100 | [10 empty] | SS, USR
|  | E.PS.065 | Post Go-Live Support | Post Go-Live Support | [17 empty] | consulting organization implementation team has primary responsibility
E.ACT.DCMRCCP Deploy Change Management Roadmap and Communication Campaign - Production
|  | E.OCM.150.5 | Conduct Change Management Roadmap and Communication Campaign | Change Management Roadmap and Communication Events |  |  | 100 | [13 empty] | PM | CCS, CPM
|  | E.OCM.155.4 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Change Management Roadmap and Communication Campaign Effectiveness Assessment |  |  | 100 | [13 empty] | PM | CCS, CPM
E.ACT.PF Plan for Future
|  | E.RD.160 | Convert Project Views to Reusable Viewpoints | New Reusable Viewpoints | [15 empty] | EA
|  | E.PS.135 | Determine Future Functional Enhancements | Future Functional Enhancements | [10 empty] | 100 | [6 empty] | SS
|  | E.PS.140 | Plan Enhancements | Future MoSCoW List | [10 empty] | 100 | [6 empty] | CPS. CPM, SS
|  | E.OCM.250 | Measure Organizational Change Effectiveness | Organizational Effectiveness Assessment |  |  | 100 | [13 empty] | PM | CPS, CPM
E.ACT.DITTP Deploy IT Transition Plan
|  | E.OCM.260 | Implement IT Transition Plan | Aligned IT Organization |  |  | 100 | [13 empty] | PM | CHRS, CITD, CIO
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone | Sign Off Milestone

## Roles
Manage Roles |  | Implement Roles |  |  |  | Customer Roles
Role ID | Role Name | Role ID | Role Name | Specialized (Sub)Roles | Estimating Role Mapping | Role ID | Role Name
PAD | Project Administrator | APS | Application/Product Specialist |  | APS-Functional Specialist | BLM | Business Line Manager
PM | Project Manager | BA | Business Analyst |  | APS-Functional Specialist | CAT | Client Assessment Team
| Project Lead(s) | CMS | Change Management Specialist |  | CMS-Change Management Specialist | CCML | Customer Change Management Lead
| Functional Lead(s) | DBA | Database Administrator |  | DBA-DBA | CCS | Customer Communication Specialist
| Technical Lead(s) | DD | Database Designer |  | TA-Technical Architect | CDA | Customer Data Administrator
| Team Members | DES | Designer |  | DEV-Technical Specialist (Developer) aka Apps Tech Specialist | CDDBA | Customer Development Database Administrator
CPS | Customer Project Sponsor | DV | Developer |  | DEV-Technical Specialist (Developer) aka Apps Tech Specialist | CE | Customer Executive
CPM | Customer Project Manager | NE | Network Engineer |  | DEV-Technical Specialist (Developer) aka Apps Tech Specialist | CEA | Customer Enterprise Archtiect
SCM | Steering Committee Member | QM | Quality Manager |  | DEV-Technical Specialist (Developer) aka Apps Tech Specialist | CERM | Customer Enterprise Repository Manager
|  | SAD | System Administrator |  | TA-Technical Architect | CFS | Customer Funtional Specialist
|  | SAN | System Analyst |  | SE-Solution Architect (Software Engineer) | CHRS | Customer HR Specialist
|  | SA | System Architect | IA - Information Architect | TA-Technical Architect | CIO | Customer Chieft Information Officer
|  | TRS | Training Specialist |  | TS-Training Specialist | CPDBA | Customer Production Database Administrator
|  | TE | Tester |  | APS-Functional Specialist DEV-Technical Specialist (Developer) aka Apps Tech Specialist | CPM | Customer Project Manager
|  | TW | Technical Writer |  | APS-Functional Specialist | CPS | Customer Project Sponsor
[6 empty] | CS | Customer Stakeholder(s)
[6 empty] | CSA | Customer System Architect
[6 empty] | CSAD | Customer System Administrator
|  | Envision Roles |  |  |  | CSDLC | Customer Software Development Lifecycle Staff
|  | Role ID | Role Name | Specialized (Sub)Roles |  | CSE | Customer System Expert
|  | CMS | Change Management Specialist |  |  | CSM | Customer Staff Member
|  | EA | Enterprise Architect | BAR - Business Architect |  | CSOLA | Customer Solution Architect
|  | SOLA | Solution Architect | AA - Application Architect |  | CTO | Customer Chief Technology Officer
|  |  |  | DA - Domain Architect |  | IQA | Independent Quality Auditor
|  |  |  | IA - Informaton Architect |  | ISM | IS Manager
|  |  |  | TA - Technical Architect |  | KEY | Ambassador User
|  | SM | Sales Manager |  |  | OS | IS Operations Staff
[6 empty] | SS | IS Support Staff
[6 empty] | USR | User
[6 empty] | VC | Validation Coordinator
[6 empty] | VS | Visionary