## Envision Mapping
Task ID | Name | Work Product | EADF Enterprise Architecture Development Framework | TOGAF The Open Group Architecture Framework | SEP SOA Engineering Planning | SMP SOA Modeling Planning | GP SOA Governance Planning | RAP SOA Reference Architecture Planning | SOA Core Workflow | BPM Roadmap | SOA Roadmap | ESF Oracle Enterprise Software Framework applicable?
PS | Project Start Up
PS.ACT.RBC | Review Bid and Contract
PS.BT.020 | Review and Confirm Business Case | Confirmed Business Case |  |  |  | Motivational Modeling
PS.BT.030 | Identify Project Stakeholders | Identified Project Stakeholders |  | A | Mobilization | Mobilization | Mobilization | Mobilization
PS.BT.040 | Review and Accept Project Budget | Accepted Project Budget
PS.ACT.VSSOS | Validate Scope, Stakeholders and OCM Strategy
PS.SM.010 | Define and Confirm Scope | Validated Scope |  | A,G | Mobilization | Mobilization | Mobilization | Mobilization
PS.ACT.DW | Develop Workplan, Risk Assessment, Quality Management Plan
PS.WM.010 | Develop Baseline Project Workplan | Baseline Project Workplan
PS.ACT.DSPB | Develop Staff Plan and Budget
PS.STM.010 | Plan Resource Requirements | Resource Plan |  | G
PS.ACT.CPMP | Complete Project Management Plan
PS.STM.020 | Develop Staff Management Plan | Staff Management Plan |  | G
PEC | Project Execution and Control
PEC.ACT.MRIP | Manage Risks, Issues and Problems
PEC.RKM.040 | Manage Risk | Managed Risk |  | H
PEC.ACT.OMT | Orient and Manage Team
PEC.STM.050 | Conduct Team Orientation(s) | Oriented Team |  |  | Service Architecture | Motivational Modeling, Domain Analysis | Current Reality, Future Vision, Roadmap | Business and IT Drivers, Current Reality, Future Vision, Roadmap
PEC.ACT.CECR | Create and Execute Configuration and Release Management
PEC.CM.040 | Create and Execute Software Configuration Management Plan | Software Configuration Management Plan | [6 empty] | ENV-Serv Arch & Gov Defn
PEC.CM.050 | Create and Execute Software Release Management Plan | Software Release Management Plan | [6 empty] | IMP-Serv Anal-Rel Plan
PC | Project Closure
PS.ACT.CPC | Close Processes and Contract
PC.CMM.040 | Document Lessons Learned | Lessons Learned |  | F,G
INIT | Initiate
INIT.ACT.PEF | Prepare Envision Foundation
INIT.ER.010 | Create Business Case for Envision Engagement | Customer Envision Engagement Strategy | EA |  | Mobilization | Mobilization | Mobilization | Mobilization
INIT.EA.001 | Justify and Engage Enterprise Architects | Assigned Enterprise Architect
INIT.ER.040 | Research Enterprise | Enterprise Research Findings | EA | A | Mobilization | Mobilization | Mobilization | Mobilization |  | Current State Assessment | Current State Assessment
INIT.ER.045 | Establish Exective Sponsorship | Committed Executive Sponsorship |  |  | Mobilization | Mobilization | Mobilization | Mobilization
INIT.BA.010 | Identify Business Strategy | Business Strategy | BA-C | Prelim, A |  | Motivational Modeling |  | Business and IT Drivers | ENV-Serv Arch & Gov Defn, ENV-Reqts ID & Disc-Reqts Mgmt | Future Vision Definition | Future Vision Definition
INIT.BA.012 | Define Business Scope | Business Scope |  |  |  | Domain Analysis |  |  | ENV-Serv Arch & Gov Defn, ENV-Reqts ID & Disc-Reqts Mgmt | Current State Assessment | Current State Assessment
INIT.BA.015 | Conduct Enterprise Stakeholder Assessment | Enterprise Stakeholder Inventory | BA-C |  |  | Domain Analysis |  |  |  | Current State Assessment | Current State Assessment
INIT.GV.010 | Define Governance Strategy | Governance Strategy | EA | G |  |  | Future Vision
INIT.BA.017.1 | Metrics Collection and Reporting Strategy | Determine Metrics Collection and Reporting Strategy |  | A,E,F | Service Analysis, Service Delivery, Service Management |  | Roadmap | Roadmap
INIT.BA.018.1 | Establish Current Baseline Metrics | Current Baseline Metrics |  | F
INIT.BA.020 | Document Enterprise Organization Structures | Enterprise Organization Structures | EA | A
INIT.BA.025 | Determine Operating Model | Validated Operating Model
INIT.EA.002 | Review External Reference Architectures | External Reference Architectures Review | EA BA-C CITA | A,B,C,D
INIT.ER.015 | Conduct Enterprise Maturity Assessment | Maturity Analysis and Recommendations Report | EA | Prelim | Mobilization | Mobilization | Mobilization | Mobilization |  | Current State Assessment | Current State Assessment
INIT.ER.020 | Determine Envision Engagement Strategy | Envision Engagement Strategy | EA | A | Mobilization | Mobilization | Mobilization | Mobilization
INIT.ACT.PD | Prepare for Discovery
INIT.EOCM.010 | Create and Manage Ad Hoc Communications | Ad Hoc Communications | EA ENG
INIT.ER.025 | Educate Enterprise on Area of Focus | Educated Enterprise | CITA |  |  |  | Future Vision |  |  |  |  | YES
INIT.ER.030 | Set and Agree on Plan for Envision Engagement | Envision Engagement Plan | EA BA-C | A | Mobilization | Mobilization | Mobilization | Mobilization
INIT.ER.050 | Validate and Agree on Envision Engagement Plan | Agreed on Envision Engagement Plan | EA BA-C | A | Mobilization | Mobilization | Mobilization | Mobilization
INIT.ACT.CEAWE | Conduct Executive Alignment Workshop - Envision
INIT.EOCM.020 | Prepare for Executive Alignment Workshop | Executive Alignment Workshop Materials | EA BA-C
INIT.EOCM.030 | Conduct Executive Alignment Workshop | Executive Business Objectives and Governance Rules | EA BA-C
INIT.EOCM.040 | Build and Deploy Sponsorship Program | Sponsorship Program | EA BA-C
INIT.ACT.DMCEC | Define and Maintain Common Enterprise Concepts
INIT.BA.030.1 | Develop Enterprise Glossary | Enterprise Glossary | CITA
INIT.EA.010.1 | Review Architecture Principles, Guidelines and Standards | Architecture Principles, Guidelines and Standards | EA | Prelim, A,B,C,D, H | Service Architecture |  |  | Current Reality | ENV-Serv Arch & Gov Defn | Future Vision Definition | Future Vision Definition | YES
INIT.ER.070 | Define Modeling Strategy for the Enterprise | Enterpise Modeling Strategy |  | B |  | Domain Analysis, Model Specification
INIT.ACT.EDGI | Execute Discovery - Gather Information (As Is)
INIT.EOCM.050 | Assess Enterprise Change Readiness | Preliminary Enterprise Change Readiness Assessment | EA BA-C
INIT.EOCM.060 | Prepare Project Team for Enterprise Culture | Prepared Project Team | EA BA-C
INIT.EOCM.070 | Identify Change Agent Structure | Change Agent Structure | EA BA-C
INIT.ER.080 | Obtain Existing Reference Material | Existing Reference Material | EA BA-C | A | [5 empty] | Current State Assessment | Current State Assessment
INIT.ER.090 | Conduct Solution Readiness Assessment | Solution Readiness Assessment | EA
INIT.GV.015 | Review Current Governance Model | Current Governance Model |  |  |  |  | Current Reality
INIT.GV.020.1 | Determine Regulatory and Business Mandates | Mandate Matrix | EA BA-C
INIT.BA.040 | Create Enterprise Function or Process Model | Enterprise Function or Process Model | BA-L | B |  | Model Specification |  |  | ENV-Reqts ID & Disc-Reqts Mgmt, ENV-Reqts ID & Disc-Serv ID & Disc | Activity Selection and Scheduling
INIT.BA.050 | Develop Enterprise Domain Model (Business Entities) | Enterprise Domain Model | BA-C | B |  | Model Specification |  |  | ENV-Reqts ID & Disc-Reqts Mgmt, ENV-Reqts ID & Disc-Serv ID & Disc
INIT.BA.055 | Develop Enterprise Knowledge Flow | Enterprise Knowledge Flow
INIT.BA.058 | Develop Business Architectures | Business Architectures |  | B
INIT.BA.060.1 | Perform High-Level Use Case Discovery | High-Level Use Cases | BA-P | B |  |  |  |  | ENV-Reqts ID & Disc-Reqts Mgmt | Activity Selection and Scheduling
INIT.EA.030 | Identify Current Enterprise Architecture | Current Enterprise Architecture | EA | A,B,C,D |  |  |  | Current Reality |  |  |  | YES
INIT.EA.040 | Analyze Capabilities | Capability Analysis Results
INIT.GV.030.1 | Discover or Define Policies | Governance Policies Catalog | EA METH ENG | G
INIT.EA.050 | Identify Current Architectural Challenges | Current Architectural Challenges | EA | C |  |  |  | Current Reality |  |  |  | YES
INIT.GV.092 | Determine Projects Meta Data Description | Projects Meta Data Description | [6 empty] | ENV-Serv Arch & Gov Defn
INIT.IP.010 | Inventory Projects | IT Project Portfolio | EA | F |  |  |  | Current Reality
INIT.GV.094 | Determine Applications Meta Data Description | Applications Meta Data Description | [6 empty] | ENV-Serv Arch & Gov Defn
INIT.IP.012 | Inventory Applications | IT Application Portfolio | ISA-P
INIT.IP.015 | Conduct Portfolio Analysis | Portfolio Analysis Report | EA CITA
INIT.BA.065 | Review Business-IT SLA | Business-IT SLA Report | BA-C
INIT.BA.067 | Review Business Volumetrics | Business Volumetrics Report | BA-C/L/P
INIT.GV.096 | Determine Services Meta Data Description | Services Meta Data Description |  |  |  | Model Specification |  |  | ENV-Serv Arch & Gov Defn
INIT.GV.098 | Determine Other Meta Data Descriptions | Other Meta Data Descriptions | [6 empty] | ENV-Serv Arch & Gov Defn
INIT.IP.014 | Inventory Services | Service Portfolio | TSA-P | [5 empty] | ENV-Serv Arch & Gov Defn
INIT.ER.100 | Define Supplemental Enterprise Requirements | Supplemental Enterprise Requirements | BA-C | B,D | [7 empty] | YES
INIT.EA.057 | Review Business Capacity Plan | Business Capacity Plan | BA-C ENG
INIT.ACT.EDBPD | Execute Discovery - Brainstorm, Prioritize and Discover Entry Points
INIT.BA.045 | Develop Enterprise Business Context Diagram | Enterprise Business Context Diagram | [6 empty] | ENV-Reqts ID & Disc-Reqts Mgmt
INIT.GV.040 | Determine Organizational Impact of Governance | Impact Study and List of Proposed Organizational Changes | EA BA-C | G
INIT.EA.060 | Identify Architectural Gaps and Improvement Options | Architectural Gaps and Improvement Options | EA | B,C,D,E |  |  |  | Roadmap |  |  |  | YES
INIT.EA.065 | Identify Enterprise IT Strategy | Enterprise IT Strategy
INIT.ER.110.1 | Perform Benefit Analysis | Benefit Analysis | EA | B,F |  |  | Roadmap |  |  |  | Future Vision Definition | YES
INIT.BA.060.2 | Perform High-Level Use Case Discovery | High-Level Use Cases | BA-C/P | [5 empty] | ENV-Reqts ID & Disc-Serv ID & Disc
INIT.EA.075 | Develop Technology Reference Architectures | Technology Reference Architectures | IA-L CITA TSA-L |  | Service Architecture |  |  | Future Vision | ENV-Serv Arch & Gov Defn |  |  | YES
INIT.BA.070 | Identify Candidate Services | Service Portfolio - Candidate Services | CITA ENG | [5 empty] | ENV-Reqts ID & Disc-Serv ID & Disc |  | Activity Selection and Scheduling
INIT.IP.020 | Analyze Services | Service Portfolio - Proposed Services | CITA ENG | [5 empty] | ENV-Reqts ID & Disc-Serv ID & Disc |  | Activity Selection and Scheduling
INIT.IP.025 | Populate Services Repository | Populated Services Repository | ENG
INIT.BA.080 | Identify Candidate Enterprise Business Rules | Candidate Business Rules | BA-C
INIT.IP.030 | Analyze Business Rules | Business Rules Analysis | EA BA-L
INIT.BA.090 | Identify Process Improvement Options | Process Improvement Options | BA-L | B,E | [5 empty] | Activity Selection and Scheduling
INIT.ER.120.1 | Identify and Mitigate Future State Risks | Future State Risks | EA | A,E,F |  |  | Roadmap
INIT.ER.130.1 | Produce MoSCoW Improvement List | MoSCoW Improvement List | EA | D |  | Motivational Modeling | Roadmap |  | ENV-Reqts ID & Disc-Reqts Mgmt | Activity Selection and Scheduling | Activity Selection and Scheduling | YES
INIT.EA.095 | Review Enterprise Software Development Process | Enterprise Software Development Process |  | G | Service Analysis, Service Delivery, Service Management, Wrap-Up | Project Delivery Planning
INIT.IP.040 | Identify Candidate Projects | Candidate Projects | EA | E |  |  |  | Roadmap |  |  | Activity Selection and Scheduling | YES
INIT.ACT.EDF | Execute Discovery - Finish
INIT.ER.140 | Share Product Strategies with Enterprise | Informed Enterprise | EA BA-C | [8 empty] | YES
INIT.ER.150 | Review Discovery Findings | Reviewed Discovery Findings | EA ENG | B,C,D |  |  | Roadmap |  |  |  |  | YES
INIT.ACT.DSPC | Develop Solution and Present to Customer
INIT.GV.050.1 | Define Policy Implementation Processes | Policy Implementation Processes | EA METH ENG | G,H
INIT.GV.060.1 | Define Policy Implementation Tooling | Governance Policy Tooling | EA GSA-P
INIT.GV.070.1 | Define Policy Metrics | Measurements Portfolio | EA ENG
INIT.GV.080.1 | Define Policy Monitoring Processes | Policy Monitoring Processes | EA METH ENG
INIT.GV.090.1 | Determine Funding Model | Funding Model | EA BA-C
INIT.GV.100.1 | Implement Governance | Governance Implementation | EA BA-C | G,H
INIT.ER.160 | Develop Desired Future State | Desired Future State | BA-C |  |  |  | Future Vision |  |  | Future Vision Definition | Future Vision Definition
INIT.ER.165 | Identify Capability Challenges | Capability Challenges | [7 empty] | Gap Analysis Process | Gap Analysis Process
INIT.ER.167 | Determine Remediation Approaches | Remediation Approaches | [7 empty] | Gap Analysis Process | Gap Analysis Process
INIT.EA.110 | Develop Future State Enterprise Architecture | Future State Enterprise Architecture | EA CITA | B,D,C | [7 empty] | YES
INIT.EA.120 | Develop Information Architecture | Information Architecture | EA IA-C | A,C | [7 empty] | YES
INIT.EA.130 | Develop Technology Architecture | Technology Architecture | TSA-L | A,D,C | [7 empty] | YES
INIT.EA.140 | Develop Applications Architecture | Applications Architecture | ISA-L | A
INIT.EA.150 | Define Transitional Architectures | Transitional Architectures |  | E,F
INIT.EA.160 | Define Business Rules Implementation Strategy | Business Rules Implementation Strategy | BA-L ENG
INIT.ER.170 | Develop Future State Transition Plan | Future State Transition Plan | EA | E,F |  |  | Roadmap | Roadmap |  | Activity Selection and Scheduling | Activity Selection and Scheduling | YES
INIT.EA.170 | Identify Integration Requirements | Integration Requirements | [7 empty] | Activity Selection and Scheduling
INIT.IP.050.1 | Prioritize Projects | Prioritized Projects | EA BA-C ENG | E,F | [6 empty] | Activity Selection and Scheduling
INIT.ER.110.2 | Perform Benefit Analysis | Benefit Analysis | EA BA-C
INIT.IP.060 | Develop IT Portfolio Plan | IT Portfolio Plan | EA BA-C ENG | F | [5 empty] | Activity Selection and Scheduling | Activity Selection and Scheduling
INIT.EA.190 | Define Product Implementation Prioritization | Product Implementation Prioritization | BA-C CITA | E | [7 empty] | YES
INIT.ER.180 | Prepare for and Present Solution Recommendations | Solution Recommendations | EA |  | Service Architecture, Service Analysis, Service Delivery, Service Management, Wrap-Up | Motivational Modeling, Domain Analysis, Model Specification, Project Delivery Planning | Current Reality, Future Vision, Roadmap | Business and IT Drivers, Current Reality, Future Vision, Roadmap |  |  |  | YES
INIT.EA.200 | Determine Development Framework and Policy Guidelines | Development Framework | TSA METH ENG
INIT.ACT.PTI | Plan Transition to Implementation
INIT.ER.190 | Review Business Feedback and Identify Opportunities | Opportunities Task List | EA |  |  |  | Roadmap |  |  |  |  | YES
INIT.ER.200 | Prepare for Transition to Sales or Services | Opportunities Action Plan | EA |  |  |  | Roadmap
ME | Maintain and Evolve
ME.ACT.ME | Maintain and Evolve
ME.BA.017.2 | Metrics Collection and Reporting Strategy | Determine Metrics Collection and Reporting Strategy
ME.BA.018.2 | Establish Current Baseline Metrics | Current Baseline Metrics
ME.BA.100 | Maintain Enterprise Business Models | Maintained Enterprise Business Models | BA-C
ME.BA.110 | Maintain Business Rules | Maintained Business Rules | BA-C
ME.BA.030.2 | Develop Enterprise Glossary | Enterprise Glossary | EA
ME.EA.010.2 | Review Architecture Principles, Guidelines and Standards | Architecture Principles, Guidelines and Standards | EA
ME.GV.020.2 | Determine Regulatory and Business Mandates | Mandate Matrix | BA-C
ME.GV.030.2 | Discover or Define Policies | Governance Policies Catalog | EA ENG
ME.GV.050.2 | Define Policy Implementation Processes | Policy Implementation Processes | METH
ME.GV.060.2 | Define Policy Implementation Tooling | Governance Policy Tooling | GSA-L
ME.GV.070.2 | Define Policy Metrics | Measurements Portfolio | BA-C/L
ME.GV.080.2 | Define Policy Monitoring Procedures | Policy Monitoring Procedures | METH
ME.GV.090.2 | Determine Funding Model | Funding Model | EA BA-C
ME.GV.100.2 | Implement Governance | Governance Implementation | EA ENG
ME.GV.110 | Monitor and Analyze Governance Processes | Governance Implementation Improvement Proposal | EA | H
ME.ER.120.2 | Identify and Mitigate Future Enterprise Architecture Risks | Future Architectural Risks | EA
ME.ER.130.2 | Produce MoSCoW Improvement List | MoSCoW Improvement List | EA
ME.EA.210 | Maintain Enterprise Architectural Models | Maintained Enterprise Architectural Models | EA
ME.IP.050.2 | Prioritize Projects | Prioritized Projects | EA BA-C ENG
ME.IP.070 | Execute and Maintain IT Portfolio and Programs | Maintained IT Portfolio and Programs | EA
ME.IP.080 | Maintain Repository of Artifacts | Maintained Repository of Artifacts | EA METH | B,H |  |  |  |  | ENV-Serv Arch & Gov Defn
ME.ER.210 | Monitor Current Situation and Pursue Relevant Updates | Monitored Current Situation |  | H
The following is not a complete listing of ALL the Implement tasks. It only contains those tasks that are included in the SOA Core Workflow view.
A | Inception
A.ACT.GBRI | Gather Business Requirements - Inception
A.RD.011.1 | Develop Future Process Model | Future Process Model | ISA-P GSA-P | [5 empty] | IMP-Serv Anal-Reqts Mngt
A.RD.020 | Obtain High-Level Business Descriptions | High-Level Business Descriptions | BA-P | [5 empty] | IMP-Serv Anal-Reqts Mngt
A.RD.065 | Develop Domain Model (Class Diagram) | Domain Model | IA-L | [5 empty] | IMP-Serv Anal-Reqts Mngt, IMP-Serv Anal-Serv ID & Disc
A.ACT.GR | Gather Solution Requirements
A.RD.045.1 | Prioritize Requirements (MoSCoW) | MoSCoW List | BA-L | [5 empty] | IMP-Serv Anal-Reqts Mngt
A.RA.023.1 | Develop Use Case Model | Use Case Model | ISA-P GSA-P | [5 empty] | IMP-Serv Anal-Reqts Mngt
A.RA.019 | Define Project Reference Architecture | Project Reference Architecture | ISA-L GSA-L | [5 empty] | Project Start Up
B | Elaboration
B.ACT.DPS | Define Project Strategy
B.TE.010 | Develop Testing Strategy | Testing Strategy | [6 empty] | IMP-Serv Test
B.ACT.GBRE | Gather Business Requirements - Elaboration
B.RD.011.2 | Develop Future Process Model | Future Process Model | BA-L | [5 empty] | IMP-Serv Anal-Serv ID & Disc
B.ACT.DTP | Develop Test Plans
B.TE.015.1 | Develop Integration Test Plan | Integration Test Plan | [6 empty] | IMP-Serv Test
B.ACT.DUCM | Develop Use Case Model
B.RA.023.2 | Develop Use Case Model | Use Case Model | BA-P | [5 empty] | IMP-Serv Anal-Serv ID & Disc
B.ACT.CS | Consolidate Specification
B.RA.025.2 | Identify Candidate Services | Service Portfolio - Candidate Services | [6 empty] | IMP-Serv Anal-Serv ID & Disc
B.ACT.BSA | Baseline Software Architecture
B.DS.040.1 | Develop Design Architecture Description | Architecture Description | [6 empty] | IMP-Serv Defn
B.ACT.AE | Analyze - Elaboration
B.AN.080.1 | Analyze Services | Service Portfolio - Proposed Project Services | [6 empty] | IMP-Serv Anal-Serv ID & Disc
B.AN.085.1 | Define Service | [7 empty] | IMP-Serv Anal-Serv ID & Disc
B.ACT.DE | Design - Elaboration
B.DS.070 | Define SOA Implementation Strategy | SOA Implementation Strategy | [6 empty] | IMP-Serv Defn
B.DS.120.1 | Design Services | Service Design | [6 empty] | IMP-Serv Design
C | Construction
C.ACT.DCCTSC | Develop Custom Component Test Scripts - Construction
C.TE.020.2 | Develop Unit Test Scripts | Unit Test Scripts | [6 empty] | IMP-Serv Test
C.ACT.ICC | Implement Custom Components
C.IM.050 | Implement Components | Implemented Components | [6 empty] | IMP-Serv IMP
C.IM.070 | Assemble Components | Assembled Components | [6 empty] | IMP-Serv Mgmt
C.ACT.PCCTC | Perform Custom Component Testing - Construction
C.TE.030.2 | Perform Unit Test - Construction | Unit-Tested Components | [6 empty] | IMP-Serv Test
C.TE.040.2 | Perform Integration Test | Integration-Tested Components | [6 empty] | IMP-Serv Test
D | Transition
D.ACT.PPE | Prepare Production Environment
D.TS.050 | Prepare Production Environment | Production Environment | [6 empty] | IMP-Serv Mgmt
D.ACT.GP | Go Production
D.TS.060 | Go Production | System in Production | [6 empty] | IMP-Serv Mgmt
E | Production
E.ACT.RPP | Resolve Production Problems
E.PS.060 | Monitor and Respond to System Problems | Problem Log | [6 empty] | IMP-Serv Mgmt
PC | Project Closure
PC.ACT.PCSUM1 | Gain Acceptance
PC.SM.050 | Gain Acceptance | Final Acceptance Certificate |  |  | Post Delivery | Post Delivery | Post Delivery | Post Delivery
PC.ACT.PCSUM3 | Document Lessons Learned and Archive Report
PC.CMM.040 | Document Lessons Learned | Lessons Learned |  |  | Post Delivery | Post Delivery | Post Delivery | Post Delivery