## CAS OUM to AIM Mapping
CAS OUM (Cloud Application Services OUM) WBS -v3.2 |  |  |  | AIM 3.2.1
Phase | Task Grp/ Task ID | Task Name | Comments | Comparable AIM Task ID | Comparable AIM Task Name
A | Project Design
PS.ACT Project Startup
| PS.ACT.RCSWB | Review Contract, Scope, Workplan and Budget |  | BT.010 BT.050 SM.010 FM.010 WM.010 | Review and Analyze Bid Material Review Contract with Customer Define and Confirm Scope Refine Project Budget Develop Baseline Project Workplan
| PS.ACT.RPAC | Review Project Approach with Customer and Confirm Customer Readiness |  | BT.060 | Review Project Approach with Customer
| PS.ACT.EGSI | Establish Governance and supporting infrastructure |  | BT.070 SM.020 WM.020 RKM.030 IPM.030 QM.010 IFM.010 | Create Project Management Framework Develop Scope Change Management Process Develop Work Management Execution and Control Processes and Policies Develop Risk Management System Develop Issue and Problem Management System Develop Quality Management Plan Develop Infrastructure Management Plan
A.TG.TR Prepare Project Team
| STM.050 | Conduct Customer Kickoff Meeting |  | STM.050 | Conduct Team Orientation
| TR.050 | Train Project Team |  | AP.050 | Conduct Project Team Learning Events
| WM.070 | Schedule Workshops | kept this task in the Design Phase rather than move to Project Startup. Scheduling of functional and technical workshops seems better addressed by functional and technical team leaders than the PM.
A.TG.FT Conduct Functional and Technical Design Workshops
| MC.040 | Conduct Functional Design Workshops |  | RD.050 BR.100 | Gather Business Requirements Define Application Setups
| DS.145 | Conduct Technical Design Workshops | - Includes providing technical guidance on integration functionality | MD.050 MD.070 | Create Application Extensions Functional Design Create Application Extensions Technical Design
| DS.160 | Conduct Design Reviews |  | MD.080 | Review Functional and Technical Designs
A.TG.SP Security Planning
| MC.060 | Develop Security Strategy and Plan | - Includes Single Sign-On (SSO) | TA.080 BR.110 | Define Application Security Architecture Design Security Profiles
A.TG.VP Validation Planning
| TE.010 | Define Validation Strategy and Plan |  | TE.010 | Define Testing Requirements and Strategy
A.TG.DO Documentation
| DO.010 | Define Documentation Requirements and Strategy |  | DO.010 | Define Documentation Requirements and Strategy
A.TG.TA Technical Readiness Assessment Kickoff
| TA.010 | Conduct Technical Readiness Assessment Kickoff Meeting
A.TG.IC Implementation Checkpoint
| WM.055.1 | Conduct Implementation Checkpoint | Includes obtaining customer sign-off where appropriate |  | Project Execution and Control
A.TG.PM Project Management
| A.PEC.TSK | Manage Project Execution |  |  | Project Execution and Control
| A.PGM.TSK | Program Management - Delete
B | Configure
B.TG.IF Initial Configuration
| MC.070.1 | Setup Applications | Includes installation of desktop clients and related support, if applicable. | BR.020 | Prepare Mapping Environment
| TE.025 | Prepare Validation Scripts | Validation scripts are intended to demonstrate in-scope functionality and validate that the system performs as expected, per the approved design | TE.040 | Develop System Test Script
| MC.080 | Conduct Configuration Validation Workshops | Iterative prototyping techniques may be utilized in the performance of this task, if applicable. | BR.080 | Test Business Solutions
| MC.050 | Update Setup Documentation | Setup Documentation may take the form of a Configuration Workbook, Functional Design Document, or Functional Workbook | BR.100 | Define Application Setups
| RD.011 | Update Business Process Model |  | BP.080 | Develop Future Process Model
B.TG.FC Configuration Familiarization and Coaching
| MC.063 | Conduct Configuration Familiarization/Coaching Sessions | - Intended to cover both Fusion Configuration Familiarization Sessions and RightNow Coaching Services - May include multiple sessions/workshops, as necessary
B.TG.DL Load and Validate Data - Configure
| CV.027 | Perform Data Mapping |  | BR.040 CV.040 | Map Business Data Perform Conversion Data Mapping
| CV.053 | Prepare Data for Loading |  | CV.050 | Define Manual Conversion Procedures
| CV.065.1 | Load, Reconcile and Validate Data |  | CV.110 | Perform Conversion Validation Tests
B.TG.CL Prepare and Load Content
| CV.026 | Conduct Content Strategy Session
| CV.066 | Prepare and Load Content
B.TG.IP Implement Integration Packages
| IM.050.1 | Implement Integration Packages - Oracle |  | MD.110 | Create Application Extension Modules
| IM.050.2 | Implement Integration Packages - Customer Systems |  | MD.110 | Create Application Extension Modules
| TE.045 | Validate Integration Packages | - Includes Unit and Link testing of integrations | TE.120 | Perform Systems Integration Test
B.TG.IE Implement Extensions
| IM.050.3 | Implement Extensions | Includes RightNow Customizations | BR.020 | Prepare Mapping Environment
| MC.070.2 | Implement Extensible Items | Includes Fusion Extensible elements | BR.020 | Prepare Mapping Environment
| MC.085 | Prepare Reports |  | BR.020 | Prepare Mapping Environment
| TE.030 | Validate Extensions | - Includes Unit and Link testing of extensions, as necessary - Separate QA testing - specific to customizations - separate team. | BR.080 | Test Business Solutions
B.TG.PC Prepare for Cutover
| TS.020 | Define Cutover Strategy | Intended to cover creation of a Deployment Plan (for RN) | PM.010 PM.030 | Define Transition Strategy Develop Transition & Contingency Plan
| TS.040 | Design Production Support Infrastructure | Intended to cover definition of a Support Model for RN. | PM.020 | Design Production Support Infrastructure
B.TG.IS Implement Security Plan
| MC.070.3 | Implement Security | Includes configuration of SSO, and role based security access to the system, as applicable | BR.110 | Design Security Profiles
B.TG.IC Implementation Checkpoint
| WM.055.2 | Conduct Implementation Checkpoint | Includes obtaining customer sign-off where appropriate |  | Project Execution and Control
B.TG.PM Project Management
| B.PEC.TSK | Manage Project Execution |  |  | Project Execution and Control
| B.PGM.TSK | Program Management - Delete
C | Validate
C.TG.PR Prepare for End-to-End Review
| MC.070.4 | Setup Applications | Includes any updates to the setup values identified as a result of the Configuration Validation Workshops. | TE.060 | Prepare Testing Environments
| TE.027 | Update Validation Scripts |  | TE.040 TE.050 | Develop System Test Script Update Validation Scripts
| TE.105 | Prepare Users for Validation |  | TE.100 | Prepare Key Users for Testing
C.TG.DL Validate Data Load - Validate
| CV.065.2 | Load, Reconcile & Validate Data |  | CV.130 | Convert and Verify Data
C.TG.ER End-to-End Review
| TE.070 | Conduct End-to-End Review | - Equivalent to a System Test - Estimates for this task should Include effort for consulting support | TE.110 | Perform System Test
C.TG.DO Documentation
| DO.070 | Publish User Guide (i.e. Job Aid) |  | DO.070 | Publish User Guide
| DO.075 | Publish Admin Guide |  | DO.090 | Publish System Management Guide
C.TG.TR Prepare for Training
| TR.080 | Prepare for Training |  | AP.150 AP.160 | Develop User Learningware Prepare User Learning Environment
| TR.085 | Translate Training Material - Delete
| TR.095 | Conduct Train-the-Trainer Workshops |  | AP.170 | Conduct User Learning Events
C.TG.TA Execute Technical Readiness Assessment
| TA.125 | Execute Technical Readiness Assessment | Includes delivery of TRA Recommendation
C.TG.IC Implementation Checkpoint
| WM.055.3 | Conduct Implementation Checkpoint | Includes obtaining customer sign-off where appropriate |  | Project Execution and Control
C.TG.PM Project Management
| C.PEC.TSK | Manage Project Execution |  |  | Project Execution and Control
| C.PGM.TSK | Program Management - Delete
D | Transition
D.TG.PT Prepare for Transition
| TS.045 | Remove Test Data from Production | May apply to Taleo only
| TS.050 | Migrate Configuration to Production | Includes Extensible items, if any | PM.050 | Set Up Applications
| TS.051 | Migrate Integrations and Extensions to Production |  | PM.040 | Prepare Production Environment
| TE.067 | Delete - Perform Quality Assurance Review - rolled into Integration Validation in Configure and into Final Validation Review in Transition. | May apply to Taleo only
| CV.065.3 | Load, Reconcile & Validate Data Loads in Production |  | CV.130 | Convert and Verify Data
D.TG.FV Final Validation
| TE.120 | Conduct Final Validation Review with Users & Stakeholders |  | TE.130 | Perform Acceptance Test
D.TG.TR Training
| TR.097 | Delete - Prepare Staging Environment for Training - rolled into Prepare Training Material and Environment | May apply to Taleo only
| TR.100 | Conduct End User Training |  | AP.170 | Conduct User Learning Events
D.TG.TS Transition to Production
| TS.052 | Implement Production Support Infrastructure |  | PM.060 | Implement Production Support Infrastructure
| TS.058 | Verify Production & Operational Readiness |  | PM.070 | Verify Production Readiness
| TS.060 | Begin Production Use |  | PM.080 | Begin Production
D.TG.IC Implementation Checkpoint
| WM.055.4 | Conduct Implementation Checkpoint | Includes obtaining customer sign-off where appropriate |  | Project Execution and Control
D.TG.PM Project Management
| D.PEC.TSK | Manage Project Execution |  |  | Project Execution and Control
| D.PGM.TSK | Program Management - Delete
E | Realization
E.TG.SP Stabilization
| PS.005 | Manage Transition to Steady-state Operations |  | PM.100 | Maintain System
| PS.065 | Post Go-Live Support | Post Go-Live Support | PM.100 | Maintain System
E.TG.TC Transition to Customer Relationship Manager
| PS.070 | Execute Handoff to Customer Relationship Manager
E.TG.PM Project Management
| B.PEC.TSK | Manage Project Execution |  |  | Project Execution and Control
| B.PGM.TSK | Program Management - Delete
PC.ACT Project Closure
| PC.ACT.GA | Gain Acceptance |  |  | Project Closure
| PC.ACT.CPC | Close Processes and Contract |  |  | Project Closure
PC | Project Closure
| PC.ACT | Project Closure
| PC.ACT.GA | Gain Acceptance
| PS.ACT.CPC | Close Processes and Contract |  | Core | Oracle
| PS.ACT.DLLAP | Document Lessons Learned and Archive Project

## AIM to CAS OUM Mapping
AIM 3.2.1 |  |  |  | OUM Cloud Application Services Implementation Approach WBS -v3.2
Phase | Process/ Task ID | Task Name | Comments | Comparable OUM Cloud Task ID | Comparable OUM Cloud Task Name
PS Project Start Up
| PMC.PSSUM1 | Review Bid and Contract |  | PS.ACT.RCSWB | Review Contract, Scope, Workplan and Budget
| PMC.PSSUM2 | Validate Scope, Stakeholders and OCM Strategy |  | PS.ACT.RCSWB | Review Contract, Scope, Workplan and Budget
| PMC.PSSUM3 | Develop Workplan, Risk Assessment, Quality Management Plan |  | PS.ACT.RCSWB | Review Contract, Scope, Workplan and Budget
| PMC.PSSUM4 | Develop Staff Plan and Budget |  | PS.ACT.RCSWB | Review Contract, Scope, Workplan and Budget
| PMC.PSSUM5 | Complete Project Management Plan |  | PS.ACT.EGSI | Establish Governance and supporting infrastructure
| PMC.PSSUM6 | Establish Project Infrastructure and Orientation Guides |  | PS.ACT.EGSI | Establish Governance and supporting infrastructure
PEC Project Execution and Control
| PMCPECSUM1 | Perform Project Execution and Control Activities |  | A/B/C/D/E.PEC.TSK STM.050 WM.055.1/2/3/4 | Manage Project Execution Conduct Customer Kickoff Meeting Conduct Implementation Checkpoint
A Definition
[BP] Business Process Architecture
| BP.010 | Define Business and Process Strategy
| BP.020 | Catalog and Analyze Potential Changes
| BP.030 | Determine Data Gathering Requirements
| BP.040 | Develop Current Process Model
| BP.050 | Review Leading Practices
| BP.060 | Develop High-Level Process Vision
| BP.070 | Develop High-Level Process Designs
[RD] Business Requirements Definition
| RD.010 | Identify Current Financial and Operating Structure
| RD.020 | Conduct Current Business Baseline
[TA] Application and Technical Architecture
| TA.010 | Define Architecture Requirements & Strategy
| TA.020 | Identify Current Technical Architecture
| TA.030 | Develop Preliminary Conceptual Architecture
[MD] Module Design and Build
| MD.010 | Define Application Extension Strategy
[CV] Data Conversion
| CV.010 | Define Data Conversion Requirements & Strategy
[DO] Documentation
| DO.010 | Define Documentation Requirements & Strategy |  | DO.010 | Define Documentation Requirements and Strategy
| DO.020 | Define Documentation Standards and Procedures
| DO.030 | Prepare Glossary
[TE] Business System Testing
| TE.010 | Define Testing Requirements and Strategy |  | TE.010 | Define Validation Strategy and Plan
[PT] Performance Testing
| PT.010 | Define Performance Testing Strategy
[AP] Adoption and Learning
| AP.010 | Define Executive Project Strategy
| AP.020 | Conduct Initial Project Team Orientation
| AP.030 | Develop Project Team Learning Plan
| AP.040 | Prepare Project Team Learning Environment
| AP.050 | Conduct Project Team Learning Events |  | TR.050 | Train Project Team
| AP.060 | Develop Business Unit Managers' Readiness Plan
| AP.070 | Develop Project Readiness Roadmap
| AP.080 | Develop & Execute Communication Campaign
B Operations Analysis
[BP] Business Process Architecture
| BP.080 | Develop Future Process Model |  | RD.011 | Update Business Process Model
[RD] Business Requirements Definition
| RD.030 | Establish Process and Mapping Summary
| RD.040 | Gather Business Volumes & Metrics
| RD.050 | Gather Business Requirements |  | MC.040 | Conduct Functional Design Workshops
| RD.060 | Determine Audit and Control Requirements
| RD.070 | Identify Business Availability Requirements
| RD.080 | Identify Reporting and Information Access Requirements
[BR] Business Requirements Mapping
| BR.010 | Analyze High-Level Gaps
| BR.020 | Prepare Mapping Environment |  | MC.070.1 IM.050.3 MC.070.2 MC.085 | Setup Applications Implement Extensions Implement Extensible Items Prepare Reports
| BR.030 | Map Business Requirements
| BR.040 | Map Business Data |  | CV.027 | Perform Data Mapping
| BR.050 | Conduct Integration Fit Analysis
| BR.060 | Create Information Model
| BR.070 | Conduct Reporting Fit Analysis
| BR.080 | Test Business Solutions |  | MC.080 TE.030 | Conduct Configuration Validation Workshops Validate Extensions
Confirm Integrated Business Solutions
[TA] Application and Technical Architecture
| TA.040 | Define Application Architecture
| TA.050 | Define System Availability Strategy
| TA.060 | Define Reporting and Information Access Strategy
| TA.070 | Revise Conceptual Architecture
[MD] Module Design and Build
| MD.020 | Define and Estimate Application Extensions
[DO] Documentation
| DO.040 | Prepare Documentation Environment
| DO.050 | Produce Documentation Prototypes and Templates
[PT] Performance Testing
| PT.020 | Identify Performance Test Scenarios
| PT.030 | Identify Performance Test Transaction Models
[AP] Adoption and Learning
| AP.090 | Develop Manager's Readiness Plan
[PM] Production Migration
| PM.010 | Define Transition Strategy |  | TS.020 | Define Cutover Strategy
C Solution Design
[BP] Business Process Architecture
| BP.090 | Document Business Procedures
[BR] Business Requirements Mapping
| BR.100 | Define Application Setups |  | MC.040 MC.050 | Conduct Functional Design Workshops Update Setup Documentation
| BR.110 | Design Security Profiles |  | MC.060 | Develop Security Strategy and Plan
[TA] Application and Technical Architecture
| TA.080 | Define Application Security Architecture |  | MC.060 | Develop Security Strategy and Plan
[MD] Module Design and Build
| MD.030 | Define Design Standards
| MD.040 | Define Build Standards
| MD.050 | Create Application Extensions Functional Design |  | DS.145 | Conduct Technical Design Workshops
| MD.060 | Design Database Extensions
| MD.070 | Create Application Extensions Technical Design |  | DS.145 | Conduct Technical Design Workshops
| MD.080 | Review Functional and Technical Designs |  | DS.160 | Conduct Design Reviews
[CV] Data Conversion
| CV.020 | Define Conversion Standards
| CV.030 | Prepare Conversion Environment
| CV.040 | Perform Conversion Data Mapping |  | CV.027 | Perform Data Mapping
| CV.050 | Define Manual Conversion Procedures |  | CV.053 | Prepare Data for Loading
| CV.060 | Design Conversion Programs
| CV.070 | Prepare Conversion Test Plans
[TE] Business System Testing
| TE.020 | Develop Unit Test Script
| TE.030 | Develop Link Test Script
| TE.040 | Develop System Test Script |  | TE.025 TE.027 | Prepare Validation Scripts Update Validation Scripts
| TE.050 | Develop Systems Integration Test Script |  | TE.025 TE.027 | Prepare Validation Scripts Update Validation Scripts
[PT] Performance Testing
| PT.040 | Create Performance Test Scripts
| PT.050 | Design Performance Test Transaction Programs
| PT.060 | Design Performance Test Data
| PT.070 | Design Test Database Load Programs
[AP] Adoption and Learning
| AP.100 | Identify Business Process Impact on Organization
| AP.110 | Align Human Performance Support Systems
| AP.120 | Align Information Technology Groups
| AP.130 | Conduct User Learning Needs Analysis
| AP.140 | Develop User Learning Plan
D Build
[TA] Application and Technical Architecture
| TA.090 | Define Application and Database Server Architecture
| TA.100 | Define & Propose Architecture Subsystems
| TA.110 | Define System Capacity Plan
| TA.120 | Define Platform and Network Architecture
| TA.130 | Define Application Deployment Plan
| TA.140 | Assess Performance Risks
| TA.150 | Define System Management Procedures
[MD] Module Design and Build
| MD.090 | Prepare Development Environment
| MD.100 | Create Database Extensions
| MD.110 | Create Application Extension Modules |  | IM.050.1 IM.050.2 | Implement Integration Packages - Oracle Implement Integration Packages - Customer Systems
| MD.120 | Create Installation Routines
[CV] Data Conversion
| CV.080 | Develop Conversion Programs
| CV.090 | Perform Conversion Unit Tests
| CV.100 | Perform Conversion Business Object Tests
| CV.110 | Perform Conversion Validation Tests |  | CV.065.1 | Load, Reconcile and Validate Data
[DO] Documentation
| DO.060 | Publish User Reference Manual
| DO.070 | Publish User Guide |  | DO.070 | Publish User Guide (i.e. Job Aid)
| DO.080 | Publish Technical Reference Manual
| DO.090 | Publish System Management Guide |  | DO.075 | Publish Admin Guide
[TE] Business System Testing
| TE.060 | Prepare Testing Environments |  | MC.070.4 | Setup Applications
| TE.070 | Perform Unit Test
| TE.080 | Perform Link Test
| TE.090 | Perform Installation Test
| TE.100 | Prepare Key Users for Testing |  | TE.105 | Prepare Users for Validation
| TE.110 | Perform System Test |  | TE.070 | Conduct End-to-End Review
| TE.120 | Perform Systems Integration Test |  | TE.045 | Validate Integration Packages
[PT] Performance Testing
| PT.080 | Create Performance Test Transaction Programs
| PT.090 | Create Test Database Load Programs
| PT.100 | Construct Performance Test Database
| PT.110 | Prepare Performance Test Environment
| PT.120 | Execute Performance Test
| PT.130 | Create Performance Test Report
[AP] Adoption and Learning
| AP.150 | Develop User Learningware |  | TR.080 | Prepare for Training
| AP.160 | Prepare User Learning Environment |  | TR.080 | Prepare for Training
[PM] Production Migration
| PM.020 | Design Production Support Infrastructure |  | TS.040 | Design Production Support Infrastructure
| PM.030 | Develop Transition & Contingency Plan |  | TS.020 | Define Cutover Strategy
E Transition
[CV] Data Conversion
| CV.120 | Install Conversion Programs
| CV.130 | Convert and Verify Data |  | CV.065.2 CV.065.3 | Load, Reconcile & Validate Data Load, Reconcile & Validate Data
[TE] Business System Testing
| TE,130 | Perform Acceptance Test |  | TE.120 | Conduct Final Validation Review with Users & Stakeholders
[AP] Adoption and Learning
| AP.070 | Conduct User Learning Events |  | TR.095 TR.100 | Conduct Train-the-Trainer Workshops Conduct End User Training
[PM] Production Migration
| PM.040 | Prepare Production Environment |  | TS.051 | Migrate Integrations and Extensions to Production
| PM.050 | Set Up Applications |  | TS.050 | Migrate Configuration to Production
| PM.060 | Implement Production Support Infrastructure |  | TS.052 | Implement Production Support Infrastructure
| PM.070 | Verify Production Readiness |  | TS.058 | Verify Production & Operational Readiness
| PM.080 | Begin Production |  | TS.060 | Begin Production Use
F Production
[AP] Adoption and Learning
| AP.180 | Conduct Effectiveness Assessment
[PM] Production Migration
| PM.090 | Measure System Performance
| PM.100 | Maintain System |  | PS.005 PS.065 | Manage Transition to Steady-state Operations Post Go-Live Support
| PM.110 | Refine Production System
| PM.120 | Decommission Former Systems
| PM.130 | Propose Future Business Direction
| PM.140 | Propose Future Technical Direction
PC Project Closure
| PMC.PCSUM1 | Gain Acceptance |  | PC.ACT.GA | Gain Acceptance
| PMC.PCSUM2 | Close Processes and Contract |  | PC.ACT.CPC | Close Processes and Contract
| PMC.PCSUM3 | Document Lessons Learned and Archive Project |  | PC.ACT.CPC | Close Processes and Contract