OUM

TS.030 Installation Plan

<Company Long Name>

<Subject>

When this template is completed, delete all the yellow notes as follows:

1. With your document open, open the Find and Replace window.
2. Expand the Find and Replace window using the More>> button.
3. Place the cursor in the Find what: field.
4. Choose Format > Style.
5. When the Find Style box opens, scroll through the list and select Note and click OK.
6. Leave the Replace with: field blank.
7. Select Replace, Replace All or Find Next to remove the yellow notes.
8. Repeat using the Note Wide style if there are any landscape sections that contain wide yellow notes.

Please refer to the OUM Template User’s Guide for detailed instructions for working with OUM templates.

Author:	<Author>

Creation Date:	May 14, 2014

Last Updated:	September 16, 2016

Document Ref:	<Document Reference Number>

Version:	DRAFT 1A

Title, Subject, Last Updated Date, Reference Number, and Version are marked by a Word Bookmark so that they can be easily reproduced in the header and footer of documents.  When you change any of these values, be careful not to accidentally delete the bookmark.  You can make bookmarks visible by selecting the Office Button>Word Options>Advanced> and checking the Show bookmarks option in the Show document content region.

Approvals:

| <Approver 1> |  |
| --- | --- |
| <Approver 2> |  |

To add additional approval lines, Press [Tab] from the last cell in the table above.

You can delete any elements of this cover page that you do not need for your document.

# Document Control

## Change Record

5

| Date | Author | Version | Change Reference |
| --- | --- | --- | --- |
| 14-May-14 | <Author> | Draft 1a | No Previous Document |

## Reviewers

| Name | Position |
| --- | --- |

Contents

1	Document Control	iii

1.1	Change Record	iii

1.2	Reviewers	iii

2	Introduction	1

2.1	Scope and Purpose	1

2.2	How to Review	1

3	Work Products	2

4	Assumptions	3

5	Usage Requirements	4

6	System Requirements	5

7	Software Installation	6

8	Transition Plan	7

8.1	General Tasks	7

8.2	Detailed Checklist Tasks	8

9	Transition Resources	15

10	Cutover Contingency Plan	16

10.1	Contingency Steps	16

10.2	Upon System Availability	16

11	Preparing for Production	17

11.1	Approach	17

12	Production Schedule - First Week	18

12.1	Using the Company Support Infrastructure	18

12.2	Information Systems Production Feedback Session	18

12.3	Support Status	19

13	Open and Closed Issues	20

13.1	Open Issues	20

13.2	Closed Issues	20

To update the table of contents, put the cursor anywhere in the table and press [F9].  To change the number of levels displayed, select the menu option Insert->Index and Tables, make sure the Table of Contents tab is active, and change the Number of Levels to a new value.

# Introduction

## Scope and Purpose

This document presents the Installation Plan for the <Application Name> system.  It describes the following:

work products

assumptions

system requirements

software installation

## How to Review

Use the following criteria when reviewing the Installation Plan:

Is the strategy in keeping with the business needs of the project?

Have all necessary equipment, resources and facilities been identified?

# Work Products

The following table details the key tasks (and their corresponding work products) to be carried out during the new system installation.

| Task | Key Work Product | Review Role | Sign-Off |
| --- | --- | --- | --- |

# Assumptions

Include in this sections any assumptions that are being made that will have an effect on the successful completion of the new system installation (for example, availability of hardware, availability of client staff)

Include with each assumption some form of indication as to on whom the assumption lies (for example, if there is an assumption for hardware to be in place then indicate the assumption is on the hardware supplier).

# Usage Requirements

Add details as to who will use the system, support levels required etc.

# System Requirements

Add details as to the operating requirements for the new system, such as operating system, hardware requirements, networks etc.

# Software Installation

Add details as to the installations required to be carried out.

# Transition Plan

This section includes a series of tasks, or checklists, to use during transition of the new system into production.  The general checklist is used to plan and estimate the Transition phase.  The specific checklist is used to guide the execution of the Transition phase.

Allocate sufficient time for executing the transition tasks.  Calculate backwards from the scheduled production to a transition start date.  Use the sample checklist tasks below as a starting point in assembling the appropriate checklist for the implementation.

Some checklist tasks cannot begin until other tasks are sufficiently completed.  Include these dependencies in the project workplan. 

Large or multi-site implementations may have additional dependencies, and may require that you execute some tasks more than once.  You may also need to arrange transition tasks sequentially.  For example, one site may transfer finished goods or materials to another.  The checklists use the word “Phase” or “Periodic” to indicate the repetition of a particular task.

## General Tasks

| Task | Description | Responsibility | Status: Phase 1 | Status: Phase 2 | Status: Periodic | Production Cutover Status |
| --- | --- | --- | --- | --- | --- | --- |
| Prepare Production Environment |  |  |  |  |  |  |
| Set Up Applications |  |  |  |  |  |  |
| Install Conversion Programs |  |  |  |  |  |  |
| Implement Production Support Infrastructure |  |  |  |  |  |  |
| Prepare User Learning Environment |  |  |  |  |  |  |
| Conduct User Learning Events |  |  |  |  |  |  |
| Perform Acceptance Test |  |  |  |  |  |  |
| Convert and Verify Data |  |  |  |  |  |  |
| Verify Production Readiness |  |  |  |  |  |  |
| Begin Production |  |  |  |  |  |  |

## Detailed Checklist Tasks

| Task | Description | Responsibility | Status: Phase 1 | Status: Phase 2 | Status: Periodic | Production Cutover Status |
| --- | --- | --- | --- | --- | --- | --- |
| TS.050 - Prepare Production Environment |  |  |  |  |  |  |
| Install the production servers. |  |  |  |  |  |  |
| Install the operating system and networking software on the servers. |  |  |  |  |  |  |
| Connect the servers to the network. |  |  |  |  |  |  |
| Create user accounts on the servers. |  |  |  |  |  |  |
| Configure the file system on the servers. |  |  |  |  |  |  |
| Install the user machines and connect them to the network. |  |  |  |  |  |  |
| Install the Oracle database on the database servers. |  |  |  |  |  |  |
| Install the applications servers. |  |  |  |  |  |  |
| Configure the standard applications database objects. |  |  |  |  |  |  |
| Create the custom database objects. |  |  |  |  |  |  |
| Install the custom modules. |  |  |  |  |  |  |
| Start up the database and verify its operation. |  |  |  |  |  |  |
| Install the system management tools. |  |  |  |  |  |  |
| Install printers and other peripheral devices. |  |  |  |  |  |  |
| Set remote synchronization system preferences | Note: If the implementation will include mobile users, System Preferences must be set to ensure that mobile user synchronization works as desired and that transaction logging is on. |  |  |  |  |  |
| Unit test remote synchronization rule changes | Remote synchronization should be tested to be sure that it is functioning correctly, and that changes are routed appropriately. If any changes have been made to the synchronization rules by Expert Services, they must be unit tested. |  |  |  |  |  |
| TS.050 - Set Up Applications |  |  |  |  |  |  |
| Run repository migration configuration utility as defined in Siebel Bookshelf. | Process will reference two different ODBC data sources (source database and target database). Will be necessary to manually create ODBC data source for target database. (Note: Follow process in Siebel Bookshelf for Microsoft servers or process for UNIX, as appropriate for environment.) If desired, update this table to include the steps for these tasks. |  |  |  |  |  |
| Create reference data from design. | Create List of Values, predefined queries, users, divisions, positions, etc. |  |  |  |  |  |
| Copy new or modified web templates, images and/or style sheets from the source environment to the target Siebel Server: Templates: (.swt files) siebsrvr_root\WEBTEMPL Images: (.gif or .jpg files) siebsrvr_root\webmaster\images\language_code Cascading Style Sheets: (.css files) siebsrvr_root\webmaster\files\language_code |  |  |  |  |  |  |
| Create required Marketing Admin Data |  |  |  |  |  |  |
| Create Required Mobile Client Admin Data |  |  |  |  |  |  |
| Create Application Meta-Data for In-Scope Siebel Modules | Note: Review and then define all the set up data that will be necessary to make the application run. Run unit tests of individual functions to confirm proper functioning of modules requiring such data. |  |  |  |  |  |
| Migrate any scripts and VB modules that are external to the repository |  |  |  |  |  |  |
| Create Workflow policies and associated data. |  |  |  |  |  |  |
| Insert Assignment Manager Rules. |  |  |  |  |  |  |
| Restart Siebel Application Server and selected services. (Note: Identify what specific server processes are needed to complete the update of the production environment. Update this table with the specific server components and processes that should be started at this time, such as EIM for batch updates of data; Workflow, EAI and System Management for using ADM to migrate customization data, e.g. LOV’s, Responsibilities, PDQ’s, etc. Update the table with all tasks to be performed for each release.) |  |  |  |  |  |  |
| <Placeholder: Specific jobs and processes that will be run to update system> |  |  |  |  |  |  |
| Bounce database |  |  |  |  |  |  |
| Run Siebel Server utility dbchck.exe (Windows) or dbchck (UNIX) to physical database schema with repository to verify that there are no inconsistencies. |  |  |  |  |  |  |
| Update database statistics with full table scan. |  |  |  |  |  |  |
| Restart all required server processes (Update plan to indicate all components that are to be started – do not leave this to memory). |  |  |  |  |  |  |
| Turn Transaction Logging to True, if it was turned off for performance reasons during batch updates. |  |  |  |  |  |  |
| Run Generate Triggers process. |  |  |  |  |  |  |
| Start Workflow Monitor. |  |  |  |  |  |  |
| Run Generate New Database Template, if implementation includes mobile users. |  |  |  |  |  |  |
| Verify that all interfaces between Siebel and other systems are working as expected. |  |  |  |  |  |  |
| Set up the application users in the new system. |  |  |  |  |  |  |
| Enter the application setups. |  |  |  |  |  |  |
| Load the initial setup data. |  |  |  |  |  |  |
| Load the setup data for application extensions. |  |  |  |  |  |  |
| Implement the security configuration. |  |  |  |  |  |  |
| Enter or load custom seed data. |  |  |  |  |  |  |
| Schedule Batch Files for System Integrations. |  |  |  |  |  |  |
| Verify the online operation of the applications. |  |  |  |  |  |  |
| Verify batch operation of the operations. |  |  |  |  |  |  |
| Back up the production system. |  |  |  |  |  |  |
| CV.064 - Install Conversion Components Initial Load |  |  |  |  |  |  |
| Install conversion programs and automated conversion tool software (if used). |  |  |  |  |  |  |
| List the location of each conversion program in the production environment. |  |  |  |  |  |  |
| List the location of any conversion tools in the production environment. |  |  |  |  |  |  |
| TS.052 - Implement Production Support Infrastructure |  |  |  |  |  |  |
| Set up a library. |  |  |  |  |  |  |
| Introduce the help desk to the organization. |  |  |  |  |  |  |
| Install communication equipment. |  |  |  |  |  |  |
| Set up and distribute reference materials. |  |  |  |  |  |  |
| Implement the online help text. |  |  |  |  |  |  |
| Implement the online issue tracking system. |  |  |  |  |  |  |
| Establish a change request and bug reporting procedure. |  |  |  |  |  |  |
| Establish online support. |  |  |  |  |  |  |
| Review procedures for getting help. |  |  |  |  |  |  |
| Distribute all support materials throughout the organization. |  |  |  |  |  |  |
| TR.090 - Prepare User Learning Environment |  |  |  |  |  |  |
| Review and update checklists. |  |  |  |  |  |  |
| Install user-learning environment. |  |  |  |  |  |  |
| Set up applications. |  |  |  |  |  |  |
| Set up support infrastructure. |  |  |  |  |  |  |
| Convert or add necessary sample data. |  |  |  |  |  |  |
| TR.100 - Conduct User Learning Events |  |  |  |  |  |  |
| Create human performance support communications. |  |  |  |  |  |  |
| Create user-learning communications. |  |  |  |  |  |  |
| Conduct human performance support orientation and learning events. |  |  |  |  |  |  |
| Hold user-learning events. |  |  |  |  |  |  |
| Monitor human performance support deployment progress. |  |  |  |  |  |  |
| Monitor skills-change progress. |  |  |  |  |  |  |
| TE.110 Prepare Acceptance Test Environment and TE.120 - Support Acceptance Test |  |  |  |  |  |  |
| Review responsibilities for the acceptance test with the team. |  |  |  |  |  |  |
| Back-up production environment for later availability |  |  |  |  |  |  |
| Validate the acceptance test environment. |  |  |  |  |  |  |
| Execute the acceptance test script. |  |  |  |  |  |  |
| Document the test results. |  |  |  |  |  |  |
| Summarize the test results. |  |  |  |  |  |  |
| Determine required actions for problem resolution. |  |  |  |  |  |  |
| Make recommendations for application changes or corrections based on acceptance testing. |  |  |  |  |  |  |
| Secure acceptance of the acceptance test results. |  |  |  |  |  |  |
| CV.065 - Convert and Verify Data |  |  |  |  |  |  |
| Verify that legacy data pre-conversion cleanup has been completed. |  |  |  |  |  |  |
| Describe the data conversion and verification sequence of events. |  |  |  |  |  |  |
| Record the sequence in which the download programs should be run and additional important information about the programs. |  |  |  |  |  |  |
| Record the sequence in which the interface table creation programs should be run and additional important information about the programs. |  |  |  |  |  |  |
| Record the sequence in which the upload programs should be run and additional important information about the programs. |  |  |  |  |  |  |
| Record the sequence in which the translation programs should be run and additional important information about the programs. |  |  |  |  |  |  |
| Record the sequence in which the interface/validation programs should be run and additional important information about the programs. |  |  |  |  |  |  |
| Run the conversion programs to convert the legacy system data. |  |  |  |  |  |  |
| Verify the converted data. |  |  |  |  |  |  |
| Secure acceptance that the Converted and Verified Data meets Century Date compliance standards. |  |  |  |  |  |  |
| TS.058 - Verify Production Readiness |  |  |  |  |  |  |
| Review the production readiness verification checklist. |  |  |  |  |  |  |
| Conduct production readiness verification. |  |  |  |  |  |  |
| Confirm the production cutover. |  |  |  |  |  |  |
| Prepare the support team. |  |  |  |  |  |  |
| Obtain agreement for the initial production schedule. |  |  |  |  |  |  |
| Verify that users are trained. |  |  |  |  |  |  |
| Verify commitment and readiness of internal and external support personnel. |  |  |  |  |  |  |
| Verify the completion of production environment. |  |  |  |  |  |  |
| Confirm senior management commitment via the steering committee. |  |  |  |  |  |  |
| Distribute the initial production schedule. |  |  |  |  |  |  |
| Obtain approval for beginning production. |  |  |  |  |  |  |
| TS.060 - Go Production |  |  |  |  |  |  |
| Initiate using the production system. |  |  |  |  |  |  |
| Initiate incident/technical issue management procedures. |  |  |  |  |  |  |
| Initiate open issues and create a resolution list. |  |  |  |  |  |  |
| Initiate support. |  |  |  |  |  |  |
| Confirm that all components of the production system are operational. |  |  |  |  |  |  |
| Declare the new system live. |  |  |  |  |  |  |

# Transition Resources

# Cutover Contingency Plan

Upon a <Company Short Name> decision not to go into production, the project team will follow the Cutover Contingency Plan outlined below.  Use of the Implementation Contingency plan is a temporary state.  It allows the project team to coordinate efforts until resolution of the factors that caused initiation of the plan.  <Company Short Name> management will alert the company of the final production date.

## Contingency Steps

- Restore former system and reset any dates, security, and so on, in order to resume normal production.

- Login to the former system to verify access.  If access is not available, call the following support number:

- Use the manual forms defined in the User Reference and Procedures Manual to track business transactions.  Date stamp all transactions.

- Submit the manual transactions to your manager for cross validation.

- Request archived or historical data from source (third-party storage or paper copy) to provide inquiry or reference information.

- Create manual forms for external documents such as order entry acknowledgment, shipment, invoices, and purchase orders.  See the User Reference Manuals and User Procedures Manuals for content.

- Wait until <Company Short Name> management announces availability of the production system.

## Upon System Availability

Verify the system date and begin recording the manual transactions.

Submit any changes or updates that require information systems assistance to the IS Manager.

Retain transaction copies for internal audits.

Resume entry of transactions online.

# Preparing for Production

This template ensures that the company plans and schedules operations in a manner capable of support by the information technology and consulting organization.

Making sure there is a support structure, setting expectations, and establishing a feedback process can significantly improve the results of the initial production week.

## Approach

Based on prior business system testing and user learning, the functionality of the production system should not be a surprise to the user community.  However, careful management of the initial production week can minimize organizational impact.  During the first week, provide additional control over the operational and support flow for all organizations.

The approach used in preparing for production is as follows:

Determine production schedules for financial, human resources, distribution, and manufacturing operations.

Assign analysts, users, or consultants to answer questions, fix problems, and provide real time training as needed.

Establish a user feedback mechanism.

Manage expectations by documenting the support priorities.

Update internal and external support channels based on the production date.

# Production Schedule - First Week

You must get commitment from department managers for the production schedule.  If you provide the right level of support, most client managers will agree to the careful orchestration of production.  If no major problems arise, normal operational procedures can begin as soon as the second day of production.

Under the process column, list the departments or processes that can begin transactions at a set point in time.  During their dedicated period, information systems will provide full support to that organization.

The operations schedule for the first week of production follows:

| Start Process | Cut Off Time (Optional) | Process | Internal Support | Super User Contact |
| --- | --- | --- | --- | --- |
| 07:00 AM |  |  |  |  |
| 08:00 AM |  |  |  |  |
| 09:00 AM |  |  |  |  |
| 10:00 AM |  |  |  |  |
| 11:00 AM |  |  |  |  |
| 12:00 noon |  |  |  |  |
| 01:00 PM |  |  |  |  |
| 02:00 PM |  |  |  |  |
| 03:00 PM |  |  |  |  |
| 04:00 PM |  |  |  |  |
| 05:00 PM |  |  |  |  |
| 06:00 PM |  |  |  |  |
| 07:00 PM |  |  |  |  |
| 08:00 PM |  |  |  |  |

## Using the Company Support Infrastructure

After production cutover, use the following process for contacting support:

- Dial the internal support number.

- Provide name and phone number.

- State priority of call.

- Describe the problem.

- If required, send supporting materials and references in production system to support.

## Information Systems Production Feedback Session

The project team will hold feedback sessions at the close of each business day for the first production week.

Location:

Time:

Attendees:

Users are encouraged to attend or send a representative with any issues, questions, or comments regarding the new system.

Priority

The information systems staff will be working to resolve any potential issues according to the established priorities.  We will address all issues.  All issues will be resolved based on their potential impacts to the business operations.  For example, issues preventing fundamental business operations will take precedence over reporting requirement.  Issues will be assigned a high, medium, or low priority.

Issues are prioritized based on the following system areas:

- Database

- Transaction Processing

- Interfaces

- Setup Modifications

- Reports

- Questions

## Support Status

Oracle Support has been notified of our production status and a dedicated resource will manage the technical assistance requests submitted during the first week.

Oracle Support Manager:

Support Telephone Number:

All standard functions will be communicated to support.  Oracle analysts will log all support calls and provide feedback to the users.  Additional information, tests, or reruns of the process may be required to expedite the support process.

# Open and Closed Issues

Add open issues that you identify while writing or reviewing this document to the open issues section.  As you resolve issues, move them to the closed issues section and keep the issue ID the same.  Include an explanation of the resolution.

When this work product is complete, any open issues should be transferred to the project- or process-level Issue Log (PJM) and managed using a project level Issue Form (PJM).  In addition, the open items should remain in the open issues section of this work product, but flagged in the resolution column as being transferred.

## Open Issues

| ID | Issue | Resolution | Responsibility | Target Date | Impact Date |
| --- | --- | --- | --- | --- | --- |

## Closed Issues

| ID | Issue | Resolution | Responsibility | Target Date | Impact Date |
| --- | --- | --- | --- | --- | --- |