## PSFT
Compass Phase | Compass Activity | Compass Step | OUM Mapping | OUM Mapping | Description
Strategy Phase |  |  | Envision Focus Area
* * Activities within the Strategy Phase are completed during the Business Development / Sales cycle * *
* * and are not listed here in order not to confuse anyone. * *
Planning Phase |  |  | Inception
* * Activities listed in Planning may have already occurred during the Business Development / Sales cycle * *
* * if not completed, they should be completed to kickoff the project. * *
| Execute Upgrade Planning Workshop |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Communicate, Coordinate, and Schedule Upgrade Planning Workshop |  | PS | OUM Manage Focus Area - Project Start Up
|  | Conduct Upgrade Planning Workshop |  | PS | OUM Manage Focus Area - Project Start Up
|  | Finalize and Distribute Upgrade Planning Workshop Charter |  | PS | OUM Manage Focus Area - Project Start Up
|  | Execute Upgrade Planning Workshop Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Execute Technology Assessment Workshop |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Communicate, Coordinate, and Schedule Technology Assessment Workshop |  | TA.010 | Conduct Technical Architecture Workshop
|  | Conduct Technology Assessment Workshop |  | TA.010 | Conduct Technical Architecture Workshop
|  | Finalize and Distribute Technology Assessment Report |  | TA.010 | Conduct Technical Architecture Workshop
|  | Execute Technology Assessment Workshop Complete |  | TA.010 | Conduct Technical Architecture Workshop
Close Planning Phase
Close Planning Phase
Structure Phase |  |  | Elaboration
| Perform Upgrade Customer Launch |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Conduct Administrative Setup |  | PS | OUM Manage Focus Area - Project Start Up
|  | Order Application Software |  | PS | OUM Manage Focus Area - Project Start Up
|  | Initiate Launch Meeting Preparation |  | PS | OUM Manage Focus Area - Project Start Up
|  | Perform PeopleSoft University Process |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Installation Requirements |  | PS | OUM Manage Focus Area - Project Start Up
|  | Conduct Launch Meeting |  | PS | OUM Manage Focus Area - Project Start Up
|  | Conduct Launch Termination |  | PS | OUM Manage Focus Area - Project Start Up
|  | Perform Upgrade Customer Launch Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Define Mission, Objectives, and Performance Measures |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Project Mission Statement |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Project Objectives and Performance Measures |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Mission, Objectives, and Performance Measures Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Define Assumptions, Constraints, Risks, and Other Critical Path Projects |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Assumptions |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Constraints |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Risks |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Other Critical Path Projects |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Assumptions, Constraints, Risks, and other Critical Path Projects Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create Project Team |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Validate Resource Requirements |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Roles and Responsibilities for Project |  | PS | OUM Manage Focus Area - Project Start Up
|  | Assemble Project Team Members |  | PS | OUM Manage Focus Area - Project Start Up
|  | Prepare for Project Team Kickoff Meetings |  | PS | OUM Manage Focus Area - Project Start Up
|  | Conduct Project Team Kickoff Meetings |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create Project Team Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Define Project Standards and Administration |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Acquire Team Work Location |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create Project Diary |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create Project Administration Guidelines |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Issue Resolution Procedures |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Project Plan Maintenance Procedures |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Operating Agreements |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Technical Project Standards |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Project Standards and Administration Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create Quality Plan |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Draft Quality Plan |  | PS | OUM Manage Focus Area - Project Start Up
|  | Determine the Quality Review Process |  | PS | OUM Manage Focus Area - Project Start Up
|  | Determine Quality Needs, Establish Quality Standards, and Design Quality Control Processes |  | PS | OUM Manage Focus Area - Project Start Up
|  | Finalize Quality Plan |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create Quality Plan Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create Organization and Business Process Change Management Plan |  |  | OCM | Organisation Change Management Process
|  | Define Organization Change Management Approach |  | OCM | Organisation Change Management Process
|  | Define Business Process Change Management Approach |  | OCM | Organisation Change Management Process
|  | Establish Organization Change Management Procedures |  | OCM | Organisation Change Management Process
|  | Establish Business Process Change Management Procedures |  | OCM | Organisation Change Management Process
|  | Finalize and Document Organization and Business Process Change Management Plan |  | OCM | Organisation Change Management Process
|  | Create Organization and Business Process Change Management Plan Complete |  | OCM | Organisation Change Management Process
| Create Functional Configuration and Scope Change Management Plan |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Functional Configuration Change Management Approach |  | PS | OUM Manage Focus Area - Project Start Up
|  | Define Scope Change Management Approach |  | PS | OUM Manage Focus Area - Project Start Up
|  | Establish Functional Configuration Change Management Procedures |  | PS | OUM Manage Focus Area - Project Start Up
|  | Establish Scope Change Management Procedures |  | PS | OUM Manage Focus Area - Project Start Up
|  | Finalize and Document Functional Configuration and Scope Change Management Plan |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create Functional Configuration and Scope Change Management Plan Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create Software Configuration Management Plan for Project |  |  | CM | Configuration Management Process
|  | Define Software Configuration Management Approach for Project |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Establish Software Configuration Management Procedures for Project |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Finalize and Document Software Configuration Management Plan for Project |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Implement Current Production System Change Management Controls |  | CM.040 | Create and Execute Software Configuration Management Plan
|  | Create Software Configuration Management Plan for Project Complete |  | CM.040 | Create and Execute Software Configuration Management Plan
| Create Project Team Communication Plan |  |  | CMM.020 | Develop Project Team Communication Plan
|  | Assess Project Team Communication Requirements |  | CMM.020 | Develop Project Team Communication Plan
|  | Develop Project Team Communication Tools |  | CMM.020 | Develop Project Team Communication Plan
|  | Develop Project Team Communication Plan |  | CMM.020 | Develop Project Team Communication Plan
|  | Create Project Team Communication Plan Complete |  | CMM.020 | Develop Project Team Communication Plan
| Establish Technical Architecture Performance Requirements |  |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Define Overall Technical Architecture Performance Requirements |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Define Database Performance Requirements |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Define Network Performance Requirements |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Define Server and Workstation Performance Requirements |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Establish Technical Architecture Performance Requirements Complete |  | B.PT.020 | Define Performance Management Requirements and Strategy
| Create Organization Communication Plan |  |  | OCM | Organisation Change Management Process
|  | Assess Organization Communication Requirements |  | OCM | Organisation Change Management Process
|  | Develop Organization Communication Tools |  | OCM | Organisation Change Management Process
|  | Develop Organization Communication Plan |  | OCM | Organisation Change Management Process
|  | Create Organization Communication Plan Complete |  | OCM | Organisation Change Management Process
| Create External Communication Plan |  |  | OCM | Organisation Change Management Process
|  | Assess External Communication Requirements |  | OCM | Organisation Change Management Process
|  | Develop External Communication Tools |  | OCM | Organisation Change Management Process
|  | Develop External Communication Plan |  | OCM | Organisation Change Management Process
|  | Create External Communication Plan Complete |  | OCM | Organisation Change Management Process
| Create Marketing Communication Plan |  |  | OCM | Organisation Change Management Process
|  | Assess Marketing Communication Requirements |  | OCM | Organisation Change Management Process
|  | Develop Marketing Communication Tools |  | OCM | Organisation Change Management Process
|  | Develop Marketing Communication Plan |  | OCM | Organisation Change Management Process
|  | Create Marketing Communication Plan Complete |  | OCM | Organisation Change Management Process
| Assess Business Needs and Impact |  |  | A.ACT.GBRI | Gather Business Requirements - Inception
|  | Obtain and Review Application Architecture |  | TA.004 | Perform Technical Architecture Impact Analysis
|  | Obtain Organization Business Process Models |  | A.RD.030 | Review Current Business Process Model
|  | Prepare for Needs Assessment Sessions |  | A.ACT.PIA | Perform Impact Analysis
|  | Conduct Needs Assessment Sessions |  | A.ACT.PIA | Perform Impact Analysis
|  | Document and Analyze Needs Assessment Results |  | A.ACT.PIA | Perform Impact Analysis
|  | Identify Potential Customization Requirements |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Assess Business Needs and Impact Complete |  | A.ACT.PIA | Perform Impact Analysis
| Define Project Strategies and Plan Project Scope |  |  | B.ACT.DPS | Define Project Strategy
|  | Define Strategy and Plan Scope for Functional Applications |  | B.ACT.DPS | Define Project Strategy
|  | Define Strategy and Plan Scope for Customizations |  | DS.020 | Define Application Extension Strategy
|  | Define Strategy and Plan Scope for Conversion |  | CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy
|  | Define Strategy and Plan Scope for Interfaces |  | DS.020 | Define Application Extension Strategy
|  | Define Strategy and Plan Scope for Reporting |  | TA.040 | Define Reporting and Information Access Strategy
|  | Define Strategy and Plan Scope for Workflow |  | TA.010 SM.030 | * Conduct Technical Architecture Workshop * Manage Scope
|  | Define Strategy and Plan Scope for Graphical Style for Web |  | DS.020 | Define Application Extension Strategy
|  | Define Strategy and Plan Scope for Content Management Process |  | DS.020 | Define Application Extension Strategy
|  | Define Strategy and Plan Scope for Information Architecture |  | RD.130 RA.019 TA.010 | * Develop Baseline Architecture Description * Define Project Reference Architecture * Conduct Technical Architecture Workshop
|  | Define Strategy and Plan Scope for Web Integration |  | DS.020 | Define Application Extension Strategy
|  | Define Strategy and Plan Scope for Application Security |  | TA.090 | Develop Security and Control Strategy
|  | Define Strategy and Plan Scope for System Security |  | TA.090 | Develop Security and Control Strategy
|  | Define Strategy and Plan Scope for Project Team Training |  | A.TR.010.1 | Prepare Training Strategy
|  | Define Strategy and Plan Scope for End-User Training |  | A.TR.010.1 | Prepare Training Strategy
|  | Define Strategy and Plan Scope for Communications |  | OCM | Organization Change Management Process
|  | Define Strategy and Plan Scope for Testing |  | B.TE.010 | Develop Testing Strategy
|  | Define Project Strategies and Plan Project Scope Complete |  | B.TE.010 | Develop Testing Strategy
| Define Project Approaches |  |  | RD.001 | Detail Business and System Objectives
|  | Define Help Desk/Knowledge Base Approach |  | TA.060 | Define System Operations and Management Strategy
|  | Define Go-Live Contingency Approach |  | TS.020 | Define Cutover Strategy
|  | Define Development Support Approach |  | DS.020 DS.050 | Define Application Extension Strategy Determine Design and Build Standards
|  | Define Production Support Approach |  | TA.070 | Define Initial Architecture and Application Mapping
|  | Define Test Move to Production Approach |  | TA.080 | Define Backup and Recovery Strategy Backup and Recovery Strategy
|  | Define Move to Production Approach |  | TS.020 | Define Cutover Strategy
|  | Define Parallel Deployment Approach |  | TS.020 | Define Cutover Strategy
|  | Define Disaster Recovery Approach |  | TA.050 | Define Disaster Recovery Strategy Disaster Recovery Strategy
|  | Define PeopleSoft Upgrade Approach |  | RD.001 | Detail Business and System Objectives
|  | Define Project Approaches Complete |  | PS | OUM Manage Focus Area - Project Execution and Control
| Assess and Define Software Configuration Management Requirements and Impact |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Software Configuration Management Requirements |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess Software Configuration Management Tools |  | TA.010 | Conduct Technical Architecture Workshop
|  | Document and Analyze Requirements and Current Environment Findings |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Potential Upgrades and/or Changes to Software Configuration Management Processes |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Software Configuration Management Strategy |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess and Define Software Configuration Management Requirements and Impact Complete |  | TA.010 | Conduct Technical Architecture Workshop
| Assess and Define Database Requirements and Impact |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Database Requirements |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess Existing Database |  | TA.010 | Conduct Technical Architecture Workshop
|  | Document and Analyze Requirements and Current Environment Findings |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Potential Database Upgrades |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Database Strategy |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess and Define Database Requirements and Impact Complete |  | TA.010 | Conduct Technical Architecture Workshop
| Assess and Define Network Requirements and Impact |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Network Requirements |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess Existing Network |  | TA.010 | Conduct Technical Architecture Workshop
|  | Document and Analyze Requirements and Current Environment Findings |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Potential Network Upgrades |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Network Strategy |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess and Define Network Requirements and Impact Complete |  | TA.010 | Conduct Technical Architecture Workshop
| Assess and Define Server and Workstation Requirements and Impact |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify All Impacted Server and Workstation Components |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Server and Workstation Requirements |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess Existing Server and Workstation Environment |  | TA.010 | Conduct Technical Architecture Workshop
|  | Document and Analyze Requirements and Current Server and Workstation Environment Findings |  | TA.010 | Conduct Technical Architecture Workshop
|  | Identify Potential Server and Workstation Upgrades |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Server and Workstation Strategy |  | TA.010 | Conduct Technical Architecture Workshop
|  | Assess and Define Server and Workstation Requirements and Impact Complete |  | TA.010 | Conduct Technical Architecture Workshop
| Assess and Define Performance Monitoring Requirements and Impact |  |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Identify Infrastructure Components Included in Monitoring |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Identify Performance Monitoring Requirements |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Determine and Publish Enterprise Environment Variables |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Assess Existing Performance Monitoring Environment |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Document and Analyze Requirements and Current Environment Findings |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Identify Potential Performance Monitoring Upgrades |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Define Performance Monitoring Strategy |  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | Assess and Define Performance Monitoring Requirements and Impact Complete |  | B.PT.020 | Define Performance Management Requirements and Strategy
| Consolidate Comprehensive Technical Architecture Strategy and Scope |  |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Preliminary Comprehensive Technical Architecture Strategy and Scope |  | TA.010 | Conduct Technical Architecture Workshop
|  | Define Comprehensive Technical Architecture Maintenance Strategy |  | TA.010 | Conduct Technical Architecture Workshop
|  | Finalize Comprehensive Technical Architecture Upgrades |  | TA.010 | Conduct Technical Architecture Workshop
|  | Create Comprehensive Technical Architecture Strategy and Scope Document |  | TA.010 | Conduct Technical Architecture Workshop
|  | Consolidate Comprehensive Technical Architecture Strategy and Scope Complete |  | TA.010 | Conduct Technical Architecture Workshop
| Consolidate Overall Scope Plan |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Consolidate and Reconcile Project Scope |  | PS | OUM Manage Focus Area - Project Start Up
|  | Identify Future Project Considerations |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Project Scope and Future Project Considerations with Project Sponsor |  | PS | OUM Manage Focus Area - Project Start Up
|  | Consolidate Overall Scope Plan Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create High-Level Project Plan |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Develop High-Level Project Plan |  | PS | OUM Manage Focus Area - Project Start Up
|  | Create High-Level Project Plan Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Publish Project Charter |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Assemble Deliverables Included in Charter |  | PS | OUM Manage Focus Area - Project Start Up
|  | Distribute Charter to Steering Committee |  | PS | OUM Manage Focus Area - Project Start Up
|  | Publish Project Charter Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Quality Review Checkpoint - Planning and Project Charter |  |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Project Deliverables |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Project Plan and Resources |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Project Processes |  | PS | OUM Manage Focus Area - Project Start Up
|  | Review Statement of Service and Current Scope |  | PS | OUM Manage Focus Area - Project Start Up
|  | Document Project Review Findings |  | PS | OUM Manage Focus Area - Project Start Up
|  | Quality Review Checkpoint Complete |  | PS | OUM Manage Focus Area - Project Start Up
| Create Project Environments |  |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Procure Hardware, Software, and Services |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Review Install Options |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Prepare Environments |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Perform Certified Installation of the PeopleSoft System |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | PeopleSoft Install |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Customer Self-Install |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Apply Updates and Fixes to Appropriate Environments |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Create Database Environments |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Provide Remote Access |  | B.ACT.PEE | Prepare Environments - Elaboration
|  | Create Project Environments Complete |  | B.ACT.PEE | Prepare Environments - Elaboration
| Delta Train Project Team |  |  | B.ACT.TPT | Train Project Team
|  | Review the Project Team Training Strategy and Scope |  | B.ACT.TPT | Train Project Team
|  | Identify Project Team Training Requirements |  | B.ACT.TPT | Train Project Team
|  | Create Project Team Training Plan and Schedule |  | B.ACT.TPT | Train Project Team
|  | Attend Training Sessions |  | B.ACT.TPT | Train Project Team
|  | Delta Train Project Team Complete |  | B.ACT.TPT | Train Project Team
| Create Parallel Deployment Plan |  |  | TS.020 | Define Cut-Over Strategy
|  | Review Parallel Deployment Approach |  | TS.020 | Define Cut-Over Strategy
|  | Determine Parallel Deployment Plan Requirements |  | TS.020 | Define Cut-Over Strategy
|  | Draft Parallel Deployment Plan |  | TS.020 | Define Cut-Over Strategy
|  | Finalize and Document Parallel Deployment Plan |  | TS.020 | Define Cut-Over Strategy
|  | Create Parallel Deployment Plan Complete |  | TS.020 | Define Cut-Over Strategy
| Create Development Support Plan |  |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Review the Development Support Approach and the Software Configuration Management Plan for Project |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Determine Development Support Requirements |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Draft New Development Support Plan |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Finalize and Document Development Support Plan |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Create Development Support Plan Complete |  | CM.010 | Develop Configuration Management Strategy and Processes
| Perform Vanilla Comparisons |  |  | RD.134 | Identify New Release Changes
|  | Perform Vanilla Comparisons |  | RD.134 | Identify New Release Changes
|  | Create Vanilla Summary Document |  | RD.134 | Identify New Release Changes
|  | Perform Vanilla Comparisons Complete |  | RD.134 | Identify New Release Changes
| Perform Upgrade Preparation through Object Analysis |  |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Execute Upgrade Instructions - Upgrade Preparation through Object Analysis |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Create Object Summary Document |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Perform Upgrade Preparation through Object Analysis Complete |  | A.RD.136 | Perform Custom Extension Impact Analysis
| Perform Batch Analysis |  |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Perform Batch Schedule/Processing Analysis |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Perform Batch Program Analysis |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Create Batch Analysis Summary Document |  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | Perform Batch Analysis Comparison Complete |  | A.RD.136 | Perform Custom Extension Impact Analysis
| Perform Delta Fit/Gap Analysis |  |  | B.ACT.PGA | Perform Gap Analysis
|  | Define Technical Environment for Fit/Gap |  | B.ACT.PGA | Perform Gap Analysis
|  | Review Assess Business Needs and Impact, and Draft Fit/Gap Schedule |  | B.ACT.PGA | Perform Gap Analysis
|  | Review Existing Fit/Gap Documentation |  | B.ACT.PGA | Perform Gap Analysis
|  | Define Business Events and Scenarios for Fit/Gap |  | B.ACT.PGA | Perform Gap Analysis
|  | Model Business Processes |  | B.ACT.PGA | Perform Gap Analysis
|  | Model Logical Data |  | B.ACT.PGA | Perform Gap Analysis
|  | Configure and Set Up Functional Environment for Fit/Gap |  | B.ACT.PGA | Perform Gap Analysis
|  | Review and Customize Necessary Objects for Fit/Gap |  | B.ACT.PGA | Perform Gap Analysis
|  | Finalize Fit/Gap Schedule |  | B.ACT.PGA | Perform Gap Analysis
|  | Perform Fit/Gap Sessions |  | B.ACT.PGA | Perform Gap Analysis
|  | Document Initial Functional Specifications |  | B.ACT.PGA | Perform Gap Analysis
|  | Finalize Fit/Gap Document |  | B.ACT.PGA | Perform Gap Analysis
|  | Validate Potential Customization Requirements |  | B.ACT.PGA | Perform Gap Analysis
|  | Perform Delta Fit/Gap Analysis Complete |  | B.ACT.PGA | Perform Gap Analysis
| Perform Configuration Test |  |  | TE | Managed across the complete TE Process
|  | Review and Update Configuration and Setup of Base Tables for Configuration Test |  | TE | Managed across the complete TE Process
|  | Create Configuration Test Plan |  | TE | Managed across the complete TE Process
|  | Create Configuration Test Scripts |  | TE | Managed across the complete TE Process
|  | Execute Configuration Test |  | TE | Managed across the complete TE Process
|  | Resolve Configuration Test Issues |  | TE | Managed across the complete TE Process
|  | Update Base Table Configuration and Setup Documentation |  | TE | Managed across the complete TE Process
|  | Validate Potential Customization Requirements |  | TE | Managed across the complete TE Process
|  | Perform Configuration Test Complete |  | TE | Managed across the complete TE Process
| Reconcile Object and Functionality Decisions |  |  | B.ACT.PGA | Perform Gap Analysis
|  | Review Object Summary, Batch Comparison Summary and Delta Fit/Gap Documents |  | B.ACT.PGA | Perform Gap Analysis
|  | Finalize Upgrade Decisions |  | B.ACT.PGA | Perform Gap Analysis
|  | Document Upgrade Decisions |  | B.ACT.PGA | Perform Gap Analysis
|  | Reconcile Object and Functionality Decisions Complete |  | B.ACT.PGA | Perform Gap Analysis
| Perform Upgrade Copy Overrides |  |  | B.ACT.PGA | Perform Gap Analysis
|  | Execute Upgrade Instructions - Upgrade Copy Overrides |  | B.ACT.PGA | Perform Gap Analysis
|  | Perform Upgrade Copy Overrides Complete |  | B.ACT.PGA | Perform Gap Analysis
| Define Gap Solutions and Functional Specifications |  |  | B.MC.100 | Define and Estimate Application Extensions
|  | Determine Alternatives and Solutions |  | B.MC.100 | Define and Estimate Application Extensions
|  | Define High-Level Estimates |  | B.MC.100 | Define and Estimate Application Extensions
|  | Finalize and Document Gap Solutions and Functional Specifications |  | B.MC.100 | Define and Estimate Application Extensions
|  | Prioritize Gap Solutions and Functional Specifications |  | B.MC.100 | Define and Estimate Application Extensions
|  | Define Gap Solutions and Functional Specifications Complete |  | B.MC.100 | Define and Estimate Application Extensions
| Finalize Project Scope |  |  | SM.010 | Define and Confirm Scope
|  | Finalize Project Scope |  | SM.010 | Define and Confirm Scope
|  | Finalize Project Scope Complete |  | SM.010 | Define and Confirm Scope
| Create Draft Project Plan |  |  | WM.010 | Develop Baseline Project Workplan
|  | Develop Draft Project Plan |  | WM.010 | Develop Baseline Project Workplan
|  | Create Draft Project Plan Complete |  | WM.010 | Develop Baseline Project Workplan
| Quality Review Checkpoint - Delta Fit/Gap Functional Requirements and Specifications |  |  | QM.040 | Manage Quality Control
|  | Review Project Deliverables |  | QM.040 | Manage Quality Control
|  | Review Project Plan and Resources |  | QM.040 | Manage Quality Control
|  | Review Project Processes |  | QM.040 | Manage Quality Control
|  | Review Statement of Service and Current Scope |  | QM.040 | Manage Quality Control
|  | Document Project Review Findings |  | QM.040 | Manage Quality Control
|  | Quality Review Checkpoint Complete |  | QM.040 | Manage Quality Control
| Close Structure Phase |  |  | PE | OUM Manage Focus Area - Project Execution and Control
|  | Close Structure Phase |  | PE | OUM Manage Focus Area - Project Execution and Control
Construct Phase |  |  | Construction
| Perform Copy through Final Cleanup |  |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Execute Upgrade Instructions - Copy through Final Cleanup |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Perform Copy through Final Cleanup Complete |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
| Create Test Move to Production Plan |  |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Review Test Move to Production Approach |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Determine Test Move to Production Plan Requirements |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Draft Test Move to Production Plan |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Finalize and Document Test Move to Production Plan |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
|  | Create Test Move to Production Plan Complete |  | B.ACT.VUPE | Validate Upgrade Process - Elaboration
| Design Software Configuration Management for Production |  |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Review/Update Software Configuration Management Requirements for Production |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Develop Plan for Software Configuration Management for Production |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Create Design for Software Configuration Management for Production |  | CM.010 | Develop Configuration Management Strategy and Processes
|  | Design Software Configuration Management for Production Complete |  | CM.010 | Develop Configuration Management Strategy and Processes
| Design Production Database |  |  | B.DS.150 | Develop Database Design
|  | Review/Update Production Database Requirements |  | B.DS.150 | Develop Database Design
|  | Develop Plan for Production Database Upgrade and Maintenance |  | B.DS.150 | Develop Database Design
|  | Create Production Database Design |  | B.DS.150 | Develop Database Design
|  | Design Production Database Complete |  | B.DS.150 | Develop Database Design
| Design Network |  |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Review/Update Network Requirements |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Develop Plan for Network Upgrade and Maintenance |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Create Network Design |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Design Network Complete |  | B.TA.070 | Define Initial Architecture and Application Mapping
| Design Server and Workstation |  |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Review/Update Server and Workstation Requirements |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Develop Plan for Server and Workstation Upgrade and Maintenance |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Create Server and Workstation Design |  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | Design Server and Workstation Complete |  | B.TA.070 | Define Initial Architecture and Application Mapping
| Design Performance Monitoring |  |  | A.PT.010 | Conduct Performance Management Workshop
|  | Review/Update Performance Monitoring Requirements |  | A.PT.010 | Conduct Performance Management Workshop
|  | Develop Plan for Performance Monitoring Upgrade and Maintenance |  | A.PT.010 | Conduct Performance Management Workshop
|  | Create Design for Performance Monitoring |  | A.PT.010 | Conduct Performance Management Workshop
|  | Design Performance Monitoring Complete |  | A.PT.010 | Conduct Performance Management Workshop
| Design Technical Architecture |  |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Incorporate Component Designs into Comprehensive Technical Architecture Design |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Define Comprehensive Technical Architecture Detail for Project Plan |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Design Technical Architecture Complete |  | C.TA.150 | Define Final Platform and Network Architecture
| Design Customizations |  |  | DS | DS - Design Process
|  | Review/Update Functional Specifications for Customizations |  | DS | DS - Design Process
|  | Define Customization Detail for Project Plan |  | DS | DS - Design Process
|  | Create/Update Technical Specifications for Customizations |  | DS | DS - Design Process
|  | Design Customizations Complete |  | DS | DS - Design Process
| Design Conversions |  |  | CV /DS | CV/DS - Conversion and Design Processes
|  | Review/Update Functional Specifications for Conversions |  | CV /DS | CV/DS - Conversion and Design Processes
|  | Define Conversion Detail for Project Plan |  | CV /DS | CV/DS - Conversion and Design Processes
|  | Perform Data Mapping for Conversions |  | CV /DS | CV/DS - Conversion and Design Processes
|  | Create Technical Specifications for Conversions |  | CV /DS | CV/DS - Conversion and Design Processes
|  | Design Conversions Complete |  | CV /DS | CV/DS - Conversion and Design Processes
| Design Interfaces |  |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Review/Update Functional Specifications for Interfaces |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Define Interface Detail for Project Plan |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Perform Data Mapping for Interfaces |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Create/Update Technical Specifications for Interfaces |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Design Interfaces Complete |  | DS/IM | DS/IM - Design and Implementation Processes
| Design Reports |  |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Review/Update Functional Specifications for Reports |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Define Report Detail for Project Plan |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Create/Update Technical Specifications for Reports |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Design Reports Complete |  | DS/IM | DS/IM - Design and Implementation Processes
| Design Workflow |  |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Review/Update Functional Specifications for Workflow |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Define Workflow Detail for Project Plan |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Create/Update Technical Specifications for Workflow |  | DS/IM | DS/IM - Design and Implementation Processes
|  | Design Workflow Complete |  | DS/IM | DS/IM - Design and Implementation Processes
| Design Application Security |  |  | B.MC.050.1 | Define Application Setups
|  | Review/Update Functional Specifications for Application Security |  | B.MC.050.1 | Define Application Setups
|  | Define Application Security Detail for Project Plan |  | B.MC.050.1 | Define Application Setups
|  | Create/Update Detailed Specifications for Application Security |  | B.MC.050.1 | Define Application Setups
|  | Design Application Security Complete |  | B.MC.050.1 | Define Application Setups
| Design Content Management Process |  |  | DS | DS - Design Process
|  | Define Content Management Process Detail for Project Plan |  | DS | DS - Design Process
|  | Create/Update Detailed Specifications for Content Management Process |  | DS | DS - Design Process
|  | Design Content Management Process Complete |  | DS | DS - Design Process
| Design Graphical Style for Web |  |  | DS | DS - Design Process
|  | Brainstorm Design Ideas |  | DS | DS - Design Process
|  | Prepare Design Elements |  | DS | DS - Design Process
|  | Rank and Select Design Elements |  | DS | DS - Design Process
|  | Design Graphical Style for Web Complete |  | DS | DS - Design Process
| Design Information Architecture |  |  | DS | DS - Design Process
|  | Review/Update Functional Specifications for Information Architecture |  | DS | DS - Design Process
|  | Define Information Architecture Detail for Project Plan |  | DS | DS - Design Process
|  | Create/Update Detailed Specifications for Information Architecture |  | DS | DS - Design Process
|  | Design Information Architecture Complete |  | DS | DS - Design Process
| Design Web Integration |  |  | DS | DS - Design Process
|  | Review/Update Functional Specifications for Web Integration |  | DS | DS - Design Process
|  | Define Web Integration Detail for Project Plan |  | DS | DS - Design Process
|  | Create/Update Technical Specifications for Web Integration |  | DS | DS - Design Process
|  | Design Web Integration Complete |  | DS | DS - Design Process
| Design System Security |  |  | TA.090 | Develop Security and Control Strategy
|  | Review/Update Functional Specifications for System Security |  | RD.055 | Review Supplemental Requirements
|  | Define System Security Detail for Project Plan |  | RD.055 | Review Supplemental Requirements
|  | Create/Update Detailed Specifications for System Security |  | RD.055 | Review Supplemental Requirements
|  | Design System Security Complete |  | RD.055 | Review Supplemental Requirements
| Create Help Desk / Knowledge Base Plan |  |  | TS.040 | Design Production Support Infrastructure
|  | Review Help Desk / Knowledge Base Approach |  | TS.040 | Design Production Support Infrastructure
|  | Determine Help Desk / Knowledge Base Requirements |  | TS.040 | Design Production Support Infrastructure
|  | Draft Help Desk / Knowledge Base Plan |  | TS.040 | Design Production Support Infrastructure
|  | Finalize and Document Help Desk / Knowledge Base Plan |  | TS.040 | Design Production Support Infrastructure
|  | Create Help Desk / Knowledge Base Plan Complete |  | TS.040 | Design Production Support Infrastructure
| Create Test Plans |  |  | TE | TE - Testing Process
|  | Create Unit Test Plan |  | TE | TE - Testing Process
|  | Create Integration Test Plan |  | TE | TE - Testing Process
|  | Create System Test Plan |  | TE | TE - Testing Process
|  | Create User Test Plan |  | TE | TE - Testing Process
|  | Create Parallel Test Plan |  | TE | TE - Testing Process
|  | Create Performance Test Plan |  | TE | TE - Testing Process
|  | Create Benchmark Test Plan |  | TE | TE - Testing Process
|  | Create Regression Test Plan |  | TE | TE - Testing Process
|  | Create Usability Test Plan |  | TE | TE - Testing Process
|  | Create Stress / Load Test Plan |  | TE | TE - Testing Process
|  | Create Technical Architecture Test Plan |  | TE | TE - Testing Process
|  | Create Test Plans Complete |  | TE | TE - Testing Process
| Design End-User Training |  |  | C.ACT.DEUT | Design End-User Training
|  | Review/Update Functional Specifications for End-User Training |  | C.ACT.DEUT | Design End-User Training
|  | Define End-User Training Detail for Project Plan |  | C.ACT.DEUT | Design End-User Training
|  | Create Detailed Specifications for End-User Training |  | C.ACT.DEUT | Design End-User Training
|  | Design End-User Training Complete |  | C.ACT.DEUT | Design End-User Training
| Create Baseline Project Plan |  |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Develop Baseline Project Plan |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Create Baseline Project Plan Complete |  | PS | OUM Manage Focus Area - Project Execution and Control
| Quality Review Checkpoint - Design |  |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Deliverables |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Plan and Resources |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Processes |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Review Statement of Service and Current Scope |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Document Project Review Findings |  | PS | OUM Manage Focus Area - Project Execution and Control
|  | Quality Review Checkpoint Complete |  | PS | OUM Manage Focus Area - Project Execution and Control
| Review Configuration and Update Base Tables |  |  | B.MC.050.1 | Review Application Setups
|  | Review Configuration Decisions |  | B.MC.050.1 | Review Application Setups
|  | Review and Update Configuration and Setup of Base Tables |  | B.MC.050.1 | Review Application Setups
|  | Update Base Table Configuration and Setup Document |  | B.MC.050.1 | Review Application Setups
|  | Review Configuration and Update Base Tables Complete |  | B.MC.050.1 | Review Application Setups
| Build Comprehensive Technical Architecture |  |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Implement Production Database Changes |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Install Network Upgrades |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Install Server and Workstation Upgrades |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Implement Software Configuration Management |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Implement Performance Monitoring Upgrades |  | C.TA.150 | Define Final Platform and Network Architecture
|  | Build Comprehensive Technical Architecture Complete |  | C.TA.150 | Define Final Platform and Network Architecture
| Build Customizations |  |  | IM | IM Process
|  | Build Customizations |  | IM | IM Process
|  | Unit Test Customizations |  | IM | IM Process
|  | Build Customizations Complete |  | IM | IM Process
| Build Conversions |  |  | CV | DM Process
|  | Build Conversions |  | CV | DM Process
|  | Unit Test Conversions |  | CV | DM Process
|  | Build Conversions Complete |  | CV | DM Process
| Build Interfaces |  |  | IM | IM Process
|  | Build Interfaces |  | IM | IM Process
|  | Unit Test Interfaces |  | IM | IM Process
|  | Build Interfaces Complete |  | IM | IM Process
| Build Reports |  |  | IM | IM Process
|  | Build Reports |  | IM | IM Process
|  | Unit Test Reports |  | IM | IM Process
|  | Build Reports Complete |  | IM | IM Process
| Build Workflow |  |  | IM | IM Process
|  | Build Workflow |  | IM | IM Process
|  | Unit Test Workflow |  | IM | IM Process
|  | Build Workflow Complete |  | IM | IM Process
| Build Application Security |  |  | B.MC.010 | Define Business Data Structures
|  | Build Application Security |  | B.MC.050.1 | Define Application Setups
|  | Unit Test Application Security |  | B.MC.050.1 | Define Application Setups
|  | Build Application Security Complete |  | B.MC.050.1 | Define Application Setups
| Build Content Management Process |  |  | IM | IM Process
|  | Build Content Management Process |  | IM | IM Process
|  | Audit Content Management Process |  | IM | IM Process
|  | Build Content Management Complete |  | IM | IM Process
| Build Graphical Style for Web |  |  | IM | IM Process
|  | Prepare Final Graphic Elements |  | IM | IM Process
|  | Build Graphical Style for Web Complete |  | IM | IM Process
| Build Information Architecture |  |  | IM | IM Process
|  | Build Information Architecture |  | IM | IM Process
|  | Unit Test Information Architecture |  | IM | IM Process
|  | Build Information Architecture Complete |  | IM | IM Process
| Build Web Integration |  |  | IM | IM Process
|  | Build Site Integration |  | IM | IM Process
|  | Build Web Integration |  | IM | IM Process
|  | Unit Test Web Integration |  | IM | IM Process
|  | Build Web Integration Complete |  | IM | IM Process
| Build System Security |  |  | B.MC.010 | Define Business Data Structures
|  | Build System Security |  | B.MC.050.1 | Define Application Setups
|  | Unit Test System Security |  | B.MC.050.1 | Define Application Setups
|  | Build System Security Complete |  | B.MC.050.1 | Define Application Setups
| Create Production Support Plan |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Production Support Approach |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Determine Production Support Requirements for the New System |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Draft New Production Support Plan |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Finalize and Document New Production Support Plan |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Create Production Support Plan Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Create Disaster Recovery Plan |  |  | B.TA.050 | Review Disaster Recovery Strategy
|  | Review Disaster Recovery Approach |  | B.TA.050 | Review Disaster Recovery Strategy
|  | Determine Disaster Recovery Requirements for the New System |  | B.TA.050 | Review Disaster Recovery Strategy
|  | Draft New Disaster Recovery Plan |  | B.TA.050 | Review Disaster Recovery Strategy
|  | Finalize and Document New Disaster Recovery Plan |  | B.TA.050 | Review Disaster Recovery Strategy
|  | Create Disaster Recovery Plan Complete |  | B.TA.050 | Review Disaster Recovery Strategy
| Create Go-Live Contingency Plan |  |  | TS.020 | Define Cutover Strategy
|  | Review Go-Live Contingency Approach |  | TS.020 | Define Cutover Strategy
|  | Determine Go-Live Contingency Plan Requirements |  | TS.020 | Define Cutover Strategy
|  | Determine Go-Live Acceptance Criteria |  | TS.020 | Define Cutover Strategy
|  | Draft Go-Live Contingency Plan |  | TS.020 | Define Cutover Strategy
|  | Finalize and Document Go-Live Contingency Plan |  | TS.020 | Define Cutover Strategy
|  | Create Go-Live Contingency Plan Complete |  | TS.020 | Define Cutover Strategy
| Create Process and Procedure Documentation |  |  | DO | DO - Documentation Process
|  | Create User Process and Procedure Documentation |  | DO | DO - Documentation Process
|  | Create System Test Scripts for Process Change |  | DO | DO - Documentation Process
|  | Create Process and Procedure Documentation Complete |  | DO | DO - Documentation Process
| Perform Test Move to Production |  |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Execute Upgrade Instructions - Test Move to Production |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Execute Additional Data Conversions |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Execute Additional Manual Steps Outside of Upgrade Instructions |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Resolve Test Move to Production Issues |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Perform Test Move to Production Complete |  | C.ACT.VUPC | Validate Upgrade Process - Construction
| Perform Integration Test |  |  | TE | TE - Testing Process
|  | Create Integration Test Scripts |  | TE | TE - Testing Process
|  | Execute Integration Test |  | TE | TE - Testing Process
|  | Resolve Integration Test Issues |  | TE | TE - Testing Process
|  | Perform Integration Test Complete |  | TE | TE - Testing Process
| Quality Review Checkpoint - Build and Test |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Plan and Resources |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Processes |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Statement of Service and Current Scope |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Document Project Review Findings |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Quality Review Checkpoint Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Close Construct Phase |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Close Construct Phase |  | PEC | OUM Manage Focus Area - Project Execution and Control
Transition Phase |  |  | Transition
| Update and Finalize Configuration and Setup of Base Tables |  |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Update and Finalize Configuration and Setup of Base Tables |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Update and Finalize Base Table Configuration and Setup Document |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Freeze Base Table Setup and Configuration |  | C.ACT.VUPC | Validate Upgrade Process - Construction
|  | Update and Finalize Configuration and Setup of Base Tables Complete |  | C.ACT.VUPC | Validate Upgrade Process - Construction
| Build End-User Training |  |  | C.ACT.BEUT | Build End-User Training
|  | Build Training Environments |  | C.ACT.BEUT | Build End-User Training
|  | Build Training Materials |  | C.ACT.BEUT | Build End-User Training
|  | Prepare for Training Sessions |  | C.ACT.BEUT | Build End-User Training
|  | Unit Test End-User Training |  | C.ACT.BEUT | Build End-User Training
|  | Build End-User Training Complete |  | C.ACT.BEUT | Build End-User Training
| Perform System Test |  |  | TE | TE - Testing Process
|  | Review/Update System Test Scripts |  | TE | TE - Testing Process
|  | Identify and Train Users to Participate in System Test |  | TE | TE - Testing Process
|  | Execute System Test |  | TE | TE - Testing Process
|  | Resolve System Test Issues |  | TE | TE - Testing Process
|  | Perform System Test Complete |  | TE | TE - Testing Process
| Quality Review Checkpoint - System Test |  |  | TE | TE - Testing Process
|  | Review Project Deliverables |  | TE | TE - Testing Process
|  | Review Project Plan and Resources |  | TE | TE - Testing Process
|  | Review Project Processes |  | TE | TE - Testing Process
|  | Review Statement of Service and Current Scope |  | TE | TE - Testing Process
|  | Document Project Review Findings |  | TE | TE - Testing Process
|  | Quality Review Checkpoint Complete |  | TE | TE - Testing Process
| Create Move to Production Plan |  |  | TS.054 | Perform Pre-Upgrade Steps
|  | Review Move to Production Approach and Test Move to Production Plan |  | TS.054 | Perform Pre-Upgrade Steps
|  | Determine Move to Production Requirements |  | TS.054 | Perform Pre-Upgrade Steps
|  | Draft Move to Production Plan |  | TS.054 | Perform Pre-Upgrade Steps
|  | Document and Finalize Move to Production Plan |  | TS.054 | Perform Pre-Upgrade Steps
|  | Create Move to Production Plan Complete |  | TS.054 | Perform Pre-Upgrade Steps
| Perform User Test |  |  | TE | TE - Testing Process
|  | Review/Update User Test Scripts |  | TE | TE - Testing Process
|  | Identify and Train Users to Participate in User Test |  | TE | TE - Testing Process
|  | Execute User Test |  | TE | TE - Testing Process
|  | Resolve User Test Issues |  | TE | TE - Testing Process
|  | Perform User Test Complete |  | TE | TE - Testing Process
| Perform Parallel Test |  |  | TE | TE - Testing Process
|  | Review/Update Parallel Test Scripts |  | TE | TE - Testing Process
|  | Identify and Train End Users to Participate in Parallel Test |  | TE | TE - Testing Process
|  | Prepare Environment for Parallel Test |  | TE | TE - Testing Process
|  | Execute Parallel Test |  | TE | TE - Testing Process
|  | Resolve Parallel Test Issues |  | TE | TE - Testing Process
|  | Perform Parallel Test Complete |  | TE | TE - Testing Process
| Perform Stress/Load Test |  |  | TE | TE - Testing Process
|  | Create Stress/Load Test Scripts |  | TE | TE - Testing Process
|  | Identify and Train End Users to Participate in Stress/Load Test |  | TE | TE - Testing Process
|  | Execute Stress/Load Test |  | TE | TE - Testing Process
|  | Resolve Stress/Load Test Issues |  | TE | TE - Testing Process
|  | Perform Stress/Load Test Complete |  | TE | TE - Testing Process
| Test Disaster Recovery Plan |  |  | TE | TE - Testing Process
|  | Create Disaster Recovery Scenarios |  | TE | TE - Testing Process
|  | Identify and Train Users to Participate in Disaster Recovery Test |  | TE | TE - Testing Process
|  | Test Disaster Recovery Plan |  | TE | TE - Testing Process
|  | Resolve Disaster Recovery Test Issues |  | TE | TE - Testing Process
|  | Test Disaster Recovery Plans Complete |  | TE | TE - Testing Process
| Perform Technical Architecture Test |  |  | TE | TE - Testing Process
|  | Create Technical Architecture Test Scripts |  | TE | TE - Testing Process
|  | Execute Technical Architecture Test |  | TE | TE - Testing Process
|  | Resolve Technical Architecture Test Issues |  | TE | TE - Testing Process
|  | Perform Technical Architecture Test Complete |  | TE | TE - Testing Process
| Perform Benchmark Test |  |  | TE | TE - Testing Process
|  | Create Benchmark Test Scripts |  | TE | TE - Testing Process
|  | Execute Benchmark Test |  | TE | TE - Testing Process
|  | Resolve Benchmark Test Issues |  | TE | TE - Testing Process
|  | Perform Benchmark Test Complete |  | TE | TE - Testing Process
| Perform Performance Test |  |  | TE | TE - Testing Process
|  | Create Performance Test Scripts |  | TE | TE - Testing Process
|  | Execute Performance Test |  | TE | TE - Testing Process
|  | Resolve Performance Test Issues |  | TE | TE - Testing Process
|  | Perform Performance Test Complete |  | TE | TE - Testing Process
| Perform Usability Test |  |  | TE | TE - Testing Process
|  | Create Usability Test Scripts |  | TE | TE - Testing Process
|  | Execute Usability Test |  | TE | TE - Testing Process
|  | Resolve Usability Test Issues |  | TE | TE - Testing Process
|  | Perform Usability Test Complete |  | TE | TE - Testing Process
| Prepare Production Environment |  |  | TS.055 | Upgrade Production Environment
|  | Establish Production Environment |  | TS.055 | Upgrade Production Environment
|  | Establish Backup and Restore Processes |  | B.TA.080 | Review Backup and Recovery Strategy
|  | Migrate/Establish Processing Schedules |  | C.TA.100 | Define System Management Procedures
|  | Migrate/Set Up Security |  | TS.054 | Implement Production Support Infrastructure
|  | Initiate Help Desk / Knowledge Base |  | TS.054 | Implement Production Support Infrastructure
|  | Evaluate Production Environment Readiness |  | D.TS.058 | Verify Production Readiness
|  | Prepare Production Environment Complete |  | TS.056 | Perform Post-Upgrade Steps
| Evaluate Readiness |  |  | D.TS.058 | Verify Production Readiness
|  | Revisit and Evaluate Go-Live Acceptance Criteria |  | D.TS.058 | Verify Production Readiness
|  | Evaluate Customer Readiness |  | D.TS.058 | Verify Production Readiness
|  | Assess Decision to Go Live |  | D.TS.058 | Verify Production Readiness
|  | Evaluate Readiness Complete |  | D.TS.058 | Verify Production Readiness
| Quality Review Checkpoint - Production Readiness |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Plan and Resources |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Processes |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Statement of Service and Current Scope |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Document Project Review Findings |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Quality Review Checkpoint Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Close Transition Phase |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Close Transition Phase |  | PEC | OUM Manage Focus Area - Project Execution and Control
Deploy Phase |  |  | Production
| Delta Train End Users |  |  | C.ACT.TEUT | Train End Users - Transition
|  | Conduct Training Sessions |  | C.ACT.TEUT | Train End Users - Transition
|  | Evaluate User Proficiency |  | C.ACT.TEUT | Train End Users - Transition
|  | Delta Train End Users Complete |  | C.ACT.TEUT | Train End Users - Transition
| Perform Move to Production |  |  | TS.055 | Upgrade Production Environment
|  | Execute Move to Production Plan |  | TS.055 | Upgrade Production Environment
|  | Perform Move to Production Complete |  | TS.055 | Upgrade Production Environment
| Provide Post-Project Support |  |  | PS | PS - Operations and Support Process
|  | Provide End-User Support |  | PS | PS - Operations and Support Process
|  | Provide Technical Support |  | PS | PS - Operations and Support Process
|  | Transition Support Responsibility |  | PS | PS - Operations and Support Process
|  | Provide Post-Project Support Complete |  | PS | PS - Operations and Support Process
| Archive Project Diary |  |  | PEC | OUM Manage Focus Area - Project Execution and Control - Project Execution and Control
|  | Review Project Documentation Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Finalize Project Documentation Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Archive Project Documentation Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Archive Project Diary Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Conduct Project Acceptance Review |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Objectives of Project |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Identify Outstanding Business Issues |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Prepare for Project Acceptance Review |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Conduct Project Acceptance Review and Transition Operational Responsibility |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Certify System |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Conduct Project Acceptance Review Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Quality Review Checkpoint - Deploy |  |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Deliverables |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Plan and Resources |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Project Processes |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Review Statement of Service and Current Scope |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Document Project Review Findings |  | PEC | OUM Manage Focus Area - Project Execution and Control
|  | Quality Review Checkpoint Complete |  | PEC | OUM Manage Focus Area - Project Execution and Control
| Close Deploy Phase |  |  | PC | OUM Manage Focus Area - Project Execution and Control
Close Deploy Phase