## Introduction
This mapping spreadsheet is intended to provide the user the ability to view OUM from either a legacy perspective of Hyperion BPM Workbench to OUM 5.1, or from the OUM 5.1 implmentation perspective of OUM to Hyperion BPM Workbench.
IMPORTANT NOTE: One needs to view the "OUM_TO_Hyperion_TASK_Mapping" worksheet in order to see all tasks that have been identified as candidate tasks when using OUM to implement a Hyperion based solution.
Usage tip: The order of the worksheets in this mapping spreadsheet have been ordered in such a way that a user with Hyperion BPM Workbench knowledge and experience could first understand how Hyperion BPM Workbench maps into OUM, and then builds the users understanding of OUM from a phase, to process, to task perspective of OUM. The important point is that one should use the last worksheet "OUM_To_Hyperion_TASK_Mapping" worksheet when attempting to finalize which tasks are appropriate for a particular engagement. It should be further noted that just because a task is flagged for Hyperion does not mean it should be executed for all Hyperion engagements. The review of OUM for Hyperion applicability covers the smaller Hyperion engagements to the largest...The mapping represents the superset of all possible tasks that one might consider for an Hyperion engagement...Use only those tasks that make sense for your engagement.
Usage tips: Please note that multiple of the worksheets employ use of Excel's column filtering. This enables a user to filter the rows displayed to a specific item you are looking for. Setting a column filter to (All) turns off the filter for a column, and also note that multiple column filters can be utilized on the same worksheet to create a dimensional viewing effect that hones in on the answer set that is applicable to your specific needs. The drop-down arrow for the filter changes color from black to blue when the filter is on. Lastly all the worksheets have been sized and formatted for printing if desired.
Index to worksheets in Hyperion Mapping spreadsheet:
INTRODUCTION: This worksheet
Hyperion_BPM_To_OUM_Mapping: Worksheet that provides the Hyperion BPM Workbench to OUM perspective
OUM_To_Hyperion_PHASE_Mapping: Worksheet that provides a OUM to Hyperion BPM Workbench phase component level perspective
OUM_To_Hyperion_PROCESS_Mapping: Worksheet that provides a OUM to Hyperion BPM Workbench process component level perspective
OUM_To_Hyperion_TASK_Mapping: Worksheet that provides a OUM to Hyperion BPM Workbench task/task step component level perspective. Column "L" (BPM Applic.) of this worksheet indicates whether a task has possible applicability for a Hyperion engagement

## Hyperion_BPM_To_OUM_Mapping
BPM Focus Area | BPM Phase | BPM Process | BPM Activity | BPM Task | BPM Task Steps | Mapping => (Notes) | OUM Focus Area | OUM Phase | OUM Process | OUM Activity | OUM Tasks
Envision | Envision the Solution | Identify the Opportunity |  | Create & Win (Create Opportunity Plan) |  |  | Envision
Envision | Envision the Solution | Identify the Opportunity | Parnter for Success |  | Charter Meetings |  | Envision
Envision | Envision the Solution | Identify the Opportunity | Parnter for Success |  | Rules of Engagement |  | Envision
Envision | Envision the Solution | Identify the Opportunity | Parnter for Success |  | Defining Checkpoints |  | Envision
Envision | Envision the Solution | Identify the Opportunity | Parnter for Success | Engage a GSI (Hyperion Global Systems Integrator Request Form) |  |  | N/A
Envision | Envision the Solution | Identify the Opportunity | Parnter for Success |  | Engage a Strategic Partner Manager |  | Envision
Envision | Envision the Solution | Architect the Solution |  | Business Requirements | Discovery Survey | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) + RA.27.1-Optional in some cases, the pre-sales consultants have done first iteration of this task | Implementation | A-Inception + B-Elaboration | [RA] Req. Analysis + [RD] Business Requirements + [AN] Analysis | B.ACT.ADE + A.ACT.GBRI + A.ACT.SKSD | RD.001 + RA.015 + RA.023.1 + RA.023.1 + RA.27.1 + RA.040 + AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Architect the Solution |  | BluePrint |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration | [RA] Req. Analysis + [RD] Business Requirements + [AN] Analysis | A.ACT.GBRI + B.ACT.ADE + A.ACT.SKSD | RA.015 + RA.023.1 + RA.027.1 + RA.040 + AN.020.1 + AN.025.1 + AN.050.1 +
Envision | Envision the Solution | Architect the Solution |  | BPMR (BPMR Overview Document) |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration | [RD] Business Requirements + [AN] Analysis | B.ACT.ADE + A.ACT.SKSD | RA.015 + RA.023.1 + RA.027.1 + RA.040 + AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Architect the Solution | Demo to Win | Demo Planning |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration | [RA] Req. Analysis + [RD] Business Requirements + [AN] Analysis | B.ACT.ADE + A.ACT.CCP | RA.030 + AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Architect the Solution | Demo to Win | Demo Preparation |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | B - Elaboration | [RA] Req. Analysis + [RD] Business Requirements + [AN] Analysis | B.ACT.ADE + A.ACT.CCP | RA.030 + AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Architect the Solution | Demo to Win | Demo Practise |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration | [RA] Req. Analysis + [RD] Business Requirements + [AN] Analysis | A.ACT.CCP + B.ACT.ADE | RA.030+ AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Architect the Solution | Sales Cycle Best Practices |  |  | Optional + Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | B - Elaboration | [RD] Business Requirements + [AN] Analysis | B.ACT.ADE | AN.020.1 + AN.025.1 + AN.050.1
Envision | Envision the Solution | Propose the Solution | Partner Checkpoints | Develop Service Option (Hyperion Only, Blended, etc.) |  |  | Implementation
Envision | Envision the Solution | Propose the Solution | Estimating Tools (Consulting Estimate) |  |  |  | Implementation
Envision | Envision the Solution | Propose the Solution | Proof of Concept (Demo) | Gather requirements for customization |  |  | Implementation | A-Inception | [RD] Business Requirements | A.ACT.GSP | RD.070
Envision | Envision the Solution | Propose the Solution | Proof of Concept (Demo) | Obtain client data |  |  | Implementation
Envision | Envision the Solution | Propose the Solution | Proof of Concept (Demo) | Construct the solution |  |  | Implementation
Envision | Envision the Solution | Propose the Solution | Proof of Concept (Demo) | Deliver the actual demo |  |  | Implementation
Envision | Envision the Solution | Propose the Solution | RFP | Consulting Service Proposal |  |  | Implementation | A-Inception | [RD] Business Requirements | A.ACT.GR | RD.045.1
Envision | Envision the Solution | Post Win Success | Hand Off | Sales to Service Handoff Meeting |  |  | Implementation
Envision | Envision the Solution | Post Win Success | Hand Off | SOW |  |  | Implementation
Envision | Envision the Solution | Post Win Success | Partner Charter Meeting | Opportunity Call Plan |  |  | Implementation
Envision | Envision the Solution | Post Win Success | Partner Charter Meeting | Partner Go To Market Strategy |  |  | Implementation
Envision | Envision the Solution | Post Win Success | Partner Charter Meeting | Sales Cycle Check List |  |  | Implementation
Manage | Manage for Success | Plan the Work | Define Work | Build the Workplan (Workplan) |  |  | Implementation | A - Inception
Manage | Manage for Success | Plan the Work | Build the Workplan |  |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Workplan | Project Workplan |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Issues | Project Status Report/Issues Log |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Scope |  |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Communication | Project Status Report |  |  | Implementation | B-Elaboration + C-Construction + D-Transition | [AP] Adoption & Learning | B.ACT.POA + C.ACT.PUT | AP.080.1 + AP.080.2 + AP.080.3
Manage | Manage for Success | Work the Plan | Manage Risk | Risk Evaluation |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Risk | Risk Identification |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Risk | Risk Mitigation |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Documents | Preparation. |  |  | Implementation | A-Inception + B-Elaboration | [DO] Documentation] |  | DO.010
Manage | Manage for Success | Work the Plan | Manage Documents | Initial Document Creation. |  |  | Implementation | A-Inception + B-Elaboration | [DO] Documentation] |  | DO.020
Manage | Manage for Success | Work the Plan | Manage Documents | Feedback and Modification |  |  | Implementation | A-Inception + B-Elaboration | [DO] Documentation] |  | DO.020
Manage | Manage for Success | Work the Plan | Manage Documents | Approval |  |  | Implementation | A-Inception + B-Elaboration | [DO] Documentation] |  | DO.020
Manage | Manage for Success | Work the Plan | Manage Quality |  |  |  | Implementation | A - Inception
Manage | Manage for Success | Work the Plan | Manage Metrics |  |  |  | Implementation | A - Inception
Build for Success | Analysis |  |  |  |  | OUM tasks mapped here align to the Analysis phase only | Implementation | B-Elaboration | [CV] Data Acquistion and Conversion |  | CV.027.1
Build for Success | Analysis |  | Application Requirements | Scope & Charter Document | Elicitation | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis | B.ACT.DUC, B.ACT.CS + B.ACT.GBRE + C.ACT.ADC + C.ACT.FR | RD.020 + RD.045.2 + RD.045.3 + RD.140.2 + RA.023.2 + RA.024.1 + RA.027.2 + RA.050 + AN.025.2
Build for Success | Analysis |  | Application Requirements | Scope & Charter Document | Validation | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration + C-Construction | [RA] Requirements Analysis + [RD] Business Requirements | A.ACT.GR + B.ACT.DUC + B.ACT.CS + C.ACT.ADC + C.ACT.FR | RD.045.2 + RD.045.3 + RD.140.2 + RA.023.2 + RA.024.1 + RA.27.2 + AN.025.2
Build for Success | Analysis |  | Application Requirements | Scope & Charter Document | Specification | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis | A.ACT.CR + A.ACT.GBR + B.ACT.DUC + B.ACT.CS + C.ACT.ADC + C.ACT.FR | RD.012 + RD.045.2 + RD.045.3 + RD.140.1 + RA.023.2 + RA.024.1 + RA.027.2 + AN.025.2
Build for Success | Analysis |  | Application Requirements | Scope & Charter Document | Verification | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) | Implementation | A-Inception + B-Elaboration + C-Construction | [RA] Requirements Analysis + [RD] Business Requirements | A.ACT.CR + A.ACT.GR + B.ACT.DUC + B.ACT.CS + C.ACT.ADC + C.ACT.FR | RD.045.2 + RD.045.3 + RD.140.2 + RD.150.1 + RA.028.1 + RA.023.2 + RA.024.1 + RA.027.2 + AN.025.2
Build for Success | Analysis |  | Solution Requirements | Conceptual Systems Design | Technical Architecture | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules) + IM.005->Sales cycle/SC demo + RA.065.1 - This task includes work defined in RA.045...Commonly referred to as "System Preferences" in DRM Hyperion (e.g. restricted characters in node name) + Console Configuration (# of web servers, web farm, data traffic management)…System preferences = functional control, and console configuration = system control | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis + [TA] Technical Architecture [IM] Implementation | A.ACT.CCP + A.ACT.GBRI + A.ACT.GR + A.ACT.GSP + B.ACT.BSA + B.ACT.GBRE + B.ACT.SSC + B.ACT.DI + C.ACT.ADC | RD.065 + RA.035 + RA.055.1 + RA.060 + RA.065.1 + RD.130.1 + TA.010 + TA.020 + TA.050 + TA.060 + TA.070 + TA.080 + TA.090 + AN.020.2 + DO.080 + IM.005
Build for Success | Analysis |  | Solution Requirements | Conceptual Systems Design | User Interaction |  | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis + [TA] Technical Architecture | A.ACT.GSP + B.ACT.DI + C.ACT.ADC | TA.010 + TA.040 + TA.050 + TA.060 + TA.070 + TA.080 + TA.090 + AN.020.2 + DO.080
Build for Success | Analysis |  | Solution Requirements | Conceptual Systems Design | Interfaces |  | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis + [TA] Technical Architecture | A.ACT.GSP + B.ACT.DI + C.ACT.ADC | TA.010 + TA.040 + TA.050 + TA.060 + TA.070 + TA.080 + TA.090 + AN.020.2 + DO.080
Build for Success | Analysis |  | Solution Requirements | Conceptual Systems Design | Reports |  | Implementation | A-Inception + B-Elaboration + C-Construction | [RD] Business Requirements + [RA] Requirements Analysis + [TA] Technical Architecture | A.ACT.GSP + B.ACT.DI + C.ACT.ADC | TA.010 + TA.040 + TA.050 + TA.060 + TA.070 + TA.080 + TA.090 + AN.020.2 + DO.080
Build for Success | Analysis | Project Strategies |  | Testing Strategy (document) |  | For Hyperion engagements this task and all the other tasks within the B.ACT.ADE activity are performed as one (I.e.activity) | Implementation | B - Elaboration | [TE] Testing + [CV] Data Acquisition and Conversion + [DS] Design + [PF] Perf. Mgt. | A.ACT.GSP + B.ACT.DE + B.ACT.PPM + B.ACT.DPS | DS.016 + DS.017.1 + DS.020.1 + TE.005.1 + TE.005.2 + TE.010 + PT.020
Build for Success | Analysis | Project Strategies |  | Implementation Strategy (document) |  | For Hyperion engagements this is typically performed during the sales cycle and documened in the SOW/scoping document - This task is seen more as a touchpoint to this work by the sales force | Implementation | B - Elaboration | [IM] Impementation + [TE] Testing + [DS] Design + [TS] Transition | A.ACT.GSP + B.ACT.DPS + B.ACT.ADE + B.ACT.DPS + B.ACT.DPS + C.ACT.PT | DS.005 + DS.016 + DS.017.1 + DS.020.1 + TA.160 + TS.010
Build for Success | Analysis | Project Strategies |  | Training Strategy (document) |  |  | Implementation | B - Elaboration | [AP] Adoption and Learning + [DS] Design | A.ACT.PPJT + B.ACT.ADE | AP.040 + AP.050 + DS.016 + DS.017.1 + DS.020.1
Build for Success | Analysis | Project Strategies |  | Data Conversion Strategy (document) |  |  | Implementation | A-Inception + B-Elaboration | [CV} Data Acquistion and Conversion + [TE] Testing + [DS] Design | A.ACT.GSP + B.ACT.ADE | CV.010 + CV.020 + CV.030.1 + CV.035.1 + CV.040.1 + DS.016 + DS.017.1 + DS.020.1
Build for Success | Analysis | Exit Gate |  | Acceptance Criteria |  | Finalizing, which may be just a check | Implementation | B - Elaboration | [RD] Business Requirements + [AN] Analysis | B.ACT.CS + C.ACT.ADC | AN.050.2
Build for Success | Analysis | Exit Gate |  | Plan Project |  | Finalizing, which may be just a check | Implementation | B - Elaboration | [AN] Analysis | C.ACT.ADC | AN.050.2
Build for Success | Analysis | Exit Gate |  | Approval to Proceed | Client sign-off | Finalizing, which may be just a check | Implementation | B - Elaboration | [RD] Business Requirements + [AN] Analysis | B.ACT.CS + C.ACT.ADC | RD.150.2 + AN.050.2
Build for Success | Design |  | Design Preparation | Architectural Foundation |  |  | Implementation | B-Elaboration + C-Construction | [DS] Design + [TA] Technical Architecture | B.ACT.DI + B.ACT.BSA + C.ACT.ADC | DS.010.1 + DS.030.1 + TA.030
Build for Success | Design |  | Design Preparation | Common Elements |  |  | Implementation | B-Elaboration + C-Construction | [DS] Design | B.ACT.ADE | DS.030.1 + DS.030.2
Build for Success | Design |  | Design Preparation | Standards and Guidelines |  |  | Implementation | C - Construction | [DS] Design | B.ACT.ADE | DS.015
Build for Success | Design |  | Application Design | Consolidation (App design) |  | Not designing trandional relational DB, but rather desiging cubes for multi-dimensional | Implementation | B-Elaboration + C-Construction | [DS] Design + [IM] Implementation | B.ACT.ADE + B.ACT.DP | DS.060.1 + DS.060.2 + IM.060.1
Build for Success | Design |  | Application Design | Enterprise Planning (App design) |  | Not designing trandional relational DB, but rather desiging cubes for multi-dimensional | Implementation | B-Elaboration + C-Construction | [DS] Design + [IM] Implementation | B.ACT.ADE + B.ACT.DP | DS.060.1 + DS.060.2 + IM.060.1
Build for Success | Design |  | Application Design | Management Reporting (App design) |  | Not designing trandional relational DB, but rather desiging cubes for multi-dimensional | Implementation | B-Elaboration + C-Construction | [DS] Design + [IM] Implementation | B.ACT.ADE + B.ACT.DP | DS.060.1 + DS.060.2 + IM.060.1
Build for Success | Design |  | Application Design | Application Design Review |  | Activity level + IM.060.2-Optional when done, for Hyperion, this taks is typically executed at an activity level | Implementation | C - Construction | [DS] Design + [IM] Implementation | B.ACT.DP + C.ACT.ADC | DS.050.2 + DS.060.2 + IM.060.1 + IM.060.2
Build for Success | Design | Solution Design | Integration Architecture | Technical Architecture | Create the Technical Architecture Design Document | When customizations exist (I.e. non Oracle/Hyperion tech) | Implementation | C - Construction | [DS] Design + [TA] Technical Architecture + [DO] Documentation | C.ACT.PD + B.ACT.ADE | DO.080 + DS.040.1 + DS.010.2 + DS.040.2
Build for Success | Design | Solution Design | Integration Architecture | Solution Design Review | Create Solution Design Document | DS.017.2: Optional - In most cases not necessary for another iteration of this task…done in .1 version + IM.060.2 - Optional, when done for Hyperion this task is typically executed at an activity level | Implementation | C - Construction | [DS] Design + [IM] Implementation | B.ACT.ADE + C.ACT.ADC | DS.050.1 + DS.017.2 + DS.020.2 + IM.060.2
Build for Success | Design | Solution Design | Configure Environment |  |  | Activity level | Implementation | B-Elaboration + C-Construction | [DS] Design + [IM] Implementation | B.ACT.PEE + B.ACT.PSTE + C.ACT.PEC | TE.070.1 + IM.007.1 + IM.007.2
Build for Success | Design | Executive Planning |  | Testing Plan |  | Clients would often do this | Implementation | B-Elaboration + C-Construction | [DS] Design + [TE] Testing + [CV] Data Acquisition and Conversion | B.ACT.PPM + B.ACT.DPS + B.ACT.DTP + B.ACT.PSTE | CV.050.1 + PT.030 + TE.015.1 + TE.025.1 + TE.050.1 + TE.080 + TE.082
Build for Success | Design | Executive Planning |  | Implementation Plan |  |  | Implementation | C - Construction | [DS] Design + [TE] Testing + [CV] Data Acquisition and Conversion + [TS] Transition | C.ACT.PCO | TS.020
Build for Success | Design | Executive Planning |  | Training Plan |  |  | Implementation | C - Construction | [DS] Design + [TE] Testing + [CV] Data Acquisition and Conversion + [AP] Adoption and Learning | C.ACT.PUT | AP.130 + AP.140
Build for Success | Design | Executive Planning |  | Data Conversion Plan |  |  | Implementation | B-Elaboration + C-Construction | [DS] Design + [TE] Testing + [CV] Data Acquisition and Conversion | B.ACT.PACD | CV.025 + CV.050.1
Build for Success | Design | Exit Gate |  | Conference Room Pilot | S/ware demo |  | Implementation | B-Elaboration + C-Construction | [DS] Design + [IM] Implementation | B.ACT.DP | IM.010 + IM.020 + IM.040.1 + IM.085
Build for Success | Design | Exit Gate |  | Re-Plan | Project Plan updated |  | Implementation | C - Construction | [DS] Design
Build for Success | Design | Exit Gate |  | Approval to Proceed | Design Document Client sign-off |  | Implementation | C - Construction | [DS] Design
Build for Success | Construct | Build Solution | (Construct) Application |  |  | For Hyperion it is more appropriate to use term creating application versus creating database, but yes task is performed…See supp guide | Implementation | C - Construction | [IM] - Implementation | C.ACT.IS | IM.040.2
Build for Success | Construct | Build Solution | Integration - data conversion |  |  | Activity level | Implementation | B-Elaboration + C-Construction | [IM] - Implementation | C.ACT.ACDC + C.ACT.IS | CV.055.1 + CV.055.2 + CV.065.1 + IM.050 + IM.070 + IM.080
Build for Success | Construct | Build Solution | (Construct) Data Stores |  |  |  | Implementation | C - Construction | [IM] - Implementation + [CV] Data Acquisition and Conversion |  | CV.068.1
Build for Success | Construct | Build Solution | Unit Test |  |  |  | Implementation | C - Construction | [IM] - Implementation
Build for Success | Construct | Supporting Documentation |  | Create "Application Maintenance" Doc |  |  | Implementation | C - Construction | [IM] - Implementation + [DO] Documentation | C.ACT.PD + C.ACT.PT | DO.060 + TA.100
Build for Success | Construct | Supporting Documentation |  | Create "End User" Manual |  |  | Implementation | C - Construction | [IM] - Implementation + [DO] Documentation | C.ACT.PD | DO.070 + TA.100
Build for Success | Construct | Supporting Documentation |  | Create "Disaster Recovery" Doc |  |  | Implementation | C - Construction | [IM] - Implementation + [DO] Documentation | C.ACT.PD | DO.80 + TA.100
Build for Success | Construct | Implementation Planning |  | Construct "Testing" programs |  | Optional for Hyperion DRM + PT.060 - Typically managed and delivered at activity level | Implementation | B-Elaboration + C-Construction | [IM] - Implementation + [TE] - Testing + [PT] - Perf. Mgt. + [TS] Transition | B.ACT.PPM + B.ACT.PUCT + C.ACT.PCO | TE.035.1 + PT.050 + PT.060 + PT.070 + PT.080 + TS.030
Build for Success | Construct | Implementation Planning |  | Construct "Implementation" programs |  |  | Implementation | C - Construction | [IM] - Implementation + [TE] - Testing
Build for Success | Construct | Implementation Planning |  | Construct "Training" material |  |  | Implementation | C - Construction | [IM] - Implementation + [TE] - Testing + [AP] Adoption and Learning | A.ACT.PUT | AP.150
Build for Success | Construct | Implementation Planning |  | Construct "Data conversion" programs |  |  | Implementation | C - Construction | [IM] - Implementation + [TE] - Testing + [CV] Data Acquisition and Conversion
Build for Success | Construct | Exit Gate |  | Conference Room Pilot II | S/ware demo |  | Implementation | C - Construction | [IM] - Implementation
Build for Success | Construct | Exit Gate |  | Re-Plan | Project Plan updated |  | Implementation | C - Construction | [IM] - Implementation
Build for Success | Construct | Exit Gate |  | Approval to Proceed | Official approval to proceed. |  | Implementation | C - Construction | [IM] - Implementation
Build for Success | Test | Test Preparation | Automated Testing | Assess Requirement |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt
Build for Success | Test | Test Preparation | Automated Testing | Prepare Automated Testing |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt
Build for Success | Test | Test Preparation | Test Cases | Manage test cases |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt | C.ACT.PT + C.ACT.PUTC | TA.110 + TE.030.2
Build for Success | Test |  | Test Execution | Integration Testing |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C-Construction + D-Transition | [TE] Testing + [PT] Performance Mgt | B.ACT.PUTE + C.ACT.PUTC + D.ACT.CPTST | TE.030.1 + TE.030.2 + PT.100
Build for Success | Test |  | Test Execution | System Testing |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C-Construction + D-Transition | [TE] Testing + [PT] Performance Mgt + [TA] Technical Architecture | C.ACT.TI + C.PSTC + C.ACT.CSIT + C.ACT.PUCTC.ACT.CPTST | TE.040.2 + TE.070.2 + TE.100 + TA.120 + TA.130 + TA.140 + PT.100
Build for Success | Test |  | Test Execution | Acceptance Testing |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C-Construction + D-Transition | [TE] Testing + [PT] Performance Mgt | D.ACT.CPTST + D.ACT.PUAT | TE.120 + PT.100
Build for Success | Test |  | Test Execution | Regression Testing |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C-Construction + D-Transition | [TE] Testing + [PT] Performance Mgt | D.ACT.CPTST | PT.100
Build for Success | Test | Exit Gate |  | Solution Test Review |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt
Build for Success | Test | Exit Gate |  | Re-Plan |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt
Build for Success | Test | Exit Gate |  | Approval to Proceed |  | The OUM [PT] Perf Mgt Process is implicit in BPM Testing | Implementation | C - Construction | [TE] Testing + [PT] Performance Mgt
Build for Success | Implement | Implementation Preparation |  | Perform Training |  | AP.170.2 is Optional | Implementation | D - Transition | [AP] Adoption and Learning + [TS] Transition | D.ACT.TU | AP.170.2 + AP.180
Build for Success | Implement | Implementation Preparation |  | Go-Live Checkpoint |  | This could be nothing more than a checklist | Implementation | D - Transition | [TS] Transition | D.ACT.GP | TS.058
Build for Success | Implement |  | Roll-Out | Implement Solution |  |  | Implementation | D - Transition | [TS] Transition | D.ACT.GP | TS.060
Build for Success | Implement |  | Roll-Out | Monitor Solution |  |  | Implementation | D - Transition | [TS] Transition | D.ACT.GP | TS.060
Build for Success | Implement |  | Roll-Out | Transition to Support |  |  | Implementation | D - Transition | [TS] Transition | D.ACT.GP | TS.060
Build for Success | Implement | Exit Gate |  | Solution Review |  |  | Implementation | D - Transition | [TS] Transition
Build for Success | Implement | Exit Gate |  | Final Approval |  |  | Implementation | D - Transition | [TS] Transition
Build for Success | Implement | Exit Gate |  | Post Implementation Review |  |  | Implementation | D-Transition + E-Production | [TS] Transition + [PS] Operations and Support | E.ACT.EPS + E.ACT.PF | PS.010 + PS.135 + PS.140
Educate |  |  | Educate for Success |  |  |  | Implementation | D - Transition
Support |  |  | Support for Success |  |  |  | Implementation | E - Production | [PS] Operation and Support | E.ACT.EPS + E.ACT.RPP | PS.050 + PS.060
Note on I1: A phase occurs once in the WBS. Within a phase exists processes, activities, tasks, and steps
Note on J1: A process exists within Phases. A process can exist in multiple phases…Typically a process will exist in multiple phases, and if not it is usually classified as an activity
Note on K1: An activity exists within a phase, and is unique to a phase. An activity contains two or more tasks. A activity is never repeated in the entire method. An activity is made up of tasks that have sub work products/deliverables that are aggregated into the activity work product or deliverable. It is not unusual to see work products associated to activities as key deliverables in a statement of work. An activity resides in a phase, and can have tasks that are from different processes
Note on L1: A task is a specific unit of work that produces a specific work product. Tasks either reside in a process or an activity Steps within a task are simply a list of work that has be performed in order for a task to be completed…There is no stated deliverable at this level.

## OUM_TO_Hyperion PHASE Mapping
OUM PHASES | OUM Phase Description | Mapping=> | Hyperion Phases
A - Inception | The overriding goal of the Inception Phase is to achieve concurrence among all stakeholders on the life cycle objectives for the project. Therefore, the Inception phase delivers the Life-Cycle Objectives Milestone. The Inception phase is significant primarily for new development efforts, in which significant businesses and requirements risks must be addressed before the project can proceed. | Maps to … | Manage for success
B - Elaboration | The goal of the Elaboration Phase is to baseline the architecture of the system to provide a stable basis for the design and implementation effort in the Construction phase. The Elaboration phase delivers the Life-Cycle Architecture Milestone. The architecture evolves from the most significant requirements -- those that have a great impact on the architecture of the system -- and an assessment of risk. The stability of the architecture is evaluated through one or more architectural prototypes. | Maps to … | Build for Success/Analysis
C - Construction | The goal of the Construction Phase is to clarify the remaining requirements and complete the development of the system based upon the baseline architecture. In one sense, the Construction phase is a manufacturing process, where emphasis is placed on managing resources and controlling operations to optimize costs, schedules, and quality. | Maps to … | Build for Success/Design & Construction & Test
D - Transition | The focus of the Transition Phase is to ensure that the work product is tested systematically and is available for end users. | Maps to … | Build for Success/Implement + Educate for Success
E - Production | The Production phase focuses on operating the newly developed system and supporting the users. | Maps to … | Support The Solution

## OUM_to_Hyperion_PROCESS_Mapping
OUM Processes | OUM Process Description | Mapping=> | Hyperion Processes
[RD] Business Requirements | In the Business Requirements process, the business requirements for the proposed system or new enhancements are identified, refined and prioritized by a tightly integrated team of empowered ambassador users and experienced analysts. | Maps To… | Envision the Solution\Architect the Solution\Business Requirements + Build for Success\Analysis\Application Requirements + Build for Success\Analysis\Solution Requirements
[RA] Requirements Analysis | In the Requirements Analysis process, the requirements captured during the Requirements Definition are analyzed. They are refined and structured via a Use Case Model in order to establish a more precise understanding of the requirements. The Use Case Model is used as the basis for the solution development. This process helps provide structure and shape to the entire solution. The Use Case Model is used to document in detail the requirements of the system in a format that both customer and the developers of the system can easily understand. | Maps To… | Build for Success\Analysis\Application Requirements+ Build for Success\Analysis\Solutions Requiremnets
[AN] Analysis | In the Analysis process, the captured requirements are analyzed by refining and structuring them via a conceptual object model, called the Analysis Model. The Analysis Model provides a more precise understanding of the requirements and provides details on the internals of the system. | Maps To… | Build for Success\Analysis
[DS] Design | In the Design process, the system is shaped and formed to meet all functional and non-functional requirements. This form is based on the architecture created and stabilized during the Analysis process. Thus, the work products produced during Analysis are an important input into this process. | Maps To… | Build for Success\Design
[IM] Implementation | Through a number of steps, mostly iterative, the final application is developed within the Implementation process. The results from the Design process are used to implement the system in terms of source code for components, scripts, executables etc. Developer testing is also implemented on software components. | Maps To… | Build for Success\Construct
[TE] Testing | The Testing process is an integrated approach to testing the quality and conformance of all elements of the new system. Therefore, it is closely related to the review tasks in the Quality Management (QM) process of PJM and to the definition and refinement of requirements in the Business Requirements process. It addresses mainly functional testing. | Maps To… | Build for Success\Test + Build for Success\Analysis\Project Strategies\Testing + Build for Success\Design\Executive Planning\Testing + Build for Success\Construct\Implementation Planning\Testing
[PT] Performance Management | The objective of the Performance Management process is to proactively define, construct, and execute an effective approach to managing performance throughout the project implementation life cycle in order to ensure that the performance of the system or system components meet the user's requirements and expectations when the system is implemented. | Maps To… | Implicit in Testing, see above
[TA] Technical Architecture | The Technical Architecture process specifies elements of the technical infrastructure of the development project. It assumes that the business already has an information system strategy and that these elements fit within that strategy. | Maps To… | Build for Success\Analysis\Solution Requirements\Technical Architecture + Build for Success\Design\Design Preparation\Architectural Foundation + Build for Success\Design\solution Design\Technical Architecture
[CV] Data Acquistion and Conversion | In the Data Conversion process the data that is required to be converted is explicitly defined, along with its sources. This data may be needed for system testing, training, and acceptance testing as well as for production. In some cases, it is beneficial to convert (some) data at earlier stages to provide as realistic as possible reviews of the components during the development iterations. On the other hand, this may be difficult, as the actual Database Design for the new system is not yet stabilized. | Maps To… | Build for Success/Analysis/Project Strategies/Data Conversion + Build for Success/Design/Executive Planning/Data Coversion + Build for Success/Construct/Build Solution/Data Stores + Build for Success/Construct/Implementation Planning/Data Conversion
[DO] Documentation | Quality documentation is a key factor in supporting the transition to production, achieving user acceptance, and maintaining the ongoing business process. | Maps To… | Addressed Indirectly in tasks - "Scope & Charter Document" is developed after Analysis and "Detailed Design Document" is prepared after the Design process in Build for Success phase. Also covered in "Build for Success\Construct\Supporting Documentation"
[AP] Adoption and Learning | Adoption and Learning focuses on the use and acceptance of new applications by all users and the optimization of organizational performance. Inherent in every technology change is the opportunity to become a stronger, more cohesive organization; a more efficient performer; a more agile competitor. | Maps To… | Build for Success\Construct\Implementation Planning\Training + Build for Success\Implement\Implementation Planning\Perform Training + Build for Success\Design\Execute Planning\Training + Build for Success\Analysis\Project Strategies\Training Educate for Success
[TS] Transition | In the Transition process, we focus on installing the solution (which includes providing installation procedures) and then going production. It begins early in the project by defining the specific requirements for cut-over to the new application system. It then includes tasks to carry out the elements of that strategy such as developing an Installation Plan, preparing the Production Environment, performing the cut-over, and decommissioning any legacy systems. | Maps To… | Build for Success\Implement
[PS] Operations and Support | The goal of the Operations and Support process is to monitor and respond to system problems, upgrade the application to fix errors and performance problems, evaluate the system in production and plan enhancements for increased functionality, improved performance, and tighter security. | Maps To… | Build for Success\Implement\Exit Gate\Post Implementation Review + Support the Solution

## OUM_TO_Hyperion_TASK_Mapping
Oum Sort Key | Act. Sort Key | OUM Phase | OUM Process | OUM Activity ID | OUM Activity Name | OUM Task ID | OUM Task Name / Work Product | Apps OUM LCD Task Dep. | New in OUM 5.0 | OUM Apps View | BPM Applic. (Y/N) | BPM Phase | BPM Process | BPM Activity | BPM Task(s) | Supp. Guide Cand. | Mapping Notes
122 | 126 | [B] Elaboration | [AN] Analysis | B.ACT.ADE | Analyze and Design - Elaboration | AN.020.1 | Create Analysis Model / Use Case Realization-Analysis | A.PMC.LCOB |  | Y | Y |  |  | Architect the solution | No direct mapping |  | Optional
124 | 128 | [B] Elaboration | [AN] Analysis | B.ACT.ADE | Analyze and Design - Elaboration | AN.025.1 | Analyze Business Rules/Analyzed Business Rules | B.RA.027.2 |  | Y | Y |  |  | Architect the solution | No direct mapping |  | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules
126 | 130 | [B] Elaboration | [AN] Analysis | B.ACT.ADE | Analyze and Design - Elaboration | AN.050.1 | Review Analysis Model / Review Results | B.AN.020.1 |  | Y | Y |  |  | Architect the solution | No direct mapping |  | Optional
128 | 256 | [C] Construction | [AN] Analysis | C.ACT.ADC | Analyze and Design - Construction | AN.020.2 | Create Analysis Model / Use Case Realization-Analysis | C.RA.180.2 |  | Y | Y |  |  | Analysis/Solution Requirements | Conceptual System Design
130 | 258 | [C] Construction | [AN] Analysis | C.ACT.ADC | Analyze and Design - Construction | AN.025.2 | Analyze Business Rules/Analyzed Business Rules | C.RA.027.3 |  | Y | Y |  |  | Analysis/Application Requirements | Scope and Charter Document |  | Look specifically at example 3 (Data-Related Rules, and Workflo/process-Related, and Security Rules
132 | 260 | [C] Construction | [AN] Analysis | C.ACT.ADC | Analyze and Design - Construction | AN.050.2 | Review Analysis Model/Reviewed Analysis Model | C.AN.020.2 |  | Y | Y |  |  | Analysis/Exit Gate | Approval to Proceed |  | Finalizing, which may be just a check
388 | 60 | [A] Inception | [AP] Adoption & Learning | A.ACT.PPJT | Prepare Project Team | AP.030 | Prepare Project Team Learning Plan/Project Team Learning Plan | PS.PMC.PSSUM5 |  | Y | Y |  |  | Project Strategies | Training Strategy (document)
390 | 62 | [A] Inception | [AP] Adoption & Learning | A.ACT.PPJT | Prepare Project Team | AP.040 | Prepare Project Team Learning Environment/Working Learning Environment | A.AP.030 |  | y | Y |  |  | Project Strategies | Training Strategy (document)
392 | 64 | [A] Inception | [AP] Adoption & Learning | A.ACT.PPJT | Prepare Project Team | AP.050 | Conduct Project Team Learning Events/Skilled Project Team | A.AP.040 |  | y | Y |  |  | Project Strategies | Training Strategy (document)
394 | 226 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.060 | Develop Business Units Managers’ Readiness Plan/Business Units Managers’ Readiness Plan | A.PMC.LCOB |  | Y | Y |  |  | No direct mapping | No direct mapping
396 | 228 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.070 | Develop Organizational Change Management Plan/Organizational Change Management Plan | B.AP.060 |  | Y | Y |  |  | No direct mapping | No direct mapping
398 | 230 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.080.1 | Develop Communication Plan/Communication Plan | B.AP.070 |  | Y | Y |  |  | Manage Communication | n/a
400 | 232 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.090 | Develop Managers’ Readiness Plan/Managers’ Readiness Plan | B.AP.070 |  | Y | Y |  |  | No direct mapping | No direct mapping | Y | Typically occurs right before Elaboration Phase or very early in Elaboration
402 | 234 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.100 | Identify Business Process Impact on Organization/Business Process Organizational Impact | A.PMC.LCOB |  | Y | Y |  |  | No direct mapping | No direct mapping
404 | 236 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.110 | Align Human Performance Support Systems/Human Performance Support Systems | B.AP.100 |  | Y | Y |  |  | No direct mapping | No direct mapping
406 | 238 | [B] Elaboration | [AP] Adoption & Learning | B.ACT.POA | Prepare Org. for Adoption | AP.120 | Align Information Technology Groups/Aligned IT Groups | B.AP.110 |  | Y | Y |  |  | No direct mapping | No direct mapping
408 | 382 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.080.2 | Develop Communication Plan/Communication Plan | B.PMC.LCAR |  | Y | Y |  |  | Manage Communication | No direct mapping
410 | 384 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.130 | Conduct User Learning Needs Analysis/User Learning Needs Analysis | B.PMC.LCAR |  | Y | Y |  |  | Executive Planning | Training Plan
412 | 386 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.140 | Develop User Learning Plan/User Learning Plan | C.AP.130 |  | Y | Y |  |  | Executive Planning | Training Plan
414 | 388 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.150 | Develop User Learningware/User Learningware | C.AP.140 |  | Y | Y |  |  | Implementation Planning | Construct "Training" material
416 | 390 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.160 | Prepare User Learning Environment/Configured User Learning Environment | C.AP.150 |  | Y | Y |  |  | No direct mapping | No direct mapping
418 | 452 | [C] Construction | [AP] Adoption & Learning | C.ACT.PUT | Prepare for User Training | AP.170.1 | Conduct User Learning Events / User Learning Events Administration |  |  |  | N
420 | 416 | [D] Transition | [AP] Adoption & Learning | D.ACT.TU | Train Users | AP.080.3 | Develop Communication Plan/Communication Plan | C.PMC.IOCM |  | Y | Y |  |  | Manage Communication
422 | 418 | [D] Transition | [AP] Adoption & Learning | D.ACT.TU | Train Users | AP.170.2 | Conduct User Learning Events/Skilled Users | C.PMC.IOCM |  | Y | Y |  |  | Implementation Preparation | Perform Training |  | Optional
424 | 420 | [D] Transition | [AP] Adoption & Learning | D.ACT.TU | Train Users | AP.180 | Conduct Effectiveness Assessment/Effectiveness Assessment | D.TS.060 |  | Y | Y |  |  | Implementation Preparation | Perform Training
332 | 44 | [A] Inception | [CV] Data Acq. & Conv. | A.ACT.GSP | Gather Supporting Requirements | CV.010 | Define Data Acquisition and Conversion Requirements/Data Acquisition and Conversion Requirements | A.RD.065, A.AP.050 |  | Y | Y |  |  | Project Strategies | Data Conversion Strategy (document)
334 | 94 | [B] Elaboration | [CV] Data Acq. & Conv. | B.ACT.DPS | Define Project Strategy | CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy/Data Acquisition, Conversion and Data Quality Strategy | A.PMC.LCOB |  | Y | Y |  |  | Project Strategies | Data Conversion Strategy (document)
336 | 222 | [B] Elaboration | [CV] Data Acq. & Conv. | B.ACT.PACDE | Prepare to Acquire & Conver Data - Elaboration | CV.025 | Define Data Acquisition and Conversion Standards/Data Acquisition and Conversion Standards | B.CV.020 |  | Y | Y |  |  | Executive Planning | Data Conversion Plan
338 | 438 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.027.1 | Perform Data Mapping/Data Mapping |  |  |  | Y |  |  | Analysis | No direct mapping | Y
340 | 440 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.030.1 | Prepare Conversion Environment (Initial Load)/Conversion Environment (Initial Load) |  |  |  | Y |  |  | Project Strategies | Data Conversion Strategy (document)
342 | 442 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.035.1 | Define Manual Conversion Procedures (Initial Load)/Manual Conversion Procedures (Initial Load) |  |  |  | Y |  |  | Project Strategies | Data Conversion Strategy (document)
344 | 444 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.040.1 | Design Conversion Components (Initial Load)/Conversion Component Designs (Initial Load) |  |  |  | Y |  |  | Project Strategies | Data Conversion Strategy (document)
346 | 446 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.050.1 | Prepare Conversion Test Plans (Initial Load)/Conversion Test Plans (Initial Load) |  |  |  | Y |  |  | Executive Planning | Testing Plan
348 | 448 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.055.1 | Implement Conversion Components (Initial Load)/Conversion Components (Initial Load) |  |  |  | Y |  |  | Build Solution | Integration - data conversion
350 | 450 | [B] Elaboration | [CV] Data Acq. & Conv. |  |  | CV.060.1 | Perform Conversion Component Test (Initial Load)/Conversion Component Test Results (Initial Load) |  |  |  | Y |  |  | No direct mapping | No direct mapping
352 | 354 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | CV.027.2 | Perform Data Mapping/Data Mapping | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping | Y
354 | 358 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | CV.030.2 | Prepare Conversion Environment (Initial Load)/Conversion Environment (Initial Load) | C.CV.027 |  | Y | N
356 | 360 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | CV.035.2 | Define Manual Conversion Procedures (Initial Load)/Manual Conversion Procedures (Initial Load) | C.DS.060.2FS-50% |  | Y | Y |  |  | No direct mapping | No direct mapping
358 | 362 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | CV.040.2 | Design Conversion Components (Initial Load)/Conversion Component Designs (Initial Load) | C.DS.060.2FS-50% |  | Y | Y |  |  | No direct mapping | No direct mapping
360 | 364 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | CV.050.2 | Prepare Conversion Test Plans (Initial Load)/Conversion Test Plans (Initial Load) | C.CV.035.2, C.CV.040.2 |  | Y | Y |  |  | No direct mapping | No direct mapping
362 | 366 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.ACDC | Acquire and Convert Data - Construction | CV.055.2 | Implement Conversion Components (Initial Load)/Conversion Components (Initial Load) | C.IM.040.2, C.CV.040.2 |  | Y | Y |  |  | Implementation Planning | Construct "Data conversion" programs
364 | 368 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.ACDC | Acquire and Convert Data - Construction | CV.060.2 | Perform Conversion Component Test (Initial Load)/Conversion Component Test Results (Initial Load) | C.CV.055.2SS+25%, C.CV.050.2 |  | Y | Y |  |  | No direct mapping | No direct mapping |  | Typically performed at Activity level
366 | 370 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.ACDC | Acquire and Convert Data - Construction | CV.065.1 | Convert and Verify Data (Initial Load)/Converted and Verified Data (Initial Load) | C.CV.060.2 |  | Y | Y |  |  | Build Solution | Integration - data conversion
368 | 372 | [C] Construction | [CV] Data Acq. & Conv. | C.ACT.ACDC | Acquire and Convert Data - Construction | CV.068.1 | Clean Data/Clean Legacy Data | C.CV.065.1SS |  | Y | Y |  |  | Build Solution | (Construct) Data Stores
370 | 402 | [D] Transition | [CV] Data Acq. & Conv. | D.ACT.CDT | Convert Data - Transition | CV.065.2 | Convert and Verify Data (Initial Load)/Converted and Verified Data (Initial Load) | C.PMC.IOCM |  | Y | Y |  |  | No direct mapping | No direct mapping
372 | 404 | [D] Transition | [CV] Data Acq. & Conv. | D.ACT.CDT | Convert Data - Transition | CV.068.2 | Clean Data/Clean Legacy Data | D.CV.065.2SS |  | Y | N
374 | 52 | [A] Inception | [DO] Documentation | A.ACT.GSP | Gather Supporting Requirements | DO.010 | Define Documentation Requirements and Strategy/Documentation Requirements and Strategy | A.RD.001, A.AP.050 |  | Y | Y |  |  | Manage Documents
376 | 96 | [B] Elaboration | [DO] Documentation | B.ACT.DPS | Define Project Strategy | DO.020 | Define Documentation Standards and Procedures/Documentation Standards and Procedures | A.PMC.LCOB |  | Y | Y |  |  | Manage Documents
378 | 116 | [B] Elaboration | [DO] Documentation | B.ACT.PEE | Prepare Environments - Elaboration | DO.040 | Prepare Documentation Environment/Documentation Environment | B.DO.020 |  | Y | Y | [5 empty] | Use existing customer environment.
380 | 374 | [C] Construction | [DO] Documentation | C.ACT.PD | Produce Documentation | DO.060 | Publish User Reference Manual/User Reference Manual | B.PMC.LCAR |  | Y | Y |  |  | Supporting Documentation | Create "Application Maintenance" Doc
382 | 376 | [C] Construction | [DO] Documentation | C.ACT.PD | Produce Documentation | DO.070 | Publish User Guide/User Guide | B.PMC.LCAR |  | Y | Y |  |  | Supporting Documentation | Create "End User" Manual
384 | 378 | [C] Construction | [DO] Documentation | C.ACT.PD | Produce Documentation | DO.080 | Publish Technical Reference Material/Technical Reference Material | B.PMC.LCAR |  | Y | Y |  |  | Technical Architecture, Supporting Documentation, Solution Requirements | Techincal Architecture/Create the Technical Architecture Design Document + Supporting Documentation/Create "Disaster Recovery" Doc + Solution Requirements/Conceptual Systems Design
385 | 380 | [C] Construction | [DO] Documentation | C.ACT.PD | Produce Documentation | DO.100 | Produce Online Help/Online Help | C.DO.060, C.DO.070 |  | Y | Y |  |  | No direct mapping | No direct mapping |  | Possibly yes for customizations
386 | 422 | [D] Transition | [DO] Documentation | D.ACT.FD | Finalize Documentation | DO.110 | Finalize Documentation/Final Documentation Work Products | C.PMC.IOCM |  | Y | Y |  |  | No direct mapping | No direct mapping
134 | 89 | [B] Elaboration | [DS] Design | B.ACT.DPS | Define Project Strategy | DS.005 | Define Application Extension Strategy/Application Extension Strategy | A.PMC.LCOB | Y | Y | Y |  |  | Project strategy | Implementation strategy (document) |  | For Hyperion engagements this is typically performed during the sales cycle and documened in the SOW/scoping document - This task is seen more as a touchpoint to this work by the sales force
136 | 124 | [B] Elaboration | [DS] Design | B.ACT.BSA | Baseline Software Architecture | DS.010.1 | Develop Architectural Design | B.RA.035 |  | Y | Y |  |  | Design preparation | Architectural Foundation
138 | 132 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.015 | Determine Design and Build Standards/Design and Build Standards | A.PMC.LCOB |  | Y | Y |  |  | Design Preparation | Standards and Guidelines
140 | 134 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.016 | Define Rules Implementation Strategy/Business Rules Implementation Strategy | B.TA.020 |  | Y | Y |  |  | Project strategies |  | Y | For Hyperion engagements this task and all the other tasks within the B.ACT.ADE activity are performed as one (I.e.activity)
142 | 136 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.017.1 | Design Business Rules/Business Rules Design | B.AN.025.1, B.DS.016 |  | Y | Y |  |  | Project strategies |  | Y | For Hyperion engagements this task and all the other tasks within the B.ACT.ADE activity are performed as one (I.e.activity)
144 | 138 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.020.1 | Develop Use Case Realization – Design/Use Case Realization | B.DS.010.1 |  | Y | Y |  |  | Project strategies
146 | 140 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.030.1 | Design Classes/Designed Classes | B.DS.010.1 |  | Y | Y |  |  | Design preparation | Desigin Preparation/Architectural Foundation + Design Preparation/Common Elements
148 | 142 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.040.1 | Design Software Components/Designed Software Components | B.RA.035 |  | Y | Y |  |  | Solution Design | Integration architecture - technical architecture |  | When customizations exist (I.e. non Oracle/Hyperion tech)
150 | 148 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.050.1 | Review Design Model/Reviewed Design Model | B.DS.020.1, B.DS.030.1, B.DS.040.1, B.DS.060.1 |  | Y | Y |  |  | Solution Design | Solution Design Review
152 | 146 | [B] Elaboration | [DS] Design | B.ACT.ADE | Analyze and Design - Elaboration | DS.060.1 | Develop Database Design/Database Design | A.PMC.LCOB |  | Y | Y |  |  | Application Design | Application Design/Consolidation (App design) + Application Design/Enterprise Planning (App design) + Application Design/Management Reporting (App design) | Y | Not designing trandional relational DB, but rather desiging cubes for multi-dimensional
154 | 262 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.010.2 | Develop Architectural Design Description/Architectural Design Description | C.AN.050.2 |  | Y | Y |  |  | Solution Design | Integration architecture - technical architecture
156 | 264 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.017.2 | Design Business Rules/Business Rules Design | C.AN.025.2 |  | Y | Y |  |  | Integration Architecture | Solution Design Review-Create Solution Design Document | Y | Optional - In most cases not necessary for another iteration of this task…done in .1 version
158 | 268 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.020.2 | Develop Use Case Realization – Design/Use Case Realization | C.DS.010.2 |  | Y | Y |  |  | Integration Architecture | Solution Design Review-Create Solution Design Document
160 | 270 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.030.2 | Design Classes/Designed Classes | C.DS.010.2 |  | Y | Y |  |  | Design Preparation | Common Elements
162 | 272 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.040.2 | Design Software Components/Designed Software Components | C.DS.020.2 |  | Y | Y |  |  | Solution Design | Integration architecture - technical architecture |  | When customizations exist (I.e. non Oracle/Hyperion tech), Solution Design, Integration architecture, technical architectureWhen customizations exist (I.e. non Oracle/Hyperion tech),
164 | 276 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.050.2 | Review Design Model/Reviewed Design Model | C.DS.030.2, C.DS.040.2, C.DS.060.2 |  | Y | Y |  |  | Application Design | Application Design Review |  | Activity level
166 | 274 | [C] Construction | [DS] Design | C.ACT.ADC | Analyze and Design - Construction | DS.060.2 | Develop Database Design/Database Design | C.DS.010.2 |  | Y | Y |  |  | Application Design |  | Y | Not designing trandional relational DB, but rather desiging cubes for multi-dimensional, or designing non-OLAP applications (e.g. DRM)
168 | 40 | [A] Inception | [IM] Implementation | A.ACT.CCP | Create Conceptual Prototype | IM.005 | Develop Conceptual Prototype/Conceptual Prototype | A.RA.023.1 |  | Y | Y |  |  | Solution Requirements | Conceptual Systems Design | Y | Sales cycle/SC demo.
170 | 108 | [B] Elaboration | [IM] Implementation | B.ACT.PEE | Prepare Environments - Elaboration | IM.007.1 | Prepare Development Environment/Development Environment | A.PMC.LCOB Apps Supplemental GuideFuctional Prototype EnvironmentCRP Environment |  | Y | Y |  |  | Configure Environment |  |  | Activity level
180 | 150 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.010 | Develop Functional Prototype/Functional PrototypeIncludes configuration. | A.PMC.LCOB Apps Supplemental Guide?Prerequisite and Dependency for AppsB.TE.025.1 |  | Y | Y |  |  | Exit Gate | Conference Room Pilot-S/ware demo
182 | 152 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.020 | Develop Architectural Foundation/Architectural Foundation | A.PMC.LCOB |  | Y | Y |  |  | Exit Gate | Conference Room Pilot-S/ware demo | Y | Optional - When it is performed, the task is performed at the activity level (develop prototypes). This is typically shown to the customer in the pre-sale cycle…The result of this pre-sale work would be documented…This would only occur here if something really changed since pre-sale
184 | 156 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.040.1 | Implement Database/Implemented Database | B.DS.050.1 |  | Y | Y |  |  | Exit Gate | Conference Room Pilot-S/ware demo | Y | See out sort key 152 - Creating database means creating initial chart-of-accounts / master data hierarchy
186 | 158 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.055.1 | Perform Rules Implementation (Rules Engine)/Implemented Business Rules (Rules Engine) | B.DS.017.1 |  | Y | Y | [5 empty] | define rules
188 | 160 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.060.1 | Perform Component Review/Component Review Results | B.IM.040.1SS+50% |  | Y | Y |  |  | Application Design, Integration Architecture | Application Design/Application Design Review, Integration Architecture/Solution Design Review | Y | Optional - When done, for Hyperion this task is typically executed at an activity level, and is also very much a high-level prototype
190 | 154 | [B] Elaboration | [IM] Implementation | B.ACT.DP | Develop Prototypes | IM.085 | Develop Look and Feel Prototype/Look and Feel Prototype | A.PMC.LCOB |  | Y | Y |  |  | Exit Gate | Conference Room Pilot-S/ware demo
192 | 282 | [C] Construction | [IM] Implementation | C.ACT.PEC | Prepare Environments - Construction | IM.007.2 | Prepare Development Environment/Development Environment | C.TE.015.2, C.TE.050.2 |  | Y | Y |  |  | Configure Environment |  |  | Activity level
194 | 294 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.040.2 | Implement Database/Implemented Database | C.DS.050.2 |  | Y | Y |  |  | (Construct) Application |  | Y | For Hyperion it is more appropriate to use term creating application versus creating database, but yes task is performed
196 | 296 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.050 | Implement Components/Implemented Components | C.DS.050.2 |  | Y | Y |  |  | Integration - data conversion, (Construct) Data Stores |  |  | Activity level
198 | 298 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.055.2 | Perform Rules Implementation (Rules Engine)/Implemented Business Rules (Rules Engine) | C.DS.017.2 |  | Y | N
200 | 302 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.060.2 | Perform Component Review/Component Review Results | C.IM.040.2SS+50%, C.IM.050SS+50% |  | Y | Y |  |  | Application Design + Integration Architecture | Application Design/Application Design Review + Integration Architecture/Solution Design Review | Y | Optional - When done, for Hyperion this task is typically executed at an activity level
202 | 304 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.070 | Assemble Components/Assembled Components | C.IM.060.2SS+25% |  | Y | Y |  |  | Integration - data conversion + (Construct) Data Stores |  |  | Activity level
204 | 306 | [C] Construction | [IM] Implementation | C.ACT.IS | Implement System | IM.080 | Integrate Services/Integrated Services | C.IM.070 |  | Y | Y |  |  | Integration - data conversion + (Construct) Data Stores |  | Y | Activity level
444 | 426 | [E] Production | [PS] Oper. and Support | E.ACT.EPS | Evaulate Production System | PS.010 | Audit System/System Evaluation | E.PT.120 |  | Y | Y |  |  | Exit Gate | Post Implementation Review
446 | 428 | [E] Production | [PS] Oper. and Support | E.ACT.EPS | Evaulate Production System | PS.050 | Analyze Problems/Fault Corrections | E.PS.010 |  | Y | Y |  |  | Support for Success
448 | 430 | [E] Production | [PS] Oper. and Support | E.ACT.RPP | Resolve Production Problems | PS.060 | Monitor and Respond to System Problems/Problem Log | E.PS.050SS |  | Y | Y |  |  | Support for Success
450 | 454 | [E] Production | [PS] Oper. and Support |  |  | PS.080 |  |  |  |  | Y |  |  | No direct mapping | No direct mapping
452 | 456 | [E] Production | [PS] Oper. and Support |  |  | PS.090 |  |  |  |  | Y |  |  | No direct mapping | No direct mapping
454 | 458 | [E] Production | [PS] Oper. and Support |  |  | PS.100 |  |  |  |  | Y |  |  | No direct mapping | No direct mapping
456 | 460 | [E] Production | [PS] Oper. and Support |  |  | PS.120 |  |  |  |  | Y |  |  | No direct mapping | No direct mapping
458 | 462 | [E] Production | [PS] Oper. and Support |  |  | PS.130 |  |  |  |  | Y |  |  | No direct mapping | No direct mapping
460 | 432 | [E] Production | [PS] Oper. and Support | E.ACT.PF | Plan for Future | PS.135 | Determine Future Functional Enhancements/Future Functional Enhancements | D.PMC.SIP |  | Y | Y |  |  | Exit Gate | Post Implementation Review
462 | 434 | [E] Production | [PS] Oper. and Support | E.ACT.PF | Plan for Future | PS.140 | Plan Enhancements/Future MoSCoW List | E.PS.135 |  | Y | Y |  |  | Exit Gate | Post Implementation Review
276 | 48 | [A] Inception | [PT] Perf. Mgt. | A.ACT.GSP | Gather Supporting Requirements | PT.010 | Conduct Performance Management Workshop/Performance Management Workshop Results | A.RD.001, A.AP.050 |  | Y | Y |  |  | No direct mapping | No direct mapping
278 | 188 | [B] Elaboration | [PT] Perf. Mgt. | B.ACT.PPM | Plan Perf. Mgt. | PT.020 | Define Performance Management Requirements and Strategy/Performance Management Requirements and Strategy | B.RA.024.1FS-50% |  | Y | Y |  |  | Project Strategies | Testing Strategy (document)
280 | 190 | [B] Elaboration | [PT] Perf. Mgt. | B.ACT.PPM | Plan Perf. Mgt. | PT.030 | Define Performance Testing Strategy/Performance Testing Strategy | B.PT.020 |  | Y | Y |  |  | Executive Planning | Testing Plan
282 | 200 | [B] Elaboration | [PT] Perf. Mgt. | B.ACT.PPM | Plan Perf. Mgt. | PT.040 | Identify Performance Testing Models and Scenarios/Performance Testing Models and Scenarios | B.PT.030 |  | Y | Y |  |  | No direct mapping | No direct mapping
284 | 202 | [B] Elaboration | [PT] Perf. Mgt. | B.ACT.PPM | Plan Perf. Mgt. | PT.050 | Design Performance Test Scripts and Programs/Performance Test Scripts and Programs Design | B.PT.040 |  | Y | Y |  |  | Implementation Planning | Construct "Testing" programs |  | Optional for Hyperion DRM
286 | 204 | [B] Elaboration | [PT] Perf. Mgt. | B.ACT.PPM | Plan Perf. Mgt. | PT.060 | Design Performance Test Data and Load Programs/Performance Test Data and Load Programs Design | B.PT.040, B.CV.020 |  | Y | Y |  |  | Implementation Planning | Construct "Testing" programs |  | Typically managed and delivered at activity level
288 | 328 | [C] Construction | [PT] Perf. Mgt. | C.ACT.PPT | Prepare for Performance Testing | PT.070 | Build Performance Test Scripts and Programs/Performance Test Scripts and Programs | B.PMC.LCAR |  | Y | Y |  |  | Implementation Planning | Construct "Testing" programs
290 | 330 | [C] Construction | [PT] Perf. Mgt. | C.ACT.PPT | Prepare for Performance Testing | PT.080 | Construct Performance Test Environment and Database/Performance Test Environment and Database | B.PMC.LCAR |  | Y | Y |  |  | Implementation Planning | Construct "Testing" programs
292 | 332 | [C] Construction | [PT] Perf. Mgt. | C.ACT.PPT | Prepare for Performance Testing | PT.090 | Conduct Performance Test Dress Rehearsal/Validated Performance Test and Environment | C.PT.070, C.PT.080 |  | Y | Y |  |  | No direct mapping | No direct mapping
294 | 398 | [D] Transition | [PT] Perf. Mgt. | D.ACT.CPTST | Conduct Performance Test | PT.100 | Execute Performance Test/Performance Test Results | C.PMC.IOCM |  | Y | Y |  |  | Test Execution
296 | 400 | [D] Transition | [PT] Perf. Mgt. | D.ACT.CPTST | Conduct Performance Test | PT.110 | Create Performance Test Report/Performance Test Report | D.PT.100 |  | Y | Y |  |  | Exit Gate | Solution Test Review
298 | 424 | [E] Production | [PT] Perf. Mgt. | E.ACT.MPSP | Manage Production System Performance | PT.120 | Conduct Production Performance Management/Managed Production Environment | D.PMC.SIP |  | Y | Y |  |  | No direct mapping | No direct mapping
50 | 10 | [A] Inception | [RA] Req. Analysis | A.ACT.GBRI | Gather business req. - Inception | RA.015 | Develop Business Use Case Model/Business Use Case Model | A.RD.001 |  | Y | Y |  |  | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document)
52 | 30 | [A] Inception | [RA] Req. Analysis | A.ACT.GR | Gather Solution Requirements | RA.023.1 | Develop Use Case Model/Use Case Model | A.RD.045.1 |  | Y | Y |  |  | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document)
54 | 32 | [A] Inception | [RA] Req. Analysis | A.ACT.GR | Gather Solution Requirements | RA.27.1 | Identify Candidate Rules/Candidate Business Rules | A.RA.023.1 |  | Y | Y |  |  | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document) |  | Optional - In some cases the pre-sales consultants have done first iteration of this task
56 | 34 | [A] Inception | [RA] Req. Analysis | A.ACT.GR | Gather Solution Requirements | RA.028.1 | Populate Rules Repository/Populated Rules Repository | A.RA.027.1 |  | Y | Y |  |  | Application Requirements | Scope & Charter Document - Verification
58 | 42 | [A] Inception | [RA] Req. Analysis | A.ACT.CCP | Gather Supporting Requirements | RA.030 | Validate Conceptual Prototype/Validated Conceptual Prototype | A.IM.005 |  | Y | Y |  |  | Demo to Win |  |  | Sales cycle/SC demo. Activity level.
60 | 56 | [A] Inception | [RA] Req. Analysis | A.ACT.SKSD | Specify Key Structure Definition | RA.040 | Define Key Business Architecture Structures/Application Architecture | A.RD.011, A.RD.012, A. RD.030, A.TA.010B.TA.020-For the future, think about B.TA.020 being in Inception. | Y | Y | Y |  |  | Architect the Solution | Architect the Solution/Business Requirements, Architect the Solution/BluePrint, Architect the Solution/BPMR (BPMR Overview Document)
62 | 58 | [A] Inception | [RA] Req. Analysis | A.ACT.SKSD | Specify Key Structure Definition | RA.045 | Define Application Configuration Parameters/Application Architecture Setup Parameters | A.RA.040 | Y | Y | Y | [5 empty] | Not executed in Inception but rather in Elaobortion...Maybe exectuted here in the broadest terms (part of task RA.65.1)...Commonly referred to as "System Preferences" in DRM Hyperion (e.g. restricted characters in node name) + Console Configuration (# of web servers, web farm, data traffic management)…System preferences = functional control, and console configuration = system control
64 | 72 | [B] Elaboration | [RA] Req. Analysis | B.ACT.DUC | Develop Use Cases | RA.023.2 | Develop Use Case Model/Use Case Model | A.PMC.LCOB |  | Y | Y |  |  | Application Requirements | Scope & Charter Document
66 | 74 | [B] Elaboration | [RA] Req. Analysis | B.ACT.DUC | Develop Use Cases | RA.024.1 | Develop Use Case Details/User Case Specification | B.RA.023.2FS-50% |  | Y | Y |  |  | Application Requirements | Scope & Charter Document
68 | 84 | [B] Elaboration | [RA] Req. Analysis | B.ACT.CS | Consolidate Specification | RA.027.2 | Identify Candidate Rules/Candidate Business Rules | B.RA.023.2, B.RD.042.2 |  | Y | Y |  |  | Application Requirements | Scope & Charter Document - Verification
70 | 86 | [B] Elaboration | [RA] Req. Analysis | B.ACT.CS | Consolidate Specification | RA.028.2 | Populate Rules Repository/Populated Rules Repository | B.RA.027.2 |  | Y | Y
72 | 122 | [B] Elaboration | [RA] Req. Analysis | B.ACT.BSA | Baseline Software Architecture | RA.035 | Develop High-Level Software Architecture Description/High-Level Software Architecture Description | B.RA.023.2, B.RD.045.2 |  | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture
74 | 68 | [B] Elaboration | [RA] Req. Analysis | B.ACT.GBRE | Gather Business Req. - Elaboration | RA.050 | Identify Potential Gaps/Potential Process Gaps | B. RD.080 | Y | Y | Y |  |  | Application Requirements | Scope & Charter Document
76 | 70 | [B] Elaboration | [RA] Req. Analysis | B.ACT.GBRE | Gather Business Req. - Elaboration | RA.055.1 | Document Business Procedures/Business Procedure Documentation | B. RD.080, PrerequisitesB.RA.024, B.DO.020 | Y | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture
78 | 118 | [B] Elaboration | [RA] Req. Analysis | B.ACT.SSC | Specify Software Configuration | RA.060 | Define Business Data Structures/Business Data Structure Definitions | B.RD.045.2, B.RA.024.1List A. RA.040 as prerequisite | Y | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture | Y | True in some cases -- must confirm.
80 | 120 | [B] Elaboration | [RA] Req. Analysis | B.ACT.SSC | Specify Software Configuration | RA.065.1 | Define Application Setups/Application Setup Documents | B. RD.080, B.RD.045.2, B.RA.024.1 | Y | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture |  | This task includes work defined in RA.045...Commonly referred to as "System Preferences" in DRM Hyperion (e.g. restricted characters in node name) + Console Configuration (# of web servers, web farm, data traffic management)…System preferences = functional control, and console configuration = system control
82 | 162 | [B] Elaboration | [RA] Req. Analysis | B.ACT.VP | Validate Prototypes | RA.085 | Validate Functional Prototype/Validated Functional Prototype | B.IM.010 |  | Y | Y |  |  | No direct mapping | No direct mapping |  | Optional based upon customer scenario
84 | 164 | [B] Elaboration | [RA] Req. Analysis | B.ACT.VP | Validate Prototypes | RA.090 | Conduct Reporting Fit Analysis/Reporting Fit Analysis | B.IM.010 | Y | Y | Y |  |  | No direct mapping | No direct mapping | ?
86 | 166 | [B] Elaboration | [RA] Req. Analysis | B.ACT.VP | Validate Prototypes | RA.095 | Validate Look and Feel Prototype/Validated Look and Feel Prototype | B.IM.085 |  | Y | Y |  |  | No direct mapping | No direct mapping | S | This is exectuted at the activity level, and it is very much high-level at this phase
88 | 168 | [B] Elaboration | [RA] Req. Analysis | B.ACT.PFG | Perform Fit Gap | RA.100 | Perform Fit Gap Analysis/Mapped Business Requirements | B.RA.050, B.RA.085, B.RA.090 | Y | Y | Y |  |  | No direct mapping | No direct mapping | Y
90 | 170 | [B] Elaboration | [RA] Req. Analysis | B.ACT.PFG | Perform Fit Gap | RA.110 | Determine Alternatives and Solutions/Application Extension Alternatives | B.RA.100 | Y | Y | Y |  |  | No direct mapping | No direct mapping
92 | 172 | [B] Elaboration | [RA] Req. Analysis | B.ACT.PFG | Perform Fit Gap | RA.120 | Define High-Level Estimate/Application Extension Estimates | B.RA.110 | Y | Y | Y |  |  | No direct mapping | No direct mapping
94 | 174 | [B] Elaboration | [RA] Req. Analysis | B.ACT.PFG | Perform Fit Gap | RA.130 | Define Gap Resolutions/Gap Resolutions | B.RA.110, B.RA.120 | Y | Y | Y |  |  | No direct mapping | No direct mapping | Y
96 | 224 | [B] Elaboration | [RA] Req. Analysis | B.ACT.PACDE | Prepare to Acquire & Conver Data - Elaboration | RA.160 | Conduct Business Data Source Gap Analysis/Business Data Source Gap Analysis | B.CV.025 |  | Y | Y |  |  | No direct mapping | No direct mapping
97 | 225 | [B] Elaboration | [RA] Req. Analysis |  |  | RA.170.1 | Conduct Data Quality Assessment |  |  |  | Y |  |  | No direct mapping | No direct mapping | Y | Performed at the metadata level for DRM applications
100 | 88 | [B] Elaboration | [RA] Req. Analysis | B.ACT.CS | Consolidate Specification | RA.180.1 | Review Requirements Analysis Models/Reviewed Requirements Analysis Models | B.RA.024.1 |  | Y | Y |  |  | No direct mapping | No direct mapping
102 | 246 | [C] Construction | [RA] Req. Analysis | C.ACT.FR | Finalize Requirements | RA.023.3 | Develop Use Case Model/Use Case Model | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
104 | 248 | [C] Construction | [RA] Req. Analysis | C.ACT.FR | Finalize Requirements | RA.024.2 | Develop Use Case Details/Use Case Specification | C.RA.023.3FS-50% |  | Y | Y |  |  | No direct mapping | No direct mapping
106 | 250 | [C] Construction | [RA] Req. Analysis | C.ACT.FR | Finalize Requirements | RA.027.3 | Identify Candidate Rules/Candidate Business Rules | C.RA.023.3, C.RD.042.3 |  | Y | Y |  |  | No direct mapping | No direct mapping |  | This occurs via the Project Scope and Charter Document
108 | 252 | [C] Construction | [RA] Req. Analysis | C.ACT.FR | Finalize Requirements | RA.028.3 | Populate Rules Repository/Populated Rules Repository | C.RA.027.3 |  | Y | Y
114 | 322 | [C] Construction | [RA] Req. Analysis | C.ACT.PSTC | Perform System Test - Construction | RA.055.2 | Document Business Procedures/Business Procedure Documentation | C.TE.070.2 Prerequisite B.RA.055.1 | Y | Y | Y |  |  | No direct mapping | No direct mapping
116 | 300 | [C] Construction | [RA] Req. Analysis | C.ACT.IS | Implement System | RA.065.2 | Define Application Setups/Application Setup Documents | B.PMC.LCAR Prerequisites B.RA.065.1B.RA.100 | Y | Y | Y |  |  | No direct mapping | No direct mapping |  | Optional
118 | 356 | [C] Construction | [RA] Req. Analysis | C.ACT.PACDC | Prepare to Acquire & Convert Data - Construction | RA.170.2 | Conduct Data Quality Assessment/High-Level Data Quality Assessment | C.CV.027 |  | Y | Y |  |  | No direct mapping | No direct mapping
120 | 254 | [C] Construction | [RA] Req. Analysis | C.ACT.FR | Finalize Requirements | RA.180.2 | Review Requirements Analysis Models/Reviewed Requirements Analysis Models | C.RA.024.2 |  | Y | Y |  |  | No direct mapping | No direct mapping
2 | 2 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.001 | Detail Busines and System Objectives/Business and System Objectives | PS.PMC.PSSUM5, A.AP.050 |  | Y | Y |  |  | Architect the Solution | Business Requirements
4 | 4 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.005 | Create Context Process Model/Context Process Model | A.RD.001 |  | Y | Y |  |  | No direct mapping | No direct mapping
6 | 6 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.011 | Create High-Level Business Process Model/High-Level Business Process Model(Level 1 and 2) | A.RD.001 |  | Y | Y |  |  | No direct mapping | No direct mapping
8 | 14 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.012 | Document Present and Future Organization Structures/Present and Future Organization Structures | A.RD.005, A.RD.011, A.RD.020, A.RD.065, A.RA.015 |  | Y | Y |  |  | Analysis | Scope & Charter Document - Specification
10 | 8 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.020 | Obtain High-Level Business Descriptions/High-Level Business Descriptions | A.RD.001 |  | Y | Y |  |  | Analysis | Scope & Charter Document - Elicitation
12 | 16 | [A] Inception | [RD] Business Requirements | A.ACT.ECBB | Establish Current Business Baseline | RD.030 | Develop Current Business Process Model/ Current Process Model | A.RD.020 | Y | Y | Y |  |  | No direct mapping | No direct mapping |  | Optional - Based
14 | 18 | [A] Inception | [RD] Business Requirements | A.ACT.ECBB | Establish Current Business Baseline | RD.034 | Document Current Business Baseline/ Current Business Baseline | A.RD.012, A.RD.030 | Y | Y | ? |  |  | No direct mapping | No direct mapping
16 | 20 | [A] Inception | [RD] Business Requirements | A.ACT.ECBB | Establish Current Business Baseline | RD.036 | Map Current Business Processes/Current Business Process Mapping Document | A.RD.011 (optional), A.RD.030 | Y | Y | Y |  |  | No direct mapping | No direct mapping
18 | 22 | [A] Inception | [RD] Business Requirements | A.ACT.GR | Gather Solution Requirements | RD.042.1 | Develop Glossary/Glossary | A.RD.005, A.RD.011, A.RD.020, A.RD.065, A.RA.015, A.RD.055 |  | Y | Y |  |  | No direct mapping | No direct mapping
20 | 24 | [A] Inception | [RD] Business Requirements | A.ACT.GR | Gather Solution Requirements | RD.045.1 | Prioritize Requirements (MoSCoW)/MoSCoW List | A.RD.005, A.RD.011, A.RD.020, A.RD.065, A.RA.015, A.RD.055, A.CV.010 |  | Y | Y |  |  | Propose the Solution | RFP-Consulting Service Proposal
22 | 26 | [A] Inception | [RD] Business Requirements | A.ACT.GR | Gather Solution Requirements | RD.055 | Detail Supplemental RequirementsSupplemental Requirements | A.RD.001 |  | Y | Y |  |  | No direct mapping | No direct mapping
24 | 12 | [A] Inception | [RD] Business Requirements | A.ACT.GBRI | Gather business req. - Inception | RD.065 | Develop Domain Model/Domain Model | A.RD.020 |  | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture
26 | 54 | [A] Inception | [RD] Business Requirements | A.ACT.GSP | Gather Supporting Requirements | RD.070 | Determine Audit and Control Requirements/Audit and Control Requirements | A.RD.012, A.RD.030, A.RD.055, A.RA.023.1 Prerequisite B.RD.080 (optional)-Sometimes these models are available before the project starts, if so use it.Also A.TA.010This is prereq to TA.090 as well.Involve Kim Z. | Y | Y | Y |  |  | Propose the Solution | Proof of Concept (Demo)-Gather requirements for customization
28 | 28 | [A] Inception | [RD] Business Requirements | A.ACT.GR | Gather Solution Requirements | RD.130.1 | Perform Global Analysis of the Application Architecture/Global Analysis of the Application Architecture | A.RD.045.1 |  | Y | Y |  |  | Solutions Requirements | Conceptual Systems Design - Technical Architecture
30 | 36 | [A] Inception | [RD] Business Requirements | A.ACT.CR | Consolidate Solution Requirements | RD.140.1 | Create Software Requirement Specification Document/Software Requirement Specification | A.RD.045.1 |  | Y | Y |  |  | Analysis | Scope & Charter Document - Specification
32 | 38 | [A] Inception | [RD] Business Requirements | A.ACT.CR | Consolidate Solution Requirements | RD.150.1 | Review Requirement Specification/Requirement Specification | A.RD.140.1 |  | Y | Y |  |  | Application Requirements | Scope & Charter Document - Verification
34 | 76 | [B] Elaboration | [RD] Business Requirements | B.ACT.CS | Consolidate Specification | RD.042.2 | Develop Glossary/Glossary | A.PMC.LCOB |  | Y | Y |  |  | No direct mapping | No direct mapping
36 | 78 | [B] Elaboration | [RD] Business Requirements | B.ACT.CS | Consolidate Specification | RD.045.2 | Prioritize Requirements (MoSCoW)/MoSCoW List | A.PMC.LCOB |  | Y | Y |  |  | Analysis | Scope & Charter Document
38 | 66 | [B] Elaboration | [RD] Business Requirements | B.ACT.GBRE | Gather Business Req. - Elaboration | RD.080 | Create Detail Business Process Model/Future Process Model | A.PMC.LCOBA.RD.001, A.RD.011, A.AP.050 Optional (why? Because you are not always doing a process model. Talk with Terri about clarifying intro to prerequisites.)A. RD.030,A.RD.036 | Y | Y | Y |  |  | No direct mapping | No direct mapping |  | Optional
40 | 80 | [B] Elaboration | [RD] Business Requirements | B.ACT.CS | Consolidate Specification | RD.140.2 | Create Software Requirement Specification Document/Software Requirement Specification | A.PMC.LCOB |  | Y | Y |  |  | Analysis | Scope & Charter Document
42 | 82 | [B] Elaboration | [RD] Business Requirements | B.ACT.CS | Consolidate Specification | RD.150.2 | Review Requirement Specification/Requirement Specification | B.RD.140.2 |  | Y | Y |  |  | Exit Gate | Exit Gate/Acceptance Criteria, Exit Gate/Approval to Proceed
44 | 240 | [C] Construction | [RD] Business Requirements | C.ACT.FR | Finalize Requirements | RD.042.3 | Develop Glossary/Glossary | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
46 | 242 | [C] Construction | [RD] Business Requirements | C.ACT.FR | Finalize Requirements | RD.045.3 | Prioritize Requirements (MoSCoW)/MoSCoW List | B.PMC.LCAR |  | Y | Y |  |  | Analysis | Scope & Charter Document
48 | 244 | [C] Construction | [RD] Business Requirements | C.ACT.FR | Finalize Requirements | RD.130.2 | Perform Global Analysis of the Application Architecture/Global Analysis of the Application Architecture | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
300 | 50 | [A] Inception | [TA] Tech. Arch. | A.ACT.GSP | Gather Supporting Requirements | TA.010 | Conduct Technical Architecture Workshop/Technical Architecture Workshop Results | A.RD.055, A.AP.050 |  | Y | Y |  |  | Solution Requirements | Technical Architecture, Conceptual Systems Design
302 | 206 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.020 | Define Architecture Requirements and Strategy/Architecture Requirements and Strategy | A.PMC.LCOB |  | Y | Y |  |  | Solution Requirements | Technical Architecture, Conceptual Systems Design
304 | 208 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.030 | Define Integration Requirements and Strategy/Integration Architecture Strategy | A.PMC.LCOB |  | Y | Y |  |  | Design Preparation | Architectural Foundation
306 | 210 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.040 | Define Reporting and Information Access Strategy/Reporting and Information Access Strategy | B.TA.020 |  | Y | Y |  |  | Solution Requirements | Conceptual Systems Design
308 | 212 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.050 | Define Disaster Recovery Strategy/Disaster Recovery Strategy | B.TA.020 |  | Y | Y |  |  | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
310 | 214 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.060 | Define System Operations and Management Strategy/System Operations and Management Strategy | B.TA.020 |  | Y | Y |  |  | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
312 | 216 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.070 | Develop Initial Architecture and Application Mapping/Initial Architecture and Application Mapping | B.TA.030, B.TA.040 |  | Y | Y |  |  | Solution Requirements | Conceptual Systems Design
314 | 218 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.080 | Define Backup and Recovery Strategy/Backup and Recovery Strategy | B.TA.050, B.TA.060, B.TA.070 |  | Y | Y |  |  | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
316 | 220 | [B] Elaboration | [TA] Tech. Arch. | B.ACT.DI | Define Infrastructure | TA.090 | Develop Security and Control Strategy/Security and Control Strategy | B.TA.070 |  | Y | Y |  |  | Solution Requirements | Solution Requirements/Conceptual Systems Design
318 | 334 | [C] Construction | [TA] Tech. Arch. | C.ACT.PT | Prepare for Transition | TA.100 | Define System Management Procedures/System Management Guide | B.PMC.LCAR |  | Y | Y |  |  | Supporting Documentation
320 | 336 | [C] Construction | [TA] Tech. Arch. | C.ACT.PT | Prepare for Transition | TA.110 | Define Operational Testing Plan/Operational Testing Plan | B.PMC.LCAR |  | Y | Y |  |  | Test Cases | Manage Test Cases
322 | 348 | [C] Construction | [TA] Tech. Arch. | C.ACT.TI | Test Infrastructure | TA.120 | Conduct Operational Testing/Operational Test Results | C.TA.110 |  | Y | Y |  |  | Test Execution | System Testing
324 | 350 | [C] Construction | [TA] Tech. Arch. | C.ACT.TI | Test Infrastructure | TA.130 | Conduct Backup and Recovery Test/Backup and Recovery Test Results | B.PMC.LCAR |  | Y | Y |  |  | Test Execution | System Testing
326 | 352 | [C] Construction | [TA] Tech. Arch. | C.ACT.TI | Test Infrastructure | TA.140 | Conduct Disaster Recovery Test/Disaster Recovery Test Results | B.PMC.LCAR |  | Y | Y |  |  | Test Execution | System Testing
328 | 338 | [C] Construction | [TA] Tech. Arch. | C.ACT.PT | Prepare for Transition | TA.150 | Define Final Platform and Network Architecture/Final Platform and Network Architecture | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
330 | 340 | [C] Construction | [TA] Tech. Arch. | C.ACT.PT | Prepare for Transition | TA.160 | Define System Capacity Plan/System Capacity Plan | B.PMC.LCAR |  | Y | Y |  |  | Project Strategies | Implementation Strategy (document)
206 | 46 | [A] Inception | [TE] Testing | A.ACT.GSP | Gather Supporting Requirements | TE.005.1 | Determine Testing Requirements/Testing Requirements | A.RD.045.1, A.RD.055, A.AP.050 |  | Y | Y |  |  | Project Strategies | Testing Strategy (document)
208 | 90 | [B] Elaboration | [TE] Testing | B.ACT.DPS | Define Project Strategy | TE.005.2 | Determine Testing Requirements/Testing Requirements | A.PMC.LCOB |  | Y | Y |  |  | Project Strategies | Testing Strategy (document)
210 | 92 | [B] Elaboration | [TE] Testing | B.ACT.DPS | Define Project Strategy | TE.010 | Develop Testing Strategy/Testing Strategy | B.RA.024.1FS-50%, B.TE.005.2 |  | Y | Y |  |  | Project Strategies | Testing Strategy (document)
212 | 100 | [B] Elaboration | [TE] Testing | B.ACT.DTP | Develop Test Plans | TE.015.1 | Develop Use Case Test Plan/Use Case Test Plan | B.TE.010 |  | Y | Y |  |  | Executive Planning | Testing Plan
214 | 110 | [B] Elaboration | [TE] Testing | B.ACT.PEE | Prepare Environments - Elaboration | TE.018.1 | Prepare Test Data/Test Data | B.TE.010 |  | Y | Y | [5 empty] | Done by customer or use existing customer data for testing - Very seldom directly addressed by implementation team
216 | 176 | [B] Elaboration | [TE] Testing | B.ACT.PUTE | Perform Unit Test - Elaboration | TE.020.1 | Develop Unit Test Scripts/Unit Test Scripts | B.IM.010SS |  | Y | Y | [5 empty] | Internal - not customer facing. Not needed in some cases.
218 | 178 | [B] Elaboration | [TE] Testing | B.ACT.PUTE | Perform Unit Test - Elaboration | TE.030.1 | Perform Unit Test/Unit-Tested Components | B.TE.020.1, B.IM.010 |  | Y | Y |  |  | Test Execution | Integration Testing
220 | 180 | [B] Elaboration | [TE] Testing | B.ACT.PUCTE | Perform Use Case Test - Elaboration | TE.035.1 | Create Use Case Test Scenarios/Use Case Test Scenarios | B.TE.015.1 |  | Y | Y |  |  | Implementation Planning | Construct "Testing" programs |  | Commonly referred to as text scripts, which are sometimes used in the system and user testing of Hyperion (depends on Hyperion application)
222 | 112 | [B] Elaboration | [TE] Testing | B.ACT.PEE | Prepare Environments - Elaboration | TE.038.1 | Prepare Use Case Test Environment/Use Case Test Environment | B.TE.015.1, B.TE.018.1SS |  | Y | Y | [5 empty] | Done by customer
224 | 182 | [B] Elaboration | [TE] Testing | B.ACT.PUCTE | Perform Use Case Test - Elaboration | TE.040.1 | Perform Use Case Test/Use Case Test Results | B.TE.035.1, B,TE.038.1, B.IM.010 |  | Y | Y |  |  | No direct mapping | No direct mapping |  | if applicable
226 | 102 | [B] Elaboration | [TE] Testing | B.ACT.DTP | Develop Test Plans | TE.050.1 | Develop System Test Plan/System Test Plan | B.TE.010 |  | Y | Y |  |  | Executive Planning | Testing Plan |  | Customer would often do this
228 | 184 | [B] Elaboration | [TE] Testing | B.ACT.PSTE | Perform System Test - Elaboration | TE.025.1 | Create System Test Scenarios/System Test Scenarios | B.TE.050.1 |  | Y | Y |  |  | Executive Planning | Testing Plan
230 | 114 | [B] Elaboration | [TE] Testing | B.ACT.PEE | Prepare Environments - Elaboration | TE.060.1 | Prepare System Test Environment/System Test Environment | B.TE.050.1 |  | Y | Y | [5 empty] | Done by customer ; initial creation of the environment maybe done by the "Infrastructure" team.
232 | 186 | [B] Elaboration | [TE] Testing | B.ACT.PSTE | Perform System Test - Elaboration | TE.070.1 | Perform System Test/System Test Results | B.TE.025.1, B.TE.060.1, B.IM.010 |  | Y | Y |  |  | Solution Design | Configure Environment
234 | 104 | [B] Elaboration | [TE] Testing | B.ACT.DTP | Develop Test Plans | TE.080 | Develop Systems Integration Test Plan/Systems Integration Test Plan | B.TE.010 |  | Y | Y |  |  | Executive Planning | Testing Plan
236 | 106 | [B] Elaboration | [TE] Testing | B.ACT.DTP | Develop Test Plans | TE.082 | Develop Acceptance Test Plan/Acceptance Test Plan | B.TE.010 |  | Y | Y |  |  | Executive Planning | Testing Plan
238 | 278 | [C] Construction | [TE] Testing | C.ACT.PTP | Perform Test Planning | TE.015.2 | Develop Use Case Test Plan/Use Case Test Plan | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
240 | 284 | [C] Construction | [TE] Testing | C.ACT.PEC | Prepare Environments - Construction | TE.018.2 | Prepare Test Data/Test Data | B.PMC.LCAR |  | Y | Y | [5 empty] | Optional, generally "Actuals" data from a known period is used.
242 | 308 | [C] Construction | [TE] Testing | C.ACT.PUTC | Perform Unit Test - Construction | TE.020.2 | Develop Unit Test Scripts/Unit Test Scripts | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
244 | 310 | [C] Construction | [TE] Testing | C.ACT.PUTC | Perform Unit Test - Construction | TE.030.2 | Perform Unit Test/Unit-Tested Components | C.TE.020.2SS |  | Y | Y |  |  | Test Execution | Integration Testing
246 | 312 | [C] Construction | [TE] Testing | C.ACT.PUCTC | Perform Use Case Test - Construction | TE.035.2 | Create Use Case Test Scenarios/Use Case Test Scenarios | C.TE.015.2 |  | Y | Y |  |  | Test Cases | Manage test cases
248 | 286 | [C] Construction | [TE] Testing | C.ACT.PEC | Prepare Environments - Construction | TE.038.2 | Prepare Use Case Test Environment/Use Case Test Environment | C.TE.015.2, C.TE.018.2SS |  | Y | N
250 | 314 | [C] Construction | [TE] Testing | C.ACT.PUCTC | Perform Use Case Test - Construction | TE.040.2 | Perform Use Case Test/Use Case Test Results | C.TE.035.2, C.TE.038.2 |  | Y | Y |  |  | Test Execution | Test Execution/System Testing, Test Execution/Acceptance Testing
252 | 280 | [C] Construction | [TE] Testing | C.ACT.PTP | Perform Test Planning | TE.050.2 | Develop System Test Plan/System Test Plan | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
254 | 316 | [C] Construction | [TE] Testing | C.ACT.PSTC | Perform System Test - Construction | TE.025.2 | Create System Test Scenarios/System Test Scenarios | C.TE.050.2 |  | Y | Y |  |  | No direct mapping | No direct mapping
256 | 288 | [C] Construction | [TE] Testing | C.ACT.PEC | Prepare Environments - Construction | TE.060.2 | Prepare System Test Environment/System Test Environment | C.TE.050.2 |  | Y | Y |  |  | No direct mapping | No direct mapping
258 | 292 | [C] Construction | [TE] Testing | C.ACT.IS | Implement System | TE.065 | Perform Installation Test/Tested Installation | C.TE.060.2 |  | Y | Y |  |  | No direct mapping | No direct mapping
260 | 318 | [C] Construction | [TE] Testing | C.ACT.PSTC | Perform System Test - Construction | TE.068 | Configure System Test Environment/ Configured System Test EnvironmentConfiguration only split configurations from TE.060 | C.TE.060.2 C.RA.065.2 | Y | Y | Y |  |  | No direct mapping | No direct mapping
262 | 320 | [C] Construction | [TE] Testing | C.ACT.PSTC | Perform System Test - Construction | TE.070.2 | Perform System Test/System Test Results | C.TE.025.2, C.TE.060.2 |  | Y | Y |  |  | Test Execution | System Testing
264 | 290 | [C] Construction | [TE] Testing | C.ACT.PEC | Prepare Environments - Construction | TE.085 | Prepare Systems Integration Test Environment/Systems Integration Test Environment | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping |  | Optional - Hyperion typically has 3 environments (Dev, Test, Prod)
266 | 324 | [C] Construction | [TE] Testing | C.ACT.CSIT | Conduct Systems Integration Test | TE.090 | Develop Systems Integration Test Scenarios/Systems Integration Test Scenarios | B.PMC.LCAR |  | Y | Y |  |  | No direct mapping | No direct mapping
268 | 326 | [C] Construction | [TE] Testing | C.ACT.CSIT | Conduct Systems Integration Test | TE.100 | Perform Systems Integration Test/Systems Integration Test Results | C.TE.090 |  | Y | Y |  |  | Test Execution | System Testing
270 | 392 | [D] Transition | [TE] Testing | D.ACT.PUAT | Perform User Acceptance Test | TE.105 | Prepare Users for Testing/Prepared Users for Testing | C.PMC.IOCM |  | Y | Y |  |  | No direct mapping | No direct mapping
272 | 394 | [D] Transition | [TE] Testing | D.ACT.PUAT | Perform User Acceptance Test | TE.110 | Prepare Acceptance Test Environment/Acceptance Test Environment | C.PMC.IOCM |  | Y | Y |  |  | No direct mapping | No direct mapping
274 | 396 | [D] Transition | [TE] Testing | D.ACT.PUAT | Perform User Acceptance Test | TE.120 | Perform Acceptance Test/Acceptance Test Results | D.TE.105, D.TE.110 |  | Y | Y |  |  | Test Execution | Acceptance Testing
426 | 98 | [B] Elaboration | [TS] Transition | B.ACT.DPS | Define Project Strategy | TS.010 | Define Initial Cut-Over Strategy/Initial Cut-Over Strategy | A.PMC.LCOB |  | Y | Y |  |  | Project Strategies | Implementation Strategy (document)
428 | 342 | [C] Construction | [TS] Transition | C.ACT.PCO | Prepare for Cut Over | TS.020 | Define Cut-Over Strategy/Cut-Over Strategy | B.PMC.LCAR |  | Y | Y |  |  | Executive Planning | Implementation Plan
430 | 344 | [C] Construction | [TS] Transition | C.ACT.PCO | Prepare for Cut Over | TS.030 | Develop Installation Plan/Installation Plan | B.PMC.LCAR |  | Y | Y |  |  | Implementation Planning | Implementation Planning/Construct "Testing" programs, Implementation Planning/Construct "Implementation" programs, Implementation Planning/Construct "Training" material, Implementation Planning/Construct "Data conversion" programs
432 | 346 | [C] Construction | [TS] Transition | C.ACT.PCO | Prepare for Cut Over | TS.040 | Design Production Support InfrastructureProduction Support Infrastructure Design | C.TA.100, C.TA.150PrerequisitesB.TA.020, B.TA.060, B.TA.070, B.AP.120 | Y | Y | N
434 | 406 | [D] Transition | [TS] Transition | D.ACT.GP | Go Production | TS.050 | Prepare Production Environment/Production Environment | C.PMC.IOCM |  | Y | Y |  |  | No direct mapping | No direct mapping
436 | 408 | [D] Transition | [TS] Transition | D.ACT.GP | Go Production | TS.054 | Implement Production Support Infrastructure/Production Support Infrastructure | D.AP.170.2 Prerequisite C.TS.040 | Y | Y | N
438 | 410 | [D] Transition | [TS] Transition | D.ACT.GP | Go Production | TS.058 | Verify Production Readiness/Production-Ready System | D.CV.065.2, D.TE.120, D.AP.170.2, D.TS.054, D.TS.050 PrerequisitesC.TS.030 | Y | Y | Y |  |  | Implementation Preparation | Go-Live Checkpoint |  | This could be nothing more than a quick checklist
440 | 412 | [D] Transition | [TS] Transition | D.ACT.GP | Go Production | TS.060 | Go Production/System in Production | D.CV.068.2, D.TE.120, D.PT.110, D.TS.050, D.TS.058 |  | Y | Y |  |  | Roll-Out, Exit Gate | Roll-Out/Implement Solution, Roll-Out/Monitor Solution, Roll-Out/Transition to Support, Exit Gate/Solution Review, Exit Gate/Final Approval, Exit Gate/Post Implementation Review
442 | 414 | [D] Transition | [TS] Transition | D.ACT.GP | Go Production | TS.070 | Shut Down Legacy System/Legacy System Shut Down | D.TS.060 |  | Y | Y |  |  | No direct mapping | No direct mapping
Note on A1: IMPORTANT - OUM Task Description links will work only if OUM is installed at the location of C:\METHOD. It is also important to not sort on tasks with any filters applied...Always do sort first, and then apply filters...Be sure to remove any column filters before attempting sorts. This spreadsheet is designed to allow one to view OUM tasks by process as it is displayed in the method by selecting the entire table and then sorting the data by column "A"* (Oum sort key), or alternatively sorting the tasks by activity based WBS by sorting the data by column "B" (Activity Sort Key). Note - The sort keys are spaced by two's in order to allow for new tasks to be inserted without having to re-key all rows. Once sorted, the tasks can be further filtered by phase, process, activity, task, etc.. The design of this spreadsheet is such that it can be used for more than simply mapping. *Need to denote that document does have header when sorting (should default to yes)
Note on I1: Contains the lowest common predecessort task dependency (LCD) that an OUM task has