## OUM to AIM Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | Comparable AIM Task ID | Comparable AIM Task Name
A Inception
A.ACT.GBRI Gather Business Requirements - Inception
|  | A.RD.001 | Detail Business and System Objectives | AP.010 BP.010 | Define Executive Project Strategy Define Business and Process Strategy
|  | A.RD.005 | Create System Context Diagram | BR.060 | Create Information Model
|  | A.RD.011.1 | Develop Future Process Model | BP.050 BP.080 | Review Leading Practices Develop Future Process Model
|  | A.RD.020 | Obtain High-Level Business Descriptions | BP.060 | Develop High-Level Process Vision
|  | A.RA.015 | Develop Business Use Case Model | BP.070 | Develop High-Level Process Designs
|  | A.RD.065 | Develop Domain Model (Business Entities) (Class Diagram)
|  | A.RD.012 | Document Present and Future Organization Structures | RD.010 | Identify Current Financial and Operating Structure
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model | BP.040 | Develop Current Process Model
|  | A.RD.034 | Document Current Business Baseline Metrics | RD.020 | Conduct Current Business Baseline
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary | DO.030 | Prepare Glossary
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW)
|  | A.RD.055 | Detail Supplemental Requirements | RD.070 | Identify Business Availability Requirements
|  | A.RD.130.1 | Develop Baseline Architecture Description | TA.010 | Define Architecture Requirements and Strategy
|  | A.RA.023.1 | Develop Use Case Model | RD.050 | Gather Business Requirements
|  | A.RA.027.1 | Identify Candidate Business Rules
|  | A.RA.028.1 | Populate Business Rules Repository
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification
|  | A.RD.150.1 | Review Requirements Specification
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype
|  | A.RA.030.1 | Validate Conceptual Prototype
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements | CV.010 | Define Data Conversion Requirements and Strategy
|  | A.TE.005.1 | Determine Testing Requirements | TE.010 | Define Testing Requirements and Strategy
|  | A.PT.010 | Conduct Performance Management Workshop | RD.040 | Gather Business Volumes and Metrics
|  | A.TA.010 | Conduct Technical Architecture Workshop
|  | A.DO.010 | Define Documentation Requirements and Strategy | DO.010 | Define Documentation Requirements and Strategy
|  | A.RD.070 | Determine Audit and Control Requirements | RD.060 | Determine Audit and Control Requirements
A.ACT.SKSD Specify Key Structure Definition
|  | A.MC.010.1 | Define Business Data Structures | TA.040 | Define Application Architecture
|  | A.MC.020 | Define Business Data Structure Setups | TA.040 | Define Application Architecture
A.ACT.CMAHC Create and Manage Ad Hoc Communications
|  | A.OCM.010 | Create and Manage Ad Hoc Communications
A.ACT.CEAW Conduct Executive Alignment Workshop
|  | A.OCM.020 | Prepare for Executive Alignment Workshop | AP.070 | Develop Project Readiness Roadmap
|  | A.OCM.030 | Conduct Executive Alignment Workshop | AP.070 | Develop Project Readiness Roadmap
|  | A.OCM.040 | Build and Deploy Sponsorship Program | AP.070 | Develop Project Readiness Roadmap
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy
|  | A.TR.020 | Prepare Project Team Learning Plan | AP.030 | Develop Project Team Learning Plan
|  | A.TR.030 | Prepare Project Team Learning Environment | AP.040 | Prepare Project Team Learning Environment
|  | A.TR.040 | Develop Project Team Learningware | AP.050 | Conduct Project Team Learning Events
|  | A.TR.050 | Conduct Project Team Learning Events | AP.050 | Conduct Project Team Learning Events
A.ACT.CAWI Conduct Alignment Workshops - Inception
|  | A.OCM.050 | Prepare for Team-Building Workshop
|  | A.OCM.060 | Conduct Team-Building Workshop
|  | A.OCM.070 | Design Managers Project Alignment Workshop | AP.090 | Develop Managers' Readiness Plan
|  | A.OCM.080 | Conduct Managers Project Alignment Workshop | AP.090 | Develop Managers' Readiness Plan
|  | A.OCM.090 | Design Change Agent Workshop
|  | A.OCM.100 | Conduct Change Agent Workshop
A.ACT.CCRA Conduct Change Readiness Assessment
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools | AP.070 | Develop Project Readiness Roadmap
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data | AP.070 | Develop Project Readiness Roadmap
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap | AP.070 | Develop Project Readiness Roadmap
A.ACT.DCMRCCI Deploy Change Management Roadmap and Communication Campaign - Inception
|  | A.OCM.140 | Develop Communication Campaign | AP.080 | Develop and Execute Communication Campaign
|  | A.OCM.150.1 | Conduct Change Management Roadmap and Communication Campaign | AP.080 | Develop and Execute Communication Campaign
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy | MD.010 | Define Application Extension Strategy
|  | B.TE.005.2 | Determine Testing Requirements | TE.010 | Define Testing Requirements and Strategy
|  | B.TE.010 | Develop Testing Strategy | TE.010 | Define Testing Requirements and Strategy
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy | CV.010 | Define Data Conversion Requirements and Strategy
|  | B.DO.020 | Define Documentation Standards and Procedures | DO.020 | Define Documentation Standards and Procedures
|  | B.TR.010.2 | Define Training Strategy
|  | B.TS.020.1 | Define Cutover Strategy | PM.010 | Define Transition Strategy
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy | TA.010 TA.020 | Define Architecture Requirements and Strategy Identify Current Technical Architecture
|  | B.TA.030 | Define Integration Requirements and Strategy | BR.050 | Conduct Integration Fit Analysis
|  | B.TA.040 | Define Reporting and Information Access Strategy | TA.060 | Define Reporting and Information Access Strategy
|  | B.TA.050 | Define Disaster Recovery Strategy
|  | B.TA.060 | Define System Operations and Management Strategy | TA.050 | Define System Availability Strategy
|  | B.TA.070 | Define Initial Architecture and Application Mapping | TA.030 | Develop Preliminary Conceptual Architecture
|  | B.TA.080 | Define Backup and Recovery Strategy | TA.150 | Define System Management Procedures
|  | B.TA.090 | Develop Security and Control Strategy | TA.080 | Define Application Security Architecture
B.ACT.PEE Prepare Environments-Elaboration
|  | B.IM.007.1 | Prepare Development Environment | MD.090 | Prepare Development Environment
|  | B.TE.018.1 | Prepare Static Test Data | TE.010 | Define Testing Requirements and Strategy
|  | B.TE.038.1 | Prepare Integration Test Environment | TE.060 | Prepare Testing Environments
|  | B.TE.060.1 | Prepare System Test Environment | BR.020 TE.060 | Prepare Mapping Environment Prepare Testing Environments
|  | B.DO.040 | Prepare Documentation Environment | DO.040 | Prepare Documentation Environment
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Develop Future Process Model | BP.080 | Develop Future Process Model
|  | B.RA.055.1 | Document Business Procedures | BP.090 | Document Business Procedures
|  | B.MC.030 | Map Business Requirements | BR.030 | Map Business Requirements
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan | TE.010 | Define Testing Requirements and Strategy
|  | B.TE.050.1 | Develop System Test Plan | TE.010 | Define Testing Requirements and Strategy
|  | B.TE.080 | Develop Systems Integration Test Plan | TE.010 | Define Testing Requirements and Strategy
|  | B.TE.082 | Develop Acceptance Test Plan | TE.010 | Define Testing Requirements and Strategy
B.ACT.SSC Specify Software Configuration
|  | B.MC.010.2 | Define Business Data Structures | BR.100 | Define Application Setups
|  | B.MC.040 | Gather Setup Information | BR.100 | Define Application Setups
|  | B.MC.050.1 | Define Application Setups | BR.100 | Define Application Setups
|  | B.MC.055 | Document Application Configuration Changes
|  | B.MC.060 | Document Functional Security | BR.110 | Design Security Profiles
B.ACT.PVC Prototype and Validate Configuration
|  | B.TE.025.1 | Create System Test Scenarios | TE.040 | Develop System Test Script
|  | B.MC.070 | Prepare Configuration Prototype Environment | BR.020 | Prepare Mapping Environment
|  | B.MC.080 | Conduct Configuration Prototyping Workshop | BR.080 | Test Business Solutions
|  | B.MC.090.2 | Conduct Reporting Fit Analysis | BR.070 | Conduct Reporting Fit Analysis
B.ACT.PGA Perform Gap Analysis
|  | B.MC.100 | Define and Estimate Application Extensions | MD.020 | Define and Estimate Application Extensions
|  | B.MC.110 | Define Gap Resolutions | BR.090 | Confirm Integrated Business Solutions
B.ACT.DUCM Develop Use Case Model
|  | B.RA.023.2 | Develop Use Case Model | RD.050 | Gather Business Requirements
B.ACT.CCPE Create Conceptual Prototype - Elaboration
|  | B.IM.005.2 | Develop Conceptual Prototype
|  | B.RA.030.2 | Validate Conceptual Prototype
B.ACT.CS Consolidate Specification
|  | B.RD.042.2 | Develop Glossary | DO.030 | Prepare Glossary
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW)
|  | B.RD.140.2 | Create Requirements Specification
|  | B.RD.150.2 | Review Requirements Specification
|  | B.RA.027.2 | Identify Candidate Business Rules
|  | B.RA.028.2 | Populate Business Rules Repository
|  | B.RA.180.1 | Review Use Case Model
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description
|  | B.AN.040.1 | Develop Analysis Architecture Description
|  | B.DS.040.1 | Develop Design Architecture Description
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details | RD.050 | Gather Business Requirements
B.ACT.AE Analyze - Elaboration
|  | B.AN.050.1 | Analyze Data | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | B.AN.060.1 | Analyze Behavior | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | B.AN.070.1 | Analyze Business Rules | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | B.AN.090.1 | Analyze User Interface | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | B.AN.100.1 | Prepare Analysis Specification | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | B.AN.110.1 | Review Analysis Model | B.MD.080 | Review Functional and Technical Designs
B.ACT.DE Design - Elaboration
|  | B.DS.050 | Determine Design and Build Standards | MD.030 MD.040 | Define Design Standards Define Build Standards
|  | B.DS.060 | Define Business Rules Implementation Strategy | B.MD.070 | Define Application Setups (Business Rules may be realized through configuration)
|  | B.DS.080.1 | Design Software Components | B.MD.070 | Create Application Extensions Technical Design
|  | B.DS.090.1 | Design Data | B.MD.070 | Create Application Extensions Technical Design
|  | B.DS.100.1 | Design Behavior | B.MD.070 | Create Application Extensions Technical Design
|  | B.DS.110.1 | Design Business Rules | B.MD.070 | Define Application Setups (Business Rules may be realized through configuration)
|  | B.DS.130.1 | Design User Interface | B.MD.070 | Create Application Extensions Technical Design
|  | B.DS.140.1 | Prepare Design Specification | B.MD.070 | Create Application Extensions Technical Design
|  | B.DS.150.1 | Develop Database Design | B.MD.060 | Design Database Extensions
|  | B.DS.160.1 | Review Design Model | B.MD.080 | Review Functional and Technical Designs
B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration
|  | B.TE.020.1 | Develop Unit Test Scripts | TE.020 | Develop Unit Test Script
|  | B.TE.035.1 | Create Integration Test Scenarios | TE.030 | Develop Link Test Script
B.ACT.DSTSE Develop System Test Scencarios – Elaboration
|  | B.TE.025.2 | Create System Test Scenarios | TE.040 | Develop System Test Script
B.ACT.DVCSP Develop and Validate Custom Software Prototypes (for Custom Extensions)
|  | B.IM.010 | Develop Functional Prototype | MD.110 | Create Application Extension Modules
|  | B.RA.085 | Validate Functional Prototype | BR.080 TE.110 | Test Business Solutions Perform System Test
|  | B.IM.020 | Develop Architectural Foundation | MD.090 | Prepare Development Environment
|  | B.IM.085 | Develop User Interface Standards Prototype | MD.110 | Create Application Extension Modules
|  | B.RA.095 | Validate User Interface Standards Prototype | BR.080 TE.110 | Test Business Solutions Perform System Test
|  | B.IM.040.1 | Implement Database | MD.100 | Create Database Extensions
|  | B.IM.055.1 | Perform Business Rules Implementation (Rules Engine) | BR.100 | Define Application Setups (Business Rules may be realized through configuration)
|  | B.IM.060.1 | Perform Component Review
B.ACT.PCCTE Perform Custom Component Testing - Elaboration
|  | B.TE.030.1 | Perform Unit Test | TE.070 | Perform Unit Test
|  | B.TE.040.1 | Perform Integration Test | TE.080 | Perform Link Test
B.ACT.PSTE Perform System Test – Elaboration
|  | B.TE.070.1 | Perform System Test | TE.110 | Perform System Test
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | B.PT.030 | Define Performance Testing Strategy | PT.010 | Define Performance Testing Strategy
|  | B.PT.040 | Identify Performance Testing Models and Scenarios | PT.020 PT.030 | Identify Performance Test Scenarios Identify Performance Test Transaction Models
|  | B.PT.050 | Design Performance Test Scripts and Programs | PT.040 PT.050 | Create Performance Test Scripts Design Performance Test Transaction Programs
|  | B.PT.060 | Design Performance Test Data and Load Programs | PT.060 PT.070 | Design Performance Test Data Design Test Database Load Programs
B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration
|  | B.CV.025 | Define Data Acquisition and Conversion Standards | CV.020 | Define Conversion Standards
|  | B.RA.160 | Conduct Business Data Source Gap Analysis | BR.040 | Map Business Data
B.ACT.PBPII Prepare Business Process Impact Inventory
|  | B.OCM.160 | Prepare Business Process Impact Inventory
B.ACT.DCMRCCE Deploy Change Management Roadmap and Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap and Communication Campaign | AP.080 | Develop and Execute Communication Campaign
|  | B.OCM.155.1 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | AP.080 | Develop and Execute Communication Campaign
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary | DO.030 | Prepare Glossary
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW)
|  | C.RD.130.2 | Develop Baseline Architecture Description | TA.070 | Revise Conceptual Architecture
|  | C.RA.023.3 | Develop Use Case Model | RD.050 | Gather Business Requirements
|  | C.RA.024.2 | Develop Use Case Details | RD.050 | Gather Business Requirements
|  | C.RA.027.3 | Identify Candidate Business Rules
|  | C.RA.028.3 | Populate Business Rules Repository
|  | C.RA.180.2 | Review Use Case Model
C.ACT.AC Analyze - Construction
|  | C.AN.040.2 | Develop Analysis Architecture Description
|  | C.AN.050.2 | Analyze Data | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | C.AN.060.2 | Analyze Behavior | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | C.AN.070.2 | Analyze Business Rules | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | C.AN.090.2 | Analyze User Interface | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | C.AN.100.2 | Prepare Analysis Specification | B.MD.050 | Create Application Extensions and Interfaces Functional Design
|  | C.AN.110.2 | Review Analysis Model | B.MD.080 | Review Functional and Technical Designs
C.ACT.DC Design - Construction
|  | C.DS.040.2 | Develop Design Architecture Description | TA.070 | Revise Conceptual Architecture
|  | C.DS.080.2 | Design Software Components | B.MD.070 | Create Application Extensions Technical Design
|  | C.DS.090.2 | Design Data | B.MD.070 | Create Application Extensions Technical Design
|  | C.DS.100.2 | Design Behavior | B.MD.070 | Create Application Extensions Technical Design
|  | C.DS.110.2 | Design Business Rules | B.MD.070
|  | C.DS.130.2 | Design User Interface | B.MD.070 | Create Application Extensions Technical Design
|  | C.DS.140.2 | Prepare Design Specification | B.MD.070 | Create Application Extensions Technical Design
|  | C.DS.150.2 | Develop Database Design | B.MD.060 | Design Database Extensions
|  | C.DS.160.2 | Review Design Model | B.MD.080 | Review Functional and Technical Designs
C.ACT.PTP Perform Test Planning
|  | C.TE.015.2 | Develop Integration Test Plan | TE.010 | Define Testing Requirements and Strategy
|  | C.TE.050.2 | Develop System Test Plan | TE.010 | Define Testing Requirements and Strategy
C.ACT.PEC Prepare Environments - Construction
|  | C.IM.007.2 | Prepare Development Environment | MD.090 | Prepare Development Environment
|  | C.TE.018.2 | Prepare Static Test Data
|  | C.TE.038.2 | Prepare Integration Test Environment | TE.060 | Prepare Testing Environments
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Develop Unit Test Scripts | TE.020 | Develop Unit Test Script
|  | C.TE.035.2 | Create Integration Test Scenarios | TE.030 | Develop Link Test Script
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios | TE.040 | Develop System Test Script
C.ACT.DSITS Develop Systems Integration Test Scenarios
|  | C.TE.090 | Develop Systems Integration Test Scenarios | TE.050 | Develop Systems Integration Test Script
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database | MD.100 | Create Database Extensions
|  | C.IM.050 | Implement Components | MD.110 | Create Application Extension Modules
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine)
|  | C.IM.060.2 | Perform Component Review
|  | C.IM.070 | Assemble Components
|  | C.IM.080 | Integrate Services
|  | C.IM.090 | Create Installation Routines | MD.120 | Create Installation Routines
|  | C.TE.065 | Perform Installation Test | TE.090 | Perform Installation Test
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test | TE.070 | Perform Unit Test
|  | C.TE.040.2 | Perform Integration Test | TE.080 | Perform Link Test
C.ACT.PST Prepare for System Test
|  | C.MC.050.2 | Define Application Setups | BR.100 | Define Application Setups
|  | C.TE.060.2 | Prepare System Test Environment | TE.060 | Prepare Testing Environments
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test | TE.110 | Perform System Test
|  | C.RA.055.2 | Document Business Procedures | BP.090 | Document Business Procedures
|  | C.TE.019.1 | Collect, Assess and Refine KPI Measurements
C.ACT.PSIT Perform Systems Integration Test
|  | C.TE.085 | Prepare Systems Integration Test Environment | TE.060 | Prepare Testing Environments
|  | C.TE.100 | Perform Systems Integration Test | TE.120 | Perform Systems Integration Test
C.ACT.PPT Prepare for Performance Testing
|  | C.PT.070 | Build Performance Test Scripts and Programs | PT.040 PT.080 | Create Performance Test Scripts Create Performance Test Transaction Programs
|  | C.PT.080 | Construct Performance Test Environment and Database | PT.100 PT.110 | Construct Performance Test Database Prepare Performance Test Environment
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures | TA.150 | Define System Management Procedures
|  | C.TA.110 | Define Operational Testing Plan
|  | C.TA.150 | Define Final Platform and Network Architecture | TA.120 | Define Platform and Network Architecture
|  | C.TA.160 | Define System Capacity Plan | TA.110 | Define System Capacity Plan
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy | PM.030 | Develop Transition and Contingency Plan
|  | C.TS.030 | Develop Installation Plan | PM.030 | Develop Transition and Contingency Plan
|  | C.TS.040 | Design Production Support Infrastructure | PM.020 | Design Production Support Infrastructure
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing
|  | C.TA.130 | Conduct Backup and Recovery Test
|  | C.TA.140 | Conduct Disaster Recovery Test
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping | CV.040 | Perform Conversion Data Mapping
|  | C.RA.170.2 | Conduct Data Quality Assessment
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load) | CV.050 | Define Manual Conversion Procedures
|  | C.CV.040.2 | Design Conversion Components (Initial Load) | CV.060 | Design Conversion Programs
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load) | CV.070 | Prepare Conversion Test Plans
C.ACT.ACDC Acquire and Convert Data-Construction
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) | CV.030 | Prepare Conversion Environment
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) | CV.080 | Develop Conversion Programs
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | CV.090 | Perform Conversion Unit Tests
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | CV.100 | Perform Conversion Business Object Tests
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | CV.110 | Perform Conversion Validation Tests
|  | C.CV.064.1 | Install Conversion Components (Initial Load) | CV.120 | Install Conversion Components
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) | CV.110 | Perform Conversion Validation Tests
|  | C.CV.068.1 | Clean Data | CV.110 | Perform Conversion Validation Tests
C.ACT.PD Produce Documentation
|  | C.DO.060 | Publish User Reference Manual | DO.060 | Publish User Reference Manual
|  | C.DO.070 | Publish User Guide | DO.070 | Publish User Guide
|  | C.DO.080 | Publish Technical Reference Material | DO.080 | Publish Technical Reference Manual
|  | C.DO.100 | Produce Online Help
C.ACT.DCMRCCC Deploy Change Management Roadmap and Communication Campaign - Construction
|  | C.OCM.150.3 | Conduct Change Management Roadmap and Communication Campaign | AP.080 | Develop and Execute Communication Campaign
|  | C.OCM.155.2 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | AP.080 | Develop and Execute Communication Campaign
C.ACT.CJIA Conduct Job Impact Analysis
|  | C.OCM.170 | Collect and Analyze Job Change Data | AP.100 | Identify Business Process Impact on Organization
|  | C.OCM.180 | Determine Impact of Job Changes | AP.100 AP.110 | Identify Business Process Impact on Organization Align Human Performance Support Systems
|  | C.OCM.190 | Prepare HR Transition Plan | AP.110 | Align Human Performance Support Systems
C.ACT.CMAWC Conduct Managers Alignment Workshop - Construction
|  | C.OCM.200 | Design Managers Unit and Department Impact Workshop | AP.060 | Develop Business Unit Managers' Readiness Plan
|  | C.OCM.210 | Conduct Managers Unit and Department Impact Workshop | AP.060 | Develop Business Unit Managers' Readiness Plan
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis | AP.130 | Conduct User Learning Needs Analysis
|  | C.TR.070 | Develop User Learning Plan | AP.140 | Develop User Learning Plan
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | AP.150 | Develop User Learningware
|  | C.TR.090 | Prepare User Learning Environment | AP.160 | Prepare User Learning Environment
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone
D Transition
D.ACT.SUAT Support User Acceptance Test
|  | D.TE.105 | Prepare Users for Testing | TE.100 | Prepare Key Users for Testing
|  | D.TE.110 | Prepare Acceptance Test Environment | TE.060 | Prepare Testing Environments
|  | D.TE.120 | Support Acceptance Test | TE.130 | Perform Acceptance Test
D.ACT.CPTST Conduct Performance Test
|  | D.PT.100 | Execute Performance Test | PT.120 | Execute Performance Test
|  | D.PT.110 | Create Performance Test Report | PT.130 | Create Performance Test Report
D.ACT.PPE Prepare Production Environment
|  | D.TS.050 | Prepare Production Environment | PM.040 PM.050 | Prepare Production Environment Set Up Applications
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load) | CV.120 | Install Conversion Components
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) | CV.130 | Convert and Verify Data
|  | D.CV.068.2 | Clean Data
D.ACT.DCMRCCT Deploy Change Management Roadmap and Communication Campaign - Transition
|  | D.OCM.150.4 | Conduct Change Management Roadmap and Communication Campaign | AP.080 | Develop and Execute Communication Campaign
|  | D.OCM.155.3 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | AP.080 | Develop and Execute Communication Campaign
D.ACT.CITA Conduct IT Alignment
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups | AP.120 | Align Information Technology Groups
|  | D.OCM.230 | Prepare IT Transition Plan | AP.120 | Align Information Technology Groups
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events | AP.170 | Conduct User Learning Events
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation
D.ACT.GP Go Production
|  | D.TS.052 | Implement Production Support Infrastructure | PM.060 | Implement Production Support Infrastructure
|  | D.TS.058 | Verify Production Readiness | PM.070 | Verify Production Readiness
|  | D.TS.060 | Go Production | PM.080 | Begin Production
|  | D.TS.070 | Shut Down Legacy System | PM.120 | Decommission Former Systems
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management | PM.090 | Measure System Performance
E.ACT.EPS Evaluate Production System
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements
|  | E.PS.010 | Audit System | AP.180 | Conduct Effectiveness Assessment
E.ACT.RPP Resolve Production Problems
|  | E.PS.050 | Analyze Problems | PM.100 | Maintain System
|  | E.PS.060 | Monitor and Respond to System Problems | PM.100 PM.110 | Maintain System Refine Production System
E.ACT.DCMRCCP Deploy Change Management Roadmap and Communication Campaign - Production
|  | E.OCM.150.5 | Conduct Change Management Roadmap and Communication Campaign | AP.080 | Develop and Execute Communication Campaign
|  | E.OCM.155.4 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | AP.080 | Develop and Execute Communication Campaign
E.ACT.PF Plan for Future
|  | E.PS.135 | Determine Future Functional Enhancements | PM.130 | Propose Future Business Direction
|  | E.PS.140 | Plan Enhancements
|  | E.OCM.250 | Measure Organizational Change Effectiveness | AP.180 | Conduct Effectiveness Assessment
E.ACT.DITTP Deploy IT Transition Plan
|  | E.OCM.260 | Implement IT Transition Plan | AP.120 | Align Information Technology Groups
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone