## OUM to Compass Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | Comparable Compass Activity | Comparable Compass Step Name
A Inception
A.ACT.GBRI Gather Business Requirements - Inception
|  | A.RD.001 | Detail Business and System Objectives | Define Mission, Objectives, and Performance Measures | Define Project Mission Statement
Define Project Objectives and Performance Measures
|  | A.RD.005 | Create System Context Diagram | Assess Business Needs and Impact | Prepare for Needs Assessment Sessions
|  | A.RD.011.1 | Develop Future Process Model | Perform Business Process Integration Modeling | Prepare for Business Process Integration Modeling Sessions
Conduct Business Process Integration Sessions
Confirm and Finalize Business Process Integration Models
Document and Analyze Business Process Integration Modeling Results
|  | A.RD.020 | Obtain High-Level Business Descriptions | Assess Business Needs and Impact | Conduct Needs Assessment Sessions
|  | A.RA.015 | Develop Business Use Case Model | Assess Business Needs and Impact | Identify Potential Customization Requirements
|  | A.RD.065 | Develop Domain Model (Business Entities) (Class Diagram)
|  | A.RD.012 | Document Present and Future Organization Structures
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model | Assess Business Needs and Impact | Obtain and Review Application Architecture
Obtain Organization Business Process Models
|  | A.RD.034 | Document Current Business Baseline Metrics
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW)
|  | A.RD.055 | Detail Supplemental Requirements
|  | A.RD.130.1 | Develop Baseline Architecture Description
|  | A.RA.023.1 | Develop Use Case Model
|  | A.RA.027.1 | Identify Candidate Business Rules
|  | A.RA.028.1 | Populate Business Rules Repository
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Functional Applications
|  |  |  | Assess Business Needs and Impact | Document and Analyze Needs Assessment Results
|  | A.RD.150.1 | Review Requirements Specification
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype
|  | A.RA.030.1 | Validate Conceptual Prototype
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Conversion
|  | A.TE.005.1 | Determine Testing Requirements | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Testing
|  | A.PT.010 | Conduct Performance Management Workshop
|  | A.TA.010 | Conduct Technical Architecture Workshop | Execute Technology Assessment Workshop
|  | A.DO.010 | Define Documentation Requirements and Strategy
|  | A.RD.070 | Determine Audit and Control Requirements | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Application Security
Define Strategy and Plan Scope for System Security
A.ACT.SKSD Specify Key Structure Definition
|  | A.MC.010.1 | Define Business Data Structures | Gather and Document Business Data Elements | Prepare for Business Data Element Sessions
|  | A.MC.020 | Define Business Data Structure Setups | Gather and Document Business Data Elements | Conduct Business Data Element Sessions Update Base Table Configuration and Setup Document
A.ACT.CMAHC Create and Manage Ad Hoc Communications
|  | A.OCM.010 | Create and Manage Ad Hoc Communications
A.ACT.CEAW Conduct Executive Alignment Workshop
|  | A.OCM.020 | Prepare for Executive Alignment Workshop | Create Organization and Business Process Change Management Plan | Define Organization Change Management Approach
|  | A.OCM.030 | Conduct Executive Alignment Workshop |  | Establish Organization Change Management Procedures
|  | A.OCM.040 | Build and Deploy Sponsorship Program
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Project Team Training
|  | A.TR.020 | Prepare Project Team Learning Plan | Train Project Team | Review the Project Team Training Strategy and Scope
Identify Project Team Training Requirements
Create Project Team Training Plan and Schedule
|  | A.TR.030 | Prepare Project Team Learning Environment | Create Project Environments
|  | A.TR.040 | Develop Project Team Learningware
|  | A.TR.050 | Conduct Project Team Learning Events | Train Project Team | Attend Training Sessions
A.ACT.CAWI Conduct Alignment Workshops - Inception
|  | A.OCM.050 | Prepare for Team-Building Workshop
|  | A.OCM.060 | Conduct Team-Building Workshop
|  | A.OCM.070 | Design Managers Project Alignment Workshop
|  | A.OCM.080 | Conduct Managers Project Alignment Workshop
|  | A.OCM.090 | Design Change Agent Workshop
|  | A.OCM.100 | Conduct Change Agent Workshop
A.ACT.CCRA Conduct Change Readiness Assessment
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap
A.ACT.DCMRCCI Deploy Change Management Roadmap and Communication Campaign - Inception
|  | A.OCM.140 | Develop Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
|  | A.OCM.150.1 | Conduct Change Management Roadmap and Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Customizations
Define Strategy and Plan Scope for Interfaces
|  | B.TE.005.2 | Determine Testing Requirements
|  | B.TE.010 | Develop Testing Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Testing
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Conversion
|  | B.DO.020 | Define Documentation Standards and Procedures | Define Project Standards and Administration | Create Project Diary
|  | B.TR.010.2 | Define Training Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Project Team Training
|  | B.TS.020.1 | Define Cutover Strategy | Define Project Approaches | Define Cutover Approach
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy | Consolidate Comprehensive Technical Architecture Strategy and Scope
|  | B.TA.030 | Define Integration Requirements and Strategy
|  | B.TA.040 | Define Reporting and Information Access Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Reporting
|  | B.TA.050 | Define Disaster Recovery Strategy | Define Project Approaches | Define Disaster Recovery Approach
|  | B.TA.060 | Define System Operations and Management Strategy | Define Project Approaches | Define Production Support Approach
|  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | B.TA.080 | Define Backup and Recovery Strategy | Prepare Production Environment | Establish Backup and Restore Processes
|  | B.TA.090 | Develop Security and Control Strategy | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Application Security
B.ACT.PEE Prepare Environments-Elaboration
|  | B.IM.007.1 | Prepare Development Environment | Create Project Environments
|  | B.TE.018.1 | Prepare Static Test Data
|  | B.TE.038.1 | Prepare Integration Test Environment
|  | B.TE.060.1 | Prepare System Test Environment | Perform Fit/Gap Analysis | Define Technical Environment for Fit/Gap
|  | B.DO.040 | Prepare Documentation Environment
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Develop Future Process Model | Perform Detailed Business Process Modeling | Review Business Needs and Process Integration Results, and Draft Business Process Modeling Schedule
Define Roles, Business Events and Scenarios for Business Process Modeling
Finalize Business Process Modeling Schedule
Draft Business Process Models
|  | B.RA.055.1 | Document Business Procedures | Perform Detailed Business Process Modeling | Document and Analyze Business Process Modeling Results
|  | B.MC.030 | Map Business Requirements | Perform Fit/Gap Analysis | Perform Fit/Gap Sessions
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan
|  | B.TE.050.1 | Develop System Test Plan | Create Test Plans | Create System Test Plan
|  | B.TE.080 | Develop Systems Integration Test Plan | Create Test Plans | Create Integration Test Plan
|  | B.TE.082 | Develop Acceptance Test Plan | Create Test Plans | Create User Test Plan
B.ACT.SSC Specify Software Configuration
|  | B.MC.010.2 | Define Business Data Structures | Gather and Document Business Data Elements | Review Base Table Configuration and Setup Document
Prepare for Business Data Element Sessions
Review and Clarify Responses
Conduct Business Data Element Sessions
|  | B.MC.040 | Gather Setup Information
|  | B.MC.050.1 | Define Application Setups | Gather and Document Business Data Elements | Update Base Table Configuration and Setup Document
|  | B.MC.055 | Document Application Configuration Changes
|  | B.MC.060 | Document Functional Security
B.ACT.PVC Prototype and Validate Configuration
|  | B.TE.025.1 | Create System Test Scenarios
|  | B.MC.070 | Prepare Configuration Prototype Environment
|  | B.MC.080 | Conduct Configuration Prototyping workshop
|  | B.MC.090 | Conduct Reporting Fit Analysis | Perform Fit/Gap Analysis | Perform Fit/Gap Sessions
B.ACT.PGA Perform Gap Analysis
|  | B.MC.100 | Define and Estimate Application Extensions | Perform Fit/Gap Analysis | Validate Potential Customization Requirements
|  |  |  | Define Gap Solutions and Functional Specifications | Determine Alternatives and Solutions
|  | B.MC.110 | Define Gap Resolutions | Define Gap Solutions and Functional Specifications | Prioritize Gap Solutions and Functional Specifications
B.ACT.DUCM Develop Use Case Model
|  | B.RA.023.2 | Develop Use Case Model
B.ACT.CCPE Create Conceptual Prototype - Elaboration
|  | B.IM.005.2 | Develop Conceptual Prototype
|  | B.RA.030.2 | Validate Conceptual Prototype
B.ACT.CS Consolidate Specification
|  | B.RD.042.2 | Develop Glossary
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW)
|  | B.RD.140.2 | Create Requirements Specification | Define Gap Solutions and Functional Specifications | Finalize and Document Gap Solutions and Functional Specifications
|  | B.RD.150.2 | Review Requirements Specification
|  | B.RA.027.2 | Identify Candidate Business Rules
|  | B.RA.028.2 | Populate Business Rules Repository
|  | B.RA.180.1 | Review Use Case Model
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description
|  | B.AN.040.1 | Develop Analysis Architecture Description
|  | B.DS.040.1 | Develop Design Architecture Description
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details
B.ACT.AE Analyze - Elaboration
|  | B.AN.050.1 | Analyze Data
|  | B.AN.060.1 | Analyze Behavior
|  | B.AN.070.1 | Analyze Business Rules
|  | B.AN.090.1 | Analyze User Interface
|  | B.AN.100.1 | Prepare Analysis Specification
|  | B.AN.110.1 | Review Analysis Model
B.ACT.DE Design - Elaboration
|  | B.DS.050 | Determine Design and Build Standards
|  | B.DS.060 | Define Business Rules Implementation Strategy
|  | B.DS.080.1 | Design Software Components | Design Customizations | Create Technical Specifications for Customizations
|  | B.DS.090.1 | Design Data
|  | B.DS.100.1 | Design Behavior
|  | B.DS.110.1 | Design Business Rules
|  | B.DS.130.1 | Design User Interface
|  | B.DS.140.1 | Prepare Design Specification
|  | B.DS.150.1 | Develop Database Design | Design Customizations | Create Technical Specifications for Customizations
|  | B.DS.160.1 | Review Design Model | Design Customizations | Create Technical Specifications for Customizations
B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration
|  | B.TE.020.1 | Develop Unit Test Scripts | Build Customizations | Unit Test Customizations
|  | B.TE.035.1 | Create Integration Test Scenarios
B.ACT.DSTSE Develop System Test Scenarios – Elaboration
|  | B.TE.025.2 | Create System Test Scenarios | Perform Fit/Gap Analysis | Define Business Events and Scenarios for Fit/Gap
B.ACT.DVCSP Develop and Validate Custom Software Prototypes
|  | B.IM.010 | Develop Functional Prototype | Perform Fit/Gap Analysis Build Customizations | Configure and Set Up Functional Environment for Fit/Gap Build Customizations
|  | B.RA.085 | Validate Functional Prototype | Perform Configuration Test Build Customizations | Unit Test Customizations
|  | B.IM.020 | Develop Architectural Foundation | Build Customizations | Build Customizations
|  | B.IM.085 | Develop User Interface Standards Prototype | Perform Fit/Gap Analysis Build Customizations | Review and Customize Necessary Objects for Fit/Gap Build Customizations
|  | B.RA.095 | Validate User Interface Standards Prototype | Perform Fit/Gap Analysis Perform Usability Test | Perform Fit/Gap Sessions
|  | B.IM.040.1 | Implement Database
|  | B.IM.055.1 | Perform Rules Implementation (Rules Engine)
|  | B.IM.060.1 | Perform Component Review
B.ACT.PCCTE Perform Custom Component Testing - Elaboration
|  | B.TE.030.1 | Perform Unit Test | Build Customizations | Unit Test Customizations
|  | B.TE.040.1 | Perform Integration Test
B.ACT.PSTE Perform System Test – Elaboration
|  | B.TE.070.1 | Perform System Test
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy | Establish Technical Architecture Performance Requirements
|  | B.PT.030 | Define Performance Testing Strategy | Create Test Plans | Create Performance Test Plan
|  |  |  | Create Test Plans | Create Stress/Load Test Plan
|  | B.PT.040 | Identify Performance Testing Models and Scenarios
|  | B.PT.050 | Design Performance Test Scripts and Programs | Perform Performance Test | Create Performance Test Scripts
|  |  |  | Perform Stress/Load Test | Create Stress/Load Test Scripts
|  | B.PT.060 | Design Performance Test Data and Load Programs
B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration
|  | B.CV.025 | Define Data Acquisition and Conversion Standards | Define Project Standards and Administration | Define Technical Project Standards
|  | B.RA.160 | Conduct Business Data Source Gap Analysis
B.ACT.PBPII Prepare Business Process Impact Inventory
|  | B.OCM.160 | Prepare Business Process Impact Inventory
B.ACT.DCMRCCE Deploy Change Management Roadmap and Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap and Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
|  | B.OCM.155.1 | Monitor Change Management Roadmap and Communication Campaign Effectiveness
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW)
|  | C.RD.130.2 | Develop Baseline Architecture Description
|  | C.RA.023.3 | Develop Use Case Model
|  | C.RA.024.2 | Develop Use Case Details
|  | C.RA.027.3 | Identify Candidate Business Rules
|  | C.RA.028.3 | Populate Business Rules Repository
|  | C.RA.180.2 | Review Use Case Model
C.ACT.AC Analyze - Construction
|  | C.AN.040.2 | Develop Analysis Architecture Description
|  | C.AN.050.2 | Analyze Data
|  | C.AN.060.2 | Analyze Behavior
|  | C.AN.070.2 | Analyze Business Rules
|  | C.AN.090.2 | Analyze User Interface
|  | C.AN.100.2 | Prepare Analysis Specification
|  | C.AN.110.2 | Review Analysis Specification
C.ACT.DC Design - Construction
|  | C.DS.040.2 | Develop Design Architecture Description
|  | C.DS.080.2 | Design Software Components | Design Customizations | Create Technical Specifications for Customizations
|  | C.DS.090.2 | Design Data
|  | C.DS.100.2 | Design Behavior
|  | C.DS.110.2 | Design Business Rules
|  | C.DS.130.2 | Design User Interface
|  | C.DS.140.2 | Prepare Design Specification
|  | C.DS.150.2 | Develop Database Design | Design Customizations | Create Technical Specifications for Customizations
|  | C.DS.160.2 | Review Design Specification | Design Customizations | Create Technical Specifications for Customizations
C.ACT.PTP Perform Test Planning
|  | C.TE.015.2 | Develop Integration Test Plan
|  | C.TE.050.2 | Develop System Test Plan | Create Test Plans | Create System Test Plan
C.ACT.PEC Prepare Environments - Construction
|  | C.IM.007.2 | Prepare Development Environment | Create Project Environments
|  | C.TE.018.2 | Prepare Static Test Data
|  | C.TE.038.2 | Prepare Integration Test Environment
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Develop Unit Test Scripts | Build Customizations | Unit Test Customizations
|  | C.TE.040.2 | Perform Integration Test
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios | Perform System Test | Review/Update System Test Scripts
C.ACT.DSITS Develop Systems Integration Test Scenarios
|  | C.TE.090 | Develop Systems Integration Test Scenarios | Perform Integration Test | Create Integration Test Scripts
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database | Create Project Environments | Create Database Environments
|  | C.IM.050 | Implement Components
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine)
|  | C.IM.060.2 | Perform Component Review
|  | C.IM.070 | Assemble Components
|  | C.IM.080 | Integrate Services
|  | C.IM.090 | Create Installation Routines
|  | C.TE.065 | Perform Installation Test
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test | Build Customizations | Unit Test Customizations
|  | C.TE.040.2 | Perform Integration Test
C.ACT.PST Prepare for System Test
|  | C.MC.050.2 | Define Application Setups | Update and Finalize Configuration and Setup of Base Tables
|  | C.TE.060.2 | Prepare System Test Environment
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test | Perform System Test | Execute System Test
Resolve System Test Issues
|  | C.RA.055.2 | Document Business Procedures
|  | C.TE.019.1 | Collect, Assess and Refine KPI Measurements
C.ACT.PSIT Perform Systems Integration Test
|  | C.TE.085 | Prepare Systems Integration Test Environment
|  | C.TE.100 | Perform Systems Integration Test | Perform Integration Test | Execute Integration Test
Resolve Integration Test Issues
C.ACT.PPT Prepare for Performance Testing
|  | C.PT.070 | Build Performance Test Scripts and Programs | Perform Performance Test | Create Performance Test Scripts
|  | C.PT.080 | Construct Performance Test Environment and Database
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures
|  | C.TA.110 | Define Operational Testing Plan | Perform Technical Architecture Test | Create Technical Architecture Test Scripts
|  | C.TA.150 | Define Final Platform and Network Architecture | Build Comprehensive Technical Architecture
|  | C.TA.160 | Define System Capacity Plan
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy | Define Approaches | Define Cutover Approach
|  | C.TS.030 | Develop Installation Plan | Create Cutover Plan
|  | C.TS.040 | Design Production Support Infrastructure | Create Production Support Plan
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing
|  | C.TA.130 | Conduct Backup and Recovery Test
|  | C.TA.140 | Conduct Disaster Recovery Test | Test Disaster Recovery Plan
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping | Design Conversions | Perform Data Mapping for Conversions
|  | C.RA.170.2 | Conduct Data Quality Assessment
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load) | Design Conversions | Design Conversions
|  | C.CV.040.2 | Design Conversion Components (Initial Load) | Design Conversions | Design Conversions
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load)
C.ACT.ACDC Acquire and Convert Data-Construction
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) | Design Conversions | Design Conversions
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) | Build Conversions | Build Conversions
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | Load Data and Execute Conversions - Preliminary | Verify Data
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | Load Data and Execute Conversions - Preliminary | Verify Data
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | Load Data and Execute Conversions - Preliminary | Verify Data
|  | C.CV.064.1 | Install Conversion Components (Initial Load) | Load Data and Execute Conversions - Preliminary | Verify Data
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) | Load Data and Execute Conversions - Preliminary | Verify Data
|  | C.CV.068.1 | Clean Data | Load Data and Execute Conversions - Preliminary | Clean Data
C.ACT.PD Produce Documentation
|  | C.DO.060 | Publish User Reference Manual | Create Process and Procedure Documentation | Create User Process and Procedure Documentation
|  | C.DO.070 | Publish User Guide
|  | C.DO.080 | Publish Technical Reference Material
|  | C.DO.100 | Produce Online Help
C.ACT.DCMRCCC Deploy Change Management Roadmap and Communication Campaign - Construction
|  | C.OCM.150.3 | Conduct Change Management Roadmap and Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
Create Marketing Communication Plan
|  | C.OCM.155.2 | Monitor Change Management Roadmap and Communication Campaign Effectiveness
C.ACT.CJIA Conduct Job Impact Analysis
|  | C.OCM.170 | Collect and Analyze Job Change Data
|  | C.OCM.180 | Determine Impact of Job Changes | Create Organization and Business Process Change Management Plan | Define Business Process Change Management Approach
Establish Business Process Change Management Procedures
|  | C.OCM.190 | Prepare HR Transition Plan
C.ACT.CMAWC Conduct Managers Alignment Workshop - Construction
|  | C.OCM.200 | Design Managers Unit and Department Impact Workshop | Create Organization and Business Process Change Management Plan | Define Business Process Change Management Approach
|  | C.OCM.210 | Conduct Managers Unit and Department Impact Workshop |  | Establish Business Process Change Management Procedures
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for End-User Training
|  | C.TR.070 | Develop User Learning Plan | Design End-User Training
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | Build End-User Training | Build Training Material
|  | C.TR.090 | Prepare User Learning Environment | Build End-User Training | Build Training Environments
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone
D Transition
| D.ACT.SUAT Support User Acceptance Test |  |  | Perform User Test
|  | D.TE.105 | Prepare Users for Testing
|  | D.TE.110 | Prepare Acceptance Test Environment
|  | D.TE.120 | Support Acceptance Test
| D.ACT.CPTST Conduct Performance Test |  |  | Perform Performance Test
|  | D.PT.100 | Execute Performance Test
|  | D.PT.110 | Create Performance Test Report
| D.ACT.PPE Prepare Production Environment |  |  | Perform Performance Test
|  | D.TS.050 | Prepare Production Environment - Consider inclusion of separate task to setup production application environment. | Prepare Production Environment | Establish Production Environment
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load) | Prepare Production Environment | Finalize Production Data and Conversions
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) | Prepare Production Environment | Finalize Production Data and Conversions
|  | D.CV.068.2 | Clean Data
D.ACT.DCMRCCT Deploy Change Management Roadmap and Communication Campaign - Transition
|  | D.OCM.150.4 | Conduct Change Management Roadmap and Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
Create Marketing Communication Plan
|  | D.OCM.155.3 | Monitor Change Management Roadmap and Communication Campaign Effectiveness
D.ACT.CITA Conduct IT Alignment
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups
|  | D.OCM.230 | Prepare IT Transition Plan
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events | Train End Users
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation
D.ACT.GP Go Production
|  | D.TS.052 | Implement Production Support Infrastructure | Prepare Production Environment | Migrate DB Objects
|  | D.TS.058 | Verify Production Readiness | Prepare Production Environment | Evaluate Production Environment Readiness
|  | D.TS.060 | Go Production | Execute Cut-Over Plan | Execute Cut-Over Plan
|  | D.TS.070 | Shut Down Legacy System
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management
E.ACT.EPS Evaluate Production System
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements
|  | E.PS.010 | Audit System
E.ACT.RPP Resolve Production Problems
|  | E.PS.050 | Analyze Problems
|  | E.PS.060 | Monitor and Respond to System Problems | Provide Post-Project Support
E.ACT.DCMRCCP Deploy Change Management Roadmap and Communication Campaign - Production
|  | E.OCM.150.5 | Conduct Change Management Roadmap and Communication Campaign | Create Organization Communication Plan
Create External Communication Plan
Create Marketing Communication Plan
|  | E.OCM.155.4 | Monitor Change Management Roadmap and Communication Campaign Effectiveness
E.ACT.PF Plan for Future
|  | E.PS.135 | Determine Future Functional Enhancements
|  | E.PS.140 | Plan Enhancements
|  | E.OCM.250 | Measure Organizational Change Effectiveness
E.ACT.DITTP Deploy IT Transition Plan
|  | E.OCM.260 | Implement IT Transition Plan
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone