## OUM to EMM Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | Comparable EMM Task ID | Comparable EMM Task Name
Envision
|  | BA.067 | Review Business Volumetrics | A.RR.060 | Gather Business Volumes
A Inception
| A.ACT.GBRI Gather Business Requirements - Inception |  |  | A.RR | Business Requirements Review
|  | A.RD.001 | Detail Business and System Objectives
|  | A.RD.011.1 | Review Future Process Model | A.RR.030 B.MU.100 A.RR.070 | Develop Future Process Model Update Process Narratives Review Business Requirements Scenarios
|  | A.RA.015 | Review Business Use Case Model
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Review Current Business Process Model | A.RR.020 | Review Current Business Processes
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW)
|  | A.RD.055 | Detail Supplemental Requirements
|  | A.RA.019 | Define Project Reference Architecture
|  | A.RA.023.1 | Review Use Case Model
|  | A.RA.025.1 | Identify Candidate Services
|  | A.RA.027.1 | Identify Candidate Business Rules
|  | A.RA.028.1 | Populate Business Rules Repository
A.ACT.PSUIA - Perform Software Upgrade Impact Analysis
|  | A.TA.004 | Perform Technical Architecture Impact Analysis | A.MA.020 | Perform Architecture Impact Analysis
|  | A.RD.134 | Identify New Software Release Changes | A.MU.005 | Identify New Release Changes
|  | A.RD.136 | Perform Customization Impact Analysis | A.ME.010 A.ME.020 | Perform Customization Impact Analysis Estimate Custom Extension Migration
|  | A.RD.138 | Perform Data Impact Analysis | A.DM.020 | Perform Data Impact Analysis
|  | A.MC.090.1 | Conduct Reporting Fit Analysis
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements
|  | A.TE.005.1 | Determine Testing Requirements
|  | A.PT.010 | Conduct Performance Management Workshop | B.MA.180 | Identify New Performance Risks
|  | A.TA.010 | Conduct Technical Architecture Workshop
|  | A.DO.010 | Review Documentation Requirements and Strategy
|  | A.RD.070 | Determine Audit and Control Requirements
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy | A.TR.010 | Prepare Training Strategy
|  | A.TR.020 | Prepare Project Team Learning Plan | A.TR.050 | Prepare Project Team Training
|  | A.TR.030 | Prepare Project Team Learning Environment
|  | A.TR.040 | Develop Project Team Learningware
|  | A.TR.050 | Conduct Project Team Learning Events | A.TR.060 | Train Project Team
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy
|  | B.TE.005.2 | Determine Testing Requirements
|  | B.TE.010 | Review Testing Strategy | B.TE.010 | Develop Test Strategy
|  | B.CV.020 | Review Data Acquisition, Conversion and Data Quality Strategy | B.DM.060 | Design Manual Migration Strategy
|  | B.DO.020 | Review Documentation Standards and Procedures
|  | B.TR.010.2 | Define Training Strategy
|  | B.TS.020.1 | Define Cutover Strategy | A.PM.010 B.PM.030 | Prepare Transition Strategy Develop Detailed Transition & Contingency Plan
B.ACT.DI Define Infrastructure
|  | B.TA.040 | Review Reporting and Information Access Strategy | A.MU.070 | Review Reporting Fit Analysis
|  | B.TA.050 | Review Disaster Recovery Strategy
|  | B.TA.060 | Review System Operations and Management Strategy
|  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | B.TA.080 | Review Backup and Recovery Strategy
|  | B.TA.090 | Develop Security and Control Strategy
| B.ACT.PEE Prepare Environments-Elaboration |  |  | A.MU.011 | Upgrade Project Environments
|  | B.IM.007.1 | Prepare Development Environment
|  | B.TE.018.1 | Prepare Static Test Data
|  | B.TE.038.1 | Prepare Integration Test Environment
|  | B.TE.060.1 | Prepare System Test Environment
|  | B.DO.040 | Prepare Documentation Environment
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Review Future Process Model
|  | B.RA.055.1 | Document Business Procedures
|  | B.MC.030 | Map Business Requirements | A.MU.020 | Remap Business Requirements
|  | B.TA.006 | Define Technical Prototype Subprojects | A.MA.110 | Define Technical Prototype Subprojects
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan
|  | B.TE.050.1 | Develop System Test Plan
|  | B.TE.080 | Develop Systems Integration Test Plan
|  | B.TE.082 | Develop Acceptance Test Plan
B.ACT.SSC Specify Software Configuration
|  | B.MC.010.2 | Review Business Data Structures | A.MU.030 | Remap Business Data
|  | B.MC.040 | Review Setup Information
|  | B.MC.055 | Document Application Configuration Changes | B.MU.110 | Revise Application Setups
|  | B.MC.060 | Review Functional Secruity | B.MU.120 | Revise Security Profiles
B.ACT.PGA Perform Gap Analysis
|  | B.MC.100 | Define and Estimate Application Extensions
|  | B.MC.110 | Define Gap Resolutions
B.ACT.DUCM Develop Use Case Model
|  | B.RA.023.2 | Review Use Case Model
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description
|  | B.DS.040.1 | Develop Design Architecture Description
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Review Use Case Details
B.ACT.AE Analyze - Elaboration
|  | B.AN.035.1 | Updated Existing Analysis Specification
B.ACT.DE Design - Elaboration
|  | B.DS.035.1 | Update Existing Design Specification | B.ME.060 | Identify Module Design Changes
|  | B.DS.050 | Review Design and Build Standards | B.ME.030 | Update Design & Build Standards
|  | B.DS.150.1 | Review Database Design | B.ME.050 | Identify Custom Database Changes
B.ACT.VUPE - Validate Upgrade Process - Elaboration
|  | B.TE.072.1 | Test Pre-Upgrade Steps | B.TE.085 | Test Pre-Upgrade Steps
|  | B.TE.073.1 | Test Packaged Software Upgrade | B.TE.091 | Test Software Upgrade
|  | B.TE.074.1 | Test Post-Upgrade Steps | B.TE.092 | Test Post-Upgrade Steps
|  | B.TE.075.1 | Perform Post-Upgrade Reconciliation Testing | B.TE.093 | Perform Post-Upgrade Reconciliation Testing
|  | B.TE.076.1 | Review Upgrade Test Results | B.TE.096 | Review Upgrade Test Results
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy
|  | B.PT.030 | Define Performance Testing Strategy
|  | B.PT.040 | Identify Performance Testing Models and Scenarios
|  | B.PT.050 | Design Performance Test Scripts and Programs
|  | B.PT.060 | Design Performance Test Data and Load Programs
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone
C Construction
C.ACT.AC Analyze - Construction
|  | C.AN.035.2 | Review Existing Analysis Specification
C.ACT.DC Design - Construction
|  | B.DS.035.1 | Update Existing Design Specification
|  | C.DS.150.2 | Review Database Design
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Review Unit Test Scripts
|  | C.TE.035.2 | Create Integration Test Scenarios
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios | B.TE.040 | Update System Test Scripts
C.ACT.DSITS Develop Systems Integration Test Scenarios
|  | C.TE.090 | Review Systems Integration Test Scenarios
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database Changes | B.ME.100 | Implement Database Changes
|  | C.IM.050 | Implement Components | B.ME.110 | Update Custom Modules
|  | C.IM.060.2 | Perform Component Review
|  | C.IM.070 | Assemble Components
|  | C.IM.090 | Create Installation Routines | B.ME.120 | Create Migration Routines
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test
|  | C.TE.040.2 | Perform Integration Test
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test
|  | C.RA.055.2 | Document Business Procedures
C.ACT.CSIT Conduct Systems Integration Test
|  | C.TE.100 | Perform Systems Integration Test | B.TE.130 | Perform Systems Integration Testing
C.ACT.PPT Prepare for Performance Testing
|  | C.PT.070 | Build Performance Test Scripts and Programs
|  | C.PT.080 | Construct Performance Test Environment and Database
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures | B.MA.190 B.DO.130 | Update System Management Procedures Update System Management Guide
|  | C.TA.110 | Define Operational Testing Plan
|  | C.TA.150 | Define Final Platform and Network Architecture | B.MA.140 B.MA.160 | Update Application Architecture Update Technical Architecture
|  | C.TA.160 | Review System Capacity Plan
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy
|  | C.TS.030 | Develop Installation Plan
|  | C.TS.040 | Review Production Support Infrastructure
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing
|  | C.TA.130 | Conduct Backup and Recovery Test
|  | C.TA.140 | Conduct Disaster Recovery Test
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping | B.DM.050 | Perform Migration Data Mapping
|  | C.RA.170.2 | Conduct Data Quality Assessment
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load)
|  | C.CV.040.2 | Design Conversion Components (Initial Load) | B.DM.070 | Design Migration Programs
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load) | B.DM.080 | Prepare Data Migration Test Plans
C.ACT.ACDC Acquire and Convert Data-Construction
|  | C.CV,030.2 | Prepare Conversion Environment (Initial Load)
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) | B.DM.090 | Develop Data Migration Programs
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | B.DM.100 | Perform Data Migration Unit Test
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | B.DM.110 | Perform Migration Business Object Test
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | B.DM.120 | Perform Data Migration Validation Test
|  | C.CV.064.1 | Install Conversion Components (Initial Load) | C.DM.130 | Install Data Migration Software
|  | C.CV.065.1 | Convert and Verify Data (Initial Load)
|  | C.CV.068.1 | Clean Data
C.ACT.VUPC - Validate Upgrade Process - Construction
|  | C.TE.072.1 | Test Pre-Upgrade Steps | B.TE.085 | Test Pre-Upgrade Steps
|  | C.TE.073.1 | Test Packaged Software Upgrade | B.TE.091 | Test Software Upgrade
|  | C.TE.074.1 | Test Post-Upgrade Steps | B.TE.092 | Test Post-Upgrade Steps
|  | C.TE.075.1 | Perform Post-Upgrade Reconciliation Testing | B.TE.093 | Perform Post-Upgrade Reconciliation Testing
|  | C.TE.076.1 | Review Upgrade Test Results | B.TE.096 | Review Upgrade Test Results
C.ACT.PD Produce Documentation
|  | C.DO.060 | Update User Reference Manual | B.DO.100 | Update User Reference Manual
|  | C.DO.070 | Update User Guide | B.DO.110 | Update User Guide
|  | C.DO.080 | Update Technical Reference Material | B.DO.120 | Update Technical Reference Manual
|  | C.DO.100 | Update Online Help | B.DO.140 | Update Online Help Text
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis
|  | C.TR.070 | Develop User Learning Plan
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | B.TR.070 | Develop User Training Materials
|  | C.TR.090 | Prepare User Learning Environment | C.TR.080 | Prepare User Training Environment
C.ACT.TEUC Train End Users - Construction
|  | C.TR.100.1 | Conduct User Learning Events | C.TR.090 | Train Users
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone
D Transition
D.ACT.SUAT Support User Acceptance Test
|  | D.TE.105 | Prepare Users for Testing | B.TE.100 | Prepare Key Users for Testing
|  | D.TE.110 | Prepare Acceptance Test Environment
|  | D.TE.120 | Support Acceptance Test | B.TE.055 B.TE.135 C.TE.140 | Update User Acceptance Test Scripts Perform User Acceptance Test, Production System Perform User Acceptance Testing, Test System
D.ACT.CPTST Conduct Performance Test
|  | D.PT.100 | Execute Performance Test
|  | D.PT.110 | Create Performance Test Report
D.ACT.PPE Prepare Production Environment
|  | TS.054 | Perform Pre-Upgrade Steps | C.PM.035 | Perform Pre-Upgrade Steps
|  | TS.055 | Upgrade Production Environment | C.PM.040 | Upgrade Production Environment
|  | TS.056 | Perform Post-Upgrade Steps | C.PM.045 | Perform Post-Upgrade Steps
|  | TS.057 | Revise Application Setups | C.PM.050 | Revise Application Setups
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load)
|  | D.CV.065.2 | Convert and Verify Data (Initial Load)
|  | D.CV.068.2 | Clean Data
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events | C.TR.090 | Train Users
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation
D.ACT.GP Go Production
|  | D.TS.058 | Verify Production Readiness | C.PM.070 | Verify Production Readiness
|  | D.TS.060 | Go Production | C.PM.080 | Commence Production
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management | D.PM.100 | Measure System Performance
E.ACT.EPS Evaluate Production System
|  | E.PS.010 | Audit System | D.PM.090 | Audit Production System
E.ACT.RPP Resolve Production Problems
|  | E.PS.050 | Analyze Problems
|  | E.PS.060 | Monitor and Respond to System Problems | D.PM.110 D.PM.120 | Maintain System Refine Production System
E.ACT.PF Plan for Future
|  | E.PS.135 | Determine Future Functional Enhancements
|  | E.PS.140 | Plan Enhancements
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone