## OUM to BPM Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | BPM Activity | BPM Task(s) | Mapping Notes
A Inception
A.ACT.GBRI Gather Business Requirements - Inception
|  | A.RD.001 | Detail Business and System Objectives | Architect the Solution | Business Requirements
|  | A.RD.005 | Create System Context Diagram | No direct mapping | No direct mapping
|  | A.RD.011.1 | Develop Future Process Model | No direct mapping | No direct mapping
|  | A.RD.020 | Obtain High-Level Business Descriptions | Analysis | Scope & Charter Document - Elicitation
|  | A.RA.015 | Develop Business Use Case Model | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document)
|  | A.RD.065 | Develop Domain Model (Business Entities) (Class Diagram) | Solutions Requirements | Conceptual Systems Design - Technical Architecture
|  | A.RD.012 | Document Present and Future Organization Structures | Analysis | Scope & Charter Document - Specification
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy | not applicable to BPM
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model | No direct mapping | No direct mapping | Optional - Based
|  | A.RD.034 | Document Current Business Baseline Metrics | No direct mapping | No direct mapping
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary | No direct mapping | No direct mapping
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW) | Propose the Solution | RFP-Consulting Service Proposal
|  | A.RD.055 | Detail Supplemental Requirements | No direct mapping | No direct mapping
|  | A.RD.130.1 | Develop Baseline Architecture Description | Solutions Requirements | Conceptual Systems Design - Technical Architecture
|  | A.RA.019 | Define Project Architecture | not applicable to BPM
|  | A.RA.023.1 | Develop Use Case Model | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document)
|  | A.RA.025.1 | Identify Candidate Services | not applicable to BPM
|  | A.RA.027.1 | Identify Candidate Business Rules | Architect the Solution | Architect the Solution/Business Requirements + Architect the Solution/BluePrint + Architect the Solution/BPMR (BPMR Overview Document) | Optional - In some cases the pre-sales consultants have done first iteration of this task
|  | A.RA.028.1 | Populate Business Rules Repository | Application Requirements | Scope & Charter Document - Verification
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification | Analysis | Scope & Charter Document - Specification
|  | A.RD.150.1 | Review Requirements Specification | Application Requirements | Scope & Charter Document - Verification
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype | Solution Requirements | Conceptual Systems Design | Sales cycle/SC demo.
|  | A.RA.030.1 | Validate Conceptual Prototype | Demo to Win |  | Sales cycle/SC demo. Activity level.
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements | Project Strategies | Data Conversion Strategy (document)
|  | A.TE.005.1 | Determine Testing Requirements | Project Strategies | Testing Strategy (document)
|  | A.PT.010 | Conduct Performance Management Workshop | No direct mapping | No direct mapping
|  | A.TA.010 | Conduct Technical Architecture Workshop | Solution Requirements | Technical Architecture, Conceptual Systems Design
|  | A.DO.010 | Define Documentation Requirements and Strategy | Manage Documents
|  | A.RD.070 | Determine Audit and Control Requirements | Propose the Solution | Proof of Concept (Demo)-Gather requirements for customization
A.ACT.SKSD Specify Key Structure Definition
|  | A.MC.010.1 | Define Business Data Structures | Architect the Solution | Architect the Solution/Business Requirements, Architect the Solution/BluePrint, Architect the Solution/BPMR (BPMR Overview Document)
|  | A.MC.020 | Define Business Data Structure Setups |  |  | Not executed in Inception but rather in Elaboration...Maybe executed here in the broadest terms (part of task RA.65.1)...Commonly referred to as "System Preferences" in DRM Hyperion (e.g. restricted characters in node name) + Console Configuration (# of web servers, web farm, data traffic management)…System preferences = functional control, and console configuration = system control
A.ACT.CMAHC Create and Manage Ad Hoc Communications
|  | A.OCM.010 | Create and Manage Ad Hoc Communications | No direct mapping | No direct mapping
A.ACT.CEAW Conduct Executive Alignment Workshop
|  | A.OCM.020 | Prepare for Executive Alignment Workshop | No direct mapping | No direct mapping
|  | A.OCM.030 | Conduct Executive Alignment Workshop | No direct mapping | No direct mapping
|  | A.OCM.040 | Build and Deploy Sponsorship Program | No direct mapping | No direct mapping
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy | Project Strategies | Training Strategy (document)
|  | A.TR.020 | Prepare Project Team Learning Plan | Project Strategies | Training Strategy (document)
|  | A.TR.030 | Prepare Project Team Learning Environment | Project Strategies | Training Strategy (document)
|  | A.TR.040 | Develop Project Team Learningware | Project Strategies | Training Strategy (document)
|  | A.TR.050 | Conduct Project Team Learning Events | Project Strategies | Training Strategy (document)
A.ACT.CAWI Conduct Alignment Workshops - Inception
|  | A.OCM.050 | Prepare for Team-Building Workshop | No direct mapping | No direct mapping
|  | A.OCM.060 | Conduct Team-Building Workshop | No direct mapping | No direct mapping
|  | A.OCM.070 | Design Managers Project Alignment Workshop | No direct mapping | No direct mapping
|  | A.OCM.080 | Conduct Managers Project Alignment Workshop | No direct mapping | No direct mapping
|  | A.OCM.090 | Design Change Agent Workshop | No direct mapping | No direct mapping
|  | A.OCM.100 | Conduct Change Agent Workshop | No direct mapping | No direct mapping
A.ACT.CCRA Conduct Change Readiness Assessment
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools | Configure Environment | No direct mapping
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data | No direct mapping | No direct mapping
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap | Manage Communication | n/a
A.ACT.DCMRCCI Deploy Change Management Roadmap and Communication Campaign - Inception
|  | A.OCM.140 | Develop Communication Campaign | Manage Communication | n/a
|  | A.OCM.150.1 | Conduct Change Management Roadmap and Communication Campaign | Manage Communication | n/a
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy | Project strategy | Implementation strategy (document) | For Hyperion engagements this is typically performed during the sales cycle and documented in the SOW/scoping document - This task is seen more as a touchpoint to this work by the sales force
|  | B.TE.005.2 | Determine Testing Requirements | Project Strategies | Testing Strategy (document)
|  | B.TE.010 | Develop Testing Strategy | Project Strategies | Testing Strategy (document)
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy | Project Strategies | Data Conversion Strategy (document)
|  | B.DO.020 | Define Documentation Standards and Procedures | Manage Documents
|  | B.TR.010.2 | Define Training Strategy | Project Strategies | Training Strategy (document)
|  | B.TS.020.1 | Define Cutover Strategy | Project Strategies | Implementation Strategy (document)
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy | Solution Requirements | Technical Architecture, Conceptual Systems Design
|  | B.TA.030 | Define Integration Requirements and Strategy | Design Preparation | Architectural Foundation
|  | B.TA.040 | Define Reporting and Information Access Strategy | Solution Requirements | Conceptual Systems Design
|  | B.TA.050 | Define Disaster Recovery Strategy | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
|  | B.TA.060 | Define System Operations and Management Strategy | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
|  | B.TA.070 | Define Initial Architecture and Application Mapping | Solution Requirements | Conceptual Systems Design
|  | B.TA.080 | Define Backup and Recovery Strategy | Solution Requirements + Supporting Documentation | Solution Requirements/Conceptual Systems Design
|  | B.TA.090 | Develop Security and Control Strategy | Solution Requirements | Solution Requirements/Conceptual Systems Design
B.ACT.PEE Prepare Environments-Elaboration
|  | B.IM.007.1 | Prepare Development Environment | Configure Environment |  | Activity level
|  | B.TE.018.1 | Prepare Static Test Data |  |  | Done by customer or use existing customer data for testing - Very seldom directly addressed by implementation team
|  | B.TE.038.1 | Prepare Integration Test Environment |  |  | Done by customer.
|  | B.TE.060.1 | Prepare System Test Environment |  |  | Done by customer; initial creation of the environment maybe done by the "Infrastructure" team.
|  | B.CV.030.1 | Prepare Conversion Environment (Initial Load) | Project Strategies | Data Conversion Strategy (document)
|  | B.DO.040 | Prepare Documentation Environment |  |  | Use existing customer environment.
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Develop Future Process Model | No direct mapping | No direct mapping | Optional
|  | B.RA.055.1 | Document Business Procedures | Solutions Requirements | Conceptual Systems Design - Technical Architecture
|  | B.MC.030 | Map Business Requirements | No direct mapping | No direct mapping
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan | Executive Planning | Testing Plan
|  | B.TE.050.1 | Develop System Test Plan | Executive Planning | Testing Plan | Customer would often do this
|  | B.TE.080 | Develop Systems Integration Test Plan | Executive Planning | Testing Plan
|  | B.TE.082 | Develop Acceptance Test Plan | Executive Planning | Testing Plan
B.ACT.SSC Specify Software Configuration
|  | B.MC.010.2 | Define Business Data Structures | Solutions Requirements | Conceptual Systems Design - Technical Architecture | True in some cases -- must confirm.
|  | B.MC.040 | Gather Setup Information
|  | B.MC.050.1 | Define Application Setups | Solutions Requirements | Conceptual Systems Design - Technical Architecture | This task includes work defined in RA.045...Commonly referred to as "System Preferences" in DRM Hyperion (e.g. restricted characters in node name) + Console Configuration (# of web servers, web farm, data traffic management)…System preferences = functional control, and console configuration = system control
|  | B.MC.055 | Document Application Configuration Changes
|  | B.MC.060 | Document Functional Security
B.ACT.PVC Prorotype and Validate Configuration
|  | B.TE.025.1 | Create System Test Scenarios | Executive Planning | Testing Plan
|  | B.MC.070 | Prepare Configuration Prototype Environment
|  | B.MC.080 | Conduct Configuration Prototyping Workshop
|  | B.MC.090.2 | Conduct Reporting Fit Analysis | No direct mapping | No direct mapping
B.ACT.PGA Perform Gap Analysis
|  | B.MC.100 | Define and Estimate Application Extensions | No direct mapping | No direct mapping
|  | B.MC.110 | Define Gap Resolutions | No direct mapping | No direct mapping
B.ACT.DUCM Develop Use Case Model
|  | B.RA.023.2 | Develop Use Case Model | Application Requirements | Scope & Charter Document
B.ACT.CCPE Create Conceptual Prototype - Elaboration
|  | B.IM.005.2 | Develop Conceptual Prototype | Solution Requirements | Conceptual Systems Design | Sales cycle/SC demo.
|  | B.RA.030.2 | Validate Conceptual Prototype | Demo to Win |  | Sales cycle/SC demo. Activity level.
B.ACT.CS Consolidate Specification
|  | B.RD.042.2 | Develop Glossary | No direct mapping | No direct mapping
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW) | Analysis | Scope & Charter Document
|  | B.RD.140.2 | Create Requirements Specification | Analysis | Scope & Charter Document
|  | B.RD.150.2 | Review Requirements Specification | Exit Gate | Exit Gate/Acceptance Criteria, Exit Gate/Approval to Proceed
|  | B.RA.025.2 | Identify Candidate Services | not applicable to BPM
|  | B.RA.027.2 | Identify Candidate Business Rules | Application Requirements | Scope & Charter Document - Verification
|  | B.RA.028.2 | Populate Business Rules Repository | No direct mapping | No direct mapping
|  | B.RA.180.1 | Review Use Case Model | No direct mapping | No direct mapping
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description | Solutions Requirements | Conceptual Systems Design - Technical Architecture
|  | B.AN.040.1 | Develop Analysis Architecture Description
|  | B.DS.040.1 | Develop Design Architecture Description | Design preparation | Architectural Foundation
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details | Application Requirements | Scope & Charter Document
B.ACT.AE Analyze - Elaboration
|  | B.AN.050.1 | Analyze Data | Architect the solution | No direct mapping | Optional
|  | B.AN.060.1 | Analyze Behavior | Architect the solution | No direct mapping | Optional
|  | B.AN.070.1 | Analyze Business Rules | Architect the solution | No direct mapping | Look specifically at example 3 (Data-Related Rules, and Workflow/process-Related, and Security Rules
|  | B.AN.080.1 | Analyze Services | not applicable to BPM
|  | B.AN.085.1 | Define Service | not applicable to BPM
|  | B.RA.026.1 | Populate Services Repository | not applicable to BPM
|  | B.AN.090.1 | Analyze User Interface | Architect the solution | No direct mapping | Optional
|  | B.AN.100.1 | Prepare Analysis Specification | Architect the solution | No direct mapping | Optional
|  | B.AN.110.1 | Review Analysis Model | Architect the solution | No direct mapping | Optional
B.ACT.DE Design - Elaboration
|  | B.DS.050 | Determine Design and Build Standards | Design Preparation | Standards and Guidelines
|  | B.DS.060 | Define Business Rules Implementation Strategy | Project strategies |  | For Hyperion engagements this task and all the other tasks within the B.ACT.ADE activity are performed as one (i.e., activity)
|  | B.DS.070 | Define SOA Implementation Strategy | not applicable to BPM
|  | B.DS.080.1 | Design Software Components | Solution Design | Integration architecture - technical architecture | When customizations exist (I.e. non Oracle/Hyperion tech)
|  | B.DS.090.1 | Design Data | Project strategies
|  | B.DS.100.1 | Design Behavior | Design preparation | Design Preparation/Architectural Foundation + Design Preparation/Common Elements
|  | B.DS.110.1 | Design Business Rules | Project strategies |  | For Hyperion engagements this task and all the other tasks within the B.ACT.ADE activity are performed as one (i.e., activity)
|  | B.DS.120.1 | Design Services | not applicable to BPM
|  | B.DS.130.1 | Design User Interface
|  | B.DS.140.1 | Prepare Design Specification | Solution Design | Solution Design Review
|  | B.DS.150.1 | Develop Database Design | Application Design | Application Design/Consolidation (App design) + Application Design/Enterprise Planning (App design) + Application Design/Management Reporting (App design) | Not designing traditional relational DB, but rather designing cubes for multi-dimensional
|  | B.DS.160.1 | Review Design Model | Solution Design | Solution Design Review
B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration
|  | B.TE.020.1 | Develop Unit Test Scripts |  |  | Internal - not customer facing. Not needed in some cases.
|  | B.TE.035.1 | Create Integration Test Scenarios | Implementation Planning | Construct "Testing" programs | Commonly referred to as text scripts, which are sometimes used in the system and user testing of Hyperion (depends on Hyperion application)
B.ACT.DSTSE Develop System Test Scenarios – Elaboration
|  | B.TE.025.2 | Create System Test Scenarios | Executive Planning | Testing Plan
B.ACT.DVCSP Develop and Validate Custom Software Prototypes
|  | B.IM.010 | Develop Functional Prototype | Exit Gate | Conference Room Pilot-S/ware demo
|  | B.RA.085 | Validate Functional Prototype | No direct mapping | No direct mapping | Optional based on customer scenario
|  | B.IM.020 | Develop Architectural Foundation | Exit Gate | Conference Room Pilot-S/ware demo | Optional - When it is performed, the task is performed at the activity level (develop prototypes). This is typically shown to the customer in the pre-sale cycle. The result of this pre-sale work would be documented. This would only occur here if something really changed since pre-sale
|  | B.IM.085 | Develop User Interface Standards Prototype | Exit Gate | Conference Room Pilot-S/ware demo
|  | B.RA.095 | Validate User Interface Standards Prototype | No direct mapping | No direct mapping | This is executed at the activity level, and it is very much high-level at this phase
|  | B.IM.040.1 | Implement Database | Exit Gate | Conference Room Pilot-S/ware demo | See out sort key 152 - Creating database means creating initial chart-of-accounts / master data hierarchy
|  | B.IM.053.1 | Register Services | not applicable to BPM
|  | B.IM.055.1 | Perform Business Rules Implementation (Rules Engine) |  |  | define rules
|  | B.IM.060.1 | Perform Component Review | Application Design, Integration Architecture | Application Design/Application Design Review, Integration Architecture/Solution Design Review | Optional - When done, for Hyperion this task is typically executed at an activity level, and is also very much a high-level prototype
B.ACT.PCCTE Perform Custom Component Testing - Elaboration
|  | B.TE.030.1 | Perform Unit Test | Test Execution | Integration Testing
|  | B.TE.040.1 | Perform Integration Test | No direct mapping | No direct mapping | if applicable
B.ACT.PSTE Perform System Test – Elaboration
|  | B.TE.070.1 | Perform System Test | Solution Design | Configure Environment
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy | Project Strategies | Testing Strategy (document)
|  | B.PT.030 | Define Performance Testing Strategy | Executive Planning | Testing Plan
|  | B.PT.040 | Identify Performance Testing Models and Scenarios | No direct mapping | No direct mapping
|  | B.PT.050 | Design Performance Test Scripts and Programs | Implementation Planning | Construct "Testing" programs | Optional for Hyperion DRM
|  | B.PT.060 | Design Performance Test Data and Load Programs | Implementation Planning | Construct "Testing" programs | Typically managed and delivered at activity level
B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration
|  | B.CV.025 | Define Data Acquisition and Conversion Standards | Executive Planning | Data Conversion Plan
|  | B.RA.160 | Conduct Business Data Source Gap Analysis | No direct mapping | No direct mapping
|  | B.CV.027.2 | Perform Data Mapping | Analysis | No direct mapping
|  | B.RA.170.2 | Conduct Data Quality Assessment | No direct mapping | No direct mapping | Performed at the metadata level for DRM applications
|  | B.CV.035.2 | Define Manual Conversion Procedures (Initial Load) | Project Strategies | Data Conversion Strategy (document)
|  | B.CV.040.2 | Design Conversion Components (Initial Load) | Project Strategies | Data Conversion Strategy (document)
|  | B.CV.050.2 | Prepare Conversion Test Plans (Initial Load) | Executive Planning | Testing Plan
|  | B.CV.055.2 | Implement Conversion Components (Initial Load) | Build Solution | Integration - data conversion
|  | B.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | No direct mapping | No direct mapping
|  | B.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | No direct mapping | No direct mapping
|  | B.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | No direct mapping | No direct mapping
B.ACT.PBPII Prepare Business Process Impace Inventory
|  | B.OCM.160 | Prepare Business Process Impace Inventory | No direct mapping | No direct mapping
B.ACT.DCMRCCE Deploy Change Management Roadmap and Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap and Communication Campaign | Manage Communication | n/a
|  | B.OCM.155.1 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Manage Communication | n/a
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary | No direct mapping | No direct mapping
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW) | Analysis | Scope & Charter Document
|  | C.RD.130.2 | Develop Baseline Architecture Description | No direct mapping | No direct mapping
|  | C.RA.023.3 | Develop Use Case Model | No direct mapping | No direct mapping
|  | C.RA.024.2 | Develop Use Case Details | No direct mapping | No direct mapping
|  | C.RA.025.3 | Identify Candidate Services
|  | C.RA.027.3 | Identify Candidate Business Rules | No direct mapping | No direct mapping | This occurs via the Project Scope and Charter Document
|  | C.RA.028.3 | Populate Business Rules Repository | No direct mapping | No direct mapping |  | Y
|  | C.RA.180.2 | Review Use Case Model | No direct mapping | No direct mapping
C.ACT.AC Analyze - Construction
|  | C.AN.040.2 | Develop Analysis Architecture Description
|  | C.AN.050.2 | Analyze Data | Analysis/Solution Requirements | Conceptual System Design
|  | C.AN.060.2 | Analyze Behavior | Analysis/Solution Requirements | Conceptual System Design
|  | C.AN.070.2 | Analyze Business Rules | Analysis/Application Requirements | Scope and Charter Document | Look specifically at example 3 (Data-Related Rules, and Workflow/process-Related, and Security Rules
|  | C.AN.080.2 | Analyze Services | not applicable to BPM
|  | C.AN.085.2 | Define Service | not applicable to BPM
|  | C.RA.026.2 | Populate Services Repository | not applicable to BPM
|  | C.AN.090.2 | Analyze User Interface | Analysis/Solution Requirements | Conceptual System Design
|  | C.AN.100.2 | Prepare Analysis Specification | Analysis/Exit Gate | Approval to Proceed | Finalizing, which may be just a check
|  | C.AN.110.2 | Review Analysis Model | Analysis/Exit Gate | Approval to Proceed | Finalizing, which may be just a check
C.ACT.DC Design - Construction
|  | C.DS.040.2 | Develop Design Architecture Description | Solution Design | Integration architecture - technical architecture
|  | C.DS.080.2 | Design Software Components | Solution Design | Integration architecture - technical architecture | When customizations exist (I.e. non Oracle/Hyperion tech), Solution Design, Integration architecture, technical architecture when customizations exist (I.e. non Oracle/Hyperion tech),
|  | C.DS.090.2 | Design Data | Design Preparation | Common Elements
|  | C.DS.100.2 | Design Behavior | Integration Architecture | Solution Design Review-Create Solution Design Document
|  | C.DS.110.2 | Design Business Rules | Integration Architecture | Solution Design Review-Create Solution Design Document | Optional - In most cases not necessary for another iteration of this task…done in .1 version
|  | C.DS.120.2 | Design Services | not applicable to BPM
|  | C.DS.130.2 | Design User Interface | Design Preparation | Common Elements
|  | C.DS.140.2 | Prepare Design Specification | Application Design | Application Design Review | Activity level
|  | C.DS.150.2 | Develop Database Design | Application Design |  | Not designing traditional relational DB, but rather designing cubes for multi-dimensional, or designing non-OLAP applications (e.g. DRM)
|  | C.DS.160.2 | Review Design Model | Application Design | Application Design Review | Activity level
C.ACT.PTP Perform Test Planning
|  | C.TE.015.2 | Develop Integration Test Plan | No direct mapping | No direct mapping
|  | C.TE.050.2 | Develop System Test Plan | No direct mapping | No direct mapping
C.ACT.PEC Prepare Environments - Construction
|  | C.IM.007.2 | Prepare Development Environment | Configure Environment |  | Activity level
|  | C.TE.018.2 | Prepare Static Test Data |  |  | Optional, generally "Actuals" data from a known period is used.
|  | C.TE.038.2 | Prepare Integration Test Environment | not applicable to BPM
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Develop Unit Test Scripts | No direct mapping | No direct mapping
|  | C.TE.035.2 | Create Integration Test Scenarios | Test Cases | Manage test cases
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios | No direct mapping | No direct mapping
C.ACT.DSITS Develop Systems Integration Test Scenarios
|  | C.TE.090 | Develop Systems Integration Test Scenarios | No direct mapping | No direct mapping
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database | (Construct) Application |  | For Hyperion it is more appropriate to use term creating application versus creating database, but yes task is performed
|  | C.IM.050 | Implement Components | Integration - data conversion, (Construct) Data Stores |  | Activity level
|  | C.IM.053.2 | Register Services | not applicable to BPM
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine) | not applicable to BPM
|  | C.IM.060.2 | Perform Component Review | Application Design + Integration Architecture | Application Design/Application Design Review + Integration Architecture/Solution Design Review | Optional - When done, for Hyperion this task is typically executed at an activity level
|  | C.IM.070 | Assemble Components | Integration - data conversion + (Construct) Data Stores |  | Activity level
|  | C.IM.080 | Integrate Services | Integration - data conversion + (Construct) Data Stores |  | Activity level
|  | C.IM.090 | Create Installation Routines | No direct mapping | No direct mapping
|  | C.TE.065 | Perform Installation Test | No direct mapping | No direct mapping
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test | Test Execution | Integration Testing
|  | C.TE.040.2 | Perform Integration Test | Test Execution | Test Execution/System Testing, Test Execution/Acceptance Testing
C.ACT.PST Prepare for System Test
|  | C.MC.050.2 | Define Application Setups | No direct mapping | No direct mapping | Optional
|  | C.TE.060.2 | Prepare System Test Environment | No direct mapping | No direct mapping
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test | Test Execution | System Testing
|  | C.RA.055.2 | Document Business Procedures | No direct mapping | No direct mapping
|  | C.TE.019.1 | Collect, Assess and Refine KPI Measurements
C.ACT.PSIT Perform Systems Integration Test
|  | C.TE.085 | Prepare Systems Integration Test Environment | No direct mapping | No direct mapping | Optional - Hyperion typically has 3 environments (Dev, Test, Prod)
|  | C.TE.100 | Perform Systems Integration Test | Test Execution | System Testing
C.ACT.PPT Prepare for Performance Testing
|  | C.PT.070 | Build Performance Test Scripts and Programs | Implementation Planning | Construct "Testing" programs
|  | C.PT.080 | Construct Performance Test Environment and Database | Implementation Planning | Construct "Testing" programs
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal | No direct mapping | No direct mapping
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures | Supporting Documentation
|  | C.TA.110 | Define Operational Testing Plan | Test Cases | Manage Test Cases
|  | C.TA.150 | Define Final Platform and Network Architecture | No direct mapping | No direct mapping
|  | C.TA.160 | Define System Capacity Plan | Project Strategies | Implementation Strategy (document)
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy | Executive Planning | Implementation Plan
|  | C.TS.030 | Develop Installation Plan | Implementation Planning | Implementation Planning/Construct "Testing" programs, Implementation Planning/Construct "Implementation" programs, Implementation Planning/Construct "Training" material, Implementation Planning/Construct "Data conversion" programs
|  | C.TS.040 | Design Production Support Infrastructure | not applicable to BPM
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing | Test Execution | System Testing
|  | C.TA.130 | Conduct Backup and Recovery Test | Test Execution | System Testing
|  | C.TA.140 | Conduct Disaster Recovery Test | Test Execution | System Testing
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping | No direct mapping | No direct mapping
|  | C.RA.170.2 | Conduct Data Quality Assessment | No direct mapping | No direct mapping
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load) | No direct mapping | No direct mapping
|  | C.CV.040.2 | Design Conversion Components (Initial Load) | No direct mapping | No direct mapping
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load) | No direct mapping | No direct mapping
C.ACT.ACDC Acquire and Convert Data-Construction
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) | not applicable to BPM
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) | Implementation Planning | Construct "Data conversion" programs
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) | No direct mapping | No direct mapping
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) | No direct mapping | No direct mapping
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) | No direct mapping | No direct mapping
|  | C.CV.064.1 | Install Conversion Components (Initial Load) | Build Solution | Integration - data conversion
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) | Build Solution | Integration - data conversion
|  | C.CV.068.1 | Clean Data | Build Solution | (Construct) Data Stores
C.ACT.PD Produce Documentation
|  | C.DO.060 | Publish User Reference Manual | Supporting Documentation | Create "Application Maintenance" Doc
|  | C.DO.070 | Publish User Guide | Supporting Documentation | Create "End User" Manual
|  | C.DO.080 | Publish Technical Reference Material | Technical Architecture, Supporting Documentation, Solution Requirements | Technical Architecture/Create the Technical Architecture Design Document + Supporting Documentation/Create "Disaster Recovery" Doc + Solution Requirements/Conceptual Systems Design
|  | C.DO.100 | Produce Online Help | No direct mapping | No direct mapping | Possibly yes for customizations
C.ACT.DCMRCCC Deploy Change Management Roadmap and Communication Campaign - Construction
|  | C.OCM.150.3 | Conduct Change Management Roadmap and Communication Campaign | Manage Communication | n/a
|  | C.OCM.155.2 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Manage Communication | n/a
C.ACT.CJIA Conduct Job Impact Analysis
|  | C.OCM.170 | Collect and Analyze Job Change Data | No direct mapping | No direct mapping
|  | C.OCM.180 | Determine Impact of Job Changes | No direct mapping | No direct mapping
|  | C.OCM.190 | Prepare HR Transition Plan | No direct mapping | No direct mapping
C.ACT.CMAWC Conduct Managers Alignment Workshop - Construction
|  | C.OCM.200 | Design Managers Unit and Department Impact Workshop | No direct mapping | No direct mapping
|  | C.OCM.210 | Conduct Managers Unit and Department Impact Workshop | No direct mapping | No direct mapping
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis | Executive Planning | Training Plan
|  | C.TR.070 | Develop User Learning Plan | Executive Planning | Training Plan
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | Implementation Planning | Construct "Training" material
|  | C.TR.090 | Prepare User Learning Environment | No direct mapping | No direct mapping
C.ACT.TEUC Train End Users - Construction
|  | C.TR.100.1 | Conduct User Learning Events | not applicable to BPM
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone
D Transition
D.ACT.SUAT Support User Acceptance Test
|  | D.TE.105 | Prepare Users for Testing | No direct mapping | No direct mapping
|  | D.TE.110 | Prepare Acceptance Test Environment | No direct mapping | No direct mapping
|  | D.TE.120 | Support Acceptance Test | Test Execution | Acceptance Testing
D.ACT.CPTST Conduct Performance Test
|  | D.PT.100 | Execute Performance Test | Test Execution
|  | D.PT.110 | Create Performance Test Report | Exit Gate | Solution Test Review
D.ACT.PPE Prepare Production Environment
|  | D.TS.050 | Prepare Production Environment | No direct mapping | No direct mapping
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load) | No direct mapping | No direct mapping
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) | No direct mapping | No direct mapping
|  | D.CV.068.2 | Clean Data | not applicable to BPM
D.ACT.DCMRCCT Deploy Change Management Roadmap and Communication Campaign - Transition
|  | D.OCM.150.4 | Conduct Change Management Roadmap and Communication Campaign | Manage Communication | n/a
|  | D.OCM.155.3 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Manage Communication | n/a
D.ACT.CITA Conduct IT Alignment
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups | No direct mapping | No direct mapping
|  | D.OCM.230 | Prepare IT Transition Plan | No direct mapping | No direct mapping
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events | Implementation Preparation | Perform Training | Optional
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation | No direct mapping | No direct mapping
D.ACT.GP Go Production
|  | D.TS.052 | Implement Production Support Infrastructure | not applicable to BPM
|  | D.TS.058 | Verify Production Readiness | Implementation Preparation | Go-Live Checkpoint | This could be nothing more than a quick checklist
|  | D.TS.060 | Go Production | Roll-Out, Exit Gate | Roll-Out/Implement Solution, Roll-Out/Monitor Solution, Roll-Out/Transition to Support, Exit Gate/Solution Review, Exit Gate/Final Approval, Exit Gate/Post Implementation Review
|  | D.TS.070 | Shut Down Legacy System | No direct mapping | No direct mapping
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management | No direct mapping | No direct mapping
E.ACT.EPS Evaluate Production System
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements
|  | E.PS.010 | Audit System | Exit Gate | Post Implementation Review
E.ACT.RPP Resolve Production Problems
|  | E.PS.050 | Analyze Problems | Support for Success
|  | E.PS.060 | Monitor and Respond to System Problems | Support for Success
E.ACT.DCMRCCP Deploy Change Management Roadmap and Communication Campaign - Production
|  | E.OCM.150.5 | Conduct Change Management Roadmap and Communication Campaign | Manage Communication | n/a
|  | E.OCM.155.4 | Monitor Change Management Roadmap and Communication Campaign Effectiveness | Manage Communication | n/a
E.ACT.PF Plan for Future
|  | E.PS.135 | Determine Future Functional Enhancements | Exit Gate | Post Implementation Review
|  | E.PS.140 | Plan Enhancements | Exit Gate | Post Implementation Review
|  | E.OCM.250 | Measure Organizational Change Effectiveness | Implementation Preparation | Perform Training
E.ACT.DITTP Deploy IT Transition Plan
|  | E.OCM.260 | Implement IT Transition Plan | No direct mapping | No direct mapping
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone