## OUM to OneMethodology Mapping
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | COMPARABLE ONEMETHODOLOGY ACTIVITY
A Inception
A.ACT.GBRI Gather Business Requirements - Inception
|  | A.RD.001 | Detail Business and System Objectives
|  | A.RD.003 | Identify Viewpoints
|  | A.RD.005 | Create System Context Diagram | Model Company Workshop Business Integration Modeling Workshop
|  | A.RD.011.1 | Develop Future Process Model | Model Company Workshop Business Integration Modeling Workshop Advanced Planning Solution Analysis Workshop AOC Solution Analysis Workshop XPI Solution Analysis Workshop
|  | A.RD.020 | Obtain High-Level Business Descriptions
|  | A.RA.010 | Simulate Business Process
|  | A.RA.015 | Develop Business Use Case Model
|  | A.RD.065 | Develop Domain Model (Business Entities) (Class Diagram)
|  | A.RD.012 | Document Present and Future Organization Structures | Financial Action Lab
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy | Business Performance Measurement Workshop
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model
|  | A.RD.034 | Document Current Business Baseline Metrics | Business Performance Baseline Workshop
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW)
|  | A.RD.055 | Detail Supplemental Requirements | Disaster Recovery Planning Workshop
|  | A.RD.130.1 | Develop Baseline Architecture Description | Technology Architecture Design Workshop*
|  | A.RA.019 | Define Project Reference Architecture
|  | A.RA.021.1 | Capture User Stories
|  | A.RA.023.1 | Develop Use Case Model
|  | A.RA.025.1 | Identify Candidate Services
|  | A.RA.027.1 | Identify Candidate Business Rules
|  | A.RA.028.1 | Populate Business Rules Repository
A.ACT.PSUIA Perform Software Upgrade Impact Analysis
|  | A.TA.004 | Perform Technical Architecture Impact Analysis | Upgrade Planning Workshop Platform Conversion Planning Workshop
|  | A.RD.134 | Identify new Software Release Changes | Upgrade Planning Workshop
|  | A.RD.136 | Perform Custom Extension Impact Analysis
|  | A.RD.138 | Perform Data Impact Analysis
|  | A.MC.090.1 | Conduct Reporting Fit Analysis
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification
|  | A.RD.150.1 | Review Requirements Specification
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype
|  | A.RA.030.1 | Validate Conceptual Prototype
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements | Data Conversion & Batch Interface Methodology Workshop Data Conversion Scope Workshop Batch Interface Scope Workshop
|  | A.TE.005.1 | Determine Testing Requirements
|  | A.PT.010 | Conduct Performance Management Workshop | Performance Management Workshop*
|  | A.TA.010 | Conduct Technical Architecture Workshop | Technology Scope Workshop Technology Architecture Design Workshop* Technology Architecture Workshop
|  | A.DO.010 | Define Documentation Requirements and Strategy | UDT Strategy Workshop UDT Detailed Design Workshop
|  | A.RD.070 | Determine Audit and Control Requirements
A.ACT.SKSD Specify Key Structure Definition
|  | A.MC.010.1 | Define Business Data Structures | Financial Action Lab Inventory Action Lab
|  | A.MC.020 | Define Business Data Structure Setups | Financial Action Lab Inventory Action Lab
A.ACT.CMAHC Create and Manage Ad Hoc Communications
|  | A.OCM.010 | Create and Manage Ad Hoc Communications
| A.ACT.CEAW Conduct Executive Alignment Workshop |  |  | Change Management Workshop (Recurring) Technology Change Management Workshop
|  | A.OCM.020 | Prepare for Executive Alignment Workshop
|  | A.OCM.030 | Conduct Executive Alignment Workshop
|  | A.OCM.040 | Build and Deploy Sponsorship Program
A.ACT.TPT Train Project Team
|  | A.TR.010.1 | Define Training Strategy
|  | A.TR.020 | Prepare Project Team Learning Plan
|  | A.TR.030 | Prepare Project Team Learning Environment
|  | A.TR.040 | Develop Project Team Learningware
|  | A.TR.050 | Conduct Project Team Learning Events | Project Team Education Workshop - Process Testing Solution Overview Education Workshop Project Team Education Workshop - Set-up Project Team Education Workshop - Modeling Project Team Education Workshop - Report Writing Project Team Education Workshop - Methodology
A.ACT.CAWI Conduct Alignment Workshops - Inception
|  | A.OCM.050 | Prepare for Team-Building Workshop
|  | A.OCM.060 | Conduct Team-Building Workshop
|  | A.OCM.070 | Design Managers' Project Alignment Workshop
|  | A.OCM.080 | Conduct Managers' Project Alignment Workshop
|  | A.OCM.090 | Design Change Agent Workshop
|  | A.OCM.100 | Conduct Change Agent Workshop
A.ACT.CCRA Conduct Change Readiness Assessment
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap
A.ACT.DCMRCCI Deploy Change Management Roadmap / Communication Campaign - Inception
|  | A.OCM.140 | Develop Communication Campaign
|  | A.OCM.150.1 | Conduct Change Management Roadmap / Communication Campaign
A.ACT.LCOB Lifecycle Objective Milestone Summary
|  | A.PMC.LCOB | Lifecycle Object Milestone
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy | Modification Scope Workshop
|  | B.TE.005.2 | Determine Testing Requirements
|  | B.TE.010 | Develop Testing Strategy
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy | Data Conversion & Batch Interface Methodology Workshop
|  | B.DO.020 | Define Documentation Standards and Procedures | User Documentation and Training Strategy Workshop
|  | B.TR.010.2 | Define Training Strategy | User Documentation and Training Strategy Workshop
|  | B.TS.020.1 | Define Cutover Strategy
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy | Technology Architecture Design Workshop*
|  | B.TA.030 | Define Integration Requirements and Strategy
|  | B.TA.040 | Define Reporting and Information Access Strategy
|  | B.TA.050 | Define Disaster Recovery Strategy | High Availability Workshop Disaster Reccovery Planning Workshop
|  | B.TA.060 | Define System Operations and Management Strategy | Enterprise Management Workshop System Administration Workshop* Operations Support Workshop
|  | B.TA.070 | Define Initial Architecture and Application Mapping
|  | B.TA.080 | Define Backup and Recovery Strategy
|  | B.TA.090 | Develop Security and Control Strategy | Security Action Lab* Security Workshop - ERP Security Workshop - APS Security Workshop - XPI Security Workshop - CRM Security Workshop - AOC Security Workshop - BI
B.ACT.PEE Prepare Environments-Elaboration
|  | B.IM.007.1 | Prepare Development Environment | Installation Workshop*
|  | B.TE.018.1 | Prepare Static Test Data
|  | B.TE.038.1 | Prepare Integration Test Environment | Installation Workshop*
|  | B.TE.060.1 | Prepare System Test Environment | Installation Workshop*
|  | B.CV.030.1 | Prepare Conversion Environment (Initial Load) | Installation Workshop*
|  | B.DO.040 | Prepare Documentation Environment | UDT Train the Documenter Workshop
B.ACT.GBRE Gather Business Requirements - Elaboration
|  | B.RD.011.2 | Develop Future Process Model | Detailed Process Modeling Workshop*
|  | B.RA.055.1 | Document Business Procedures
|  | B.MC.030 | Map Business Requirements | Business Process Gap Analysis Workshop CRM Gap Analysis Workshop
|  | B.TA.006 | Define Technical Prototype Subprojects
B.ACT.DTP Develop Test Plans
|  | B.TE.015.1 | Develop Integration Test Plan
|  | B.TE.050.1 | Develop System Test Plan
|  | B.TE.080 | Develop Systems Integration Test Plan
|  | B.TE.082 | Develop Acceptance Test Plan
B.ACT.SSC Specify Software Configuration
|  | B.MC.010.2 | Define Business Data Structures | Action Labs* Advanced Stock Valuation Workshop
|  | B.MC.040 | Gather Setup Information
|  | B.MC.050.1 | Define Application Setups | ERP Configurator Workshop (system code 32)..* Advanced Transportation Workshop ..* Advanced Warehouse Workshop ..* Demand Forecasting Workshop..* Batch Processing Workshop* AOC Development Workshop Application Configuration Workshop*
|  | B.MC.055 | Document Application Configuration Changes
|  | B.MC.060 | Document Functional Security
B.ACT.PVC Prototype and Validate Configuration
|  | B.TE.025.1 | Create System Test Scenarios
|  | B.MC.070 | Prepare Configuration Prototype Environment
|  | B.MC.080 | Conduct Configuration Prototyping Workshop
|  | B.RA.090.2 | Conduct Reporting Fit Analysis | Advanced Reporting Workshop - Configure Phase Print Management Action Lab* Print Management Workshop* Forms Action Lab
B.ACT.PFG Perform Fit Gap
|  | B.MC.100 | Define and Estimate Application Extensions
|  | B.MC.110 | Define Gap Resolutions
B.ACT.DUCM Develop Use Case Model
|  | B.RA.021.2 | Capture User Stories
|  | B.RA.023.2 | Develop Use Case Model
C.ACT.CCPE Create Conceptual Prototype - Elaboration
|  | B.IM.005.2 | Develop Conceptual Prototype
|  | B.RA.030.2 | Validate Conceptual Prototype
| B.ACT.CS Consolidate Specification |  |  | Localization Strategy Workshop
|  | B.RD.042.2 | Develop Glossary
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW)
|  | B.RD.140.2 | Create Requirements Specification
|  | B.RD.150.2 | Review Requirements Specification
|  | B.RA.025.2 | Identify Candidate Services
|  | B.RA.027.2 | Identify Candidate Business Rules
|  | B.RA.028.2 | Populate Business Rules Repository
|  | B.RA.180.1 | Review Use Case Model
| B.ACT.BSA Baseline Software Architecture |  |  | Technology Architecture Design WS
|  | B.RA.035 | Develop High-Level Software Architecture Description
|  | B.AN.040.1 | Develop Analysis Architecture Description
|  | B.DS.040.1 | Develop Design Architecture Description
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details
| B.ACT.AE Analyze - Elaboration |  |  | Model and Build PDP Interfaces Workshop AOC Design Workshop Model and Build PS-D Interfaces Workshop Model and Build Demand Consensus Interfaces Workshop Model and Build SNO Interfaces Workshop Model and Build Order Promising Interfaces Workshop Model and Build PS-P Interfaces Workshop CRM Custom Design & Code Workshop
|  | B.AN.035.1 | Update Existing Analysis Specification
|  | B.AN.050.1 | Analyze Data | Business Intelligence Workshop
|  | B.AN.060.1 | Analyze Behavior
|  | B.AN.070.1 | Analyze Business Rules
|  | B.AN.080.1 | Analyze Services
|  | B.AN.085.1 | Define Service
|  | B.RA.026.1 | Populate Services Repository
|  | B.AN.090.1 | Analyze User Interface | Presentation Layer Workshop*
|  | B.AN.100.1 | Prepare Analysis Specification
|  | B.AN.110.1 | Review Analysis Model
| B.ACT.DE Design - Elaboration |  |  | Modification Design Workshop XPI Development Workshop
|  | B.DS.035.1 | Update Existing Design Specification
|  | B.DS.050 | Determine Design and Build Standards
|  | B.DS.060 | Define Business Rules Implementation Strategy
|  | B.DS.070.1 | Design SOA Implementation Strategy
|  | B.DS.080.1 | Design Software Components
|  | B.DS.090.1 | Design Data
|  | B.DS.100.1 | Design Behavior
|  | B.DS.110.1 | Design Business Rules
|  | B.DS.120.1 | Design Services
|  | B.DS.130.1 | Design User Interface
|  | B.DS.140.1 | Prepare Design Specification
|  | B.DS.150.1 | Develop Database Design
|  | B.DS.160.1 | Review Design Model
B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration
|  | B.TE.020.1 | Develop Unit Test Scripts
|  | B.TE.035.1 | Create Integration Test Scenarios
B.ACT.DSTSE Develop System Test Scenarios – Elaboration
|  | B.TE.025.2 | Create System Test Scenarios
B.ACT.DVCSP Develop and Validate Custom Software Prototypes
|  | B.IM.010 | Develop Functional Prototype | Solution Walkthrough Workshop*
|  | B.RA.085 | Validate Functional Prototype | Solution Walkthrough Workshop* AOC Design Validation Workshop
|  | B.IM.020 | Develop Architectural Foundation
|  | B.IM.085 | Develop User Interface Standards Prototype | Presentation Layer Workshop*
|  | B.RA.095 | Validate User Interface Standards Prototype | Presentation Layer Workshop*
|  | B.IM.040.1 | Implement Database
|  | B.IM.053.1 | Register Services
|  | B.IM.055.1 | Perform Business Rules Implementation (Rules Engine)
|  | B.IM.060.1 | Perform Component Review
B.ACT.PCCTE Perform Custom Component Testing - Elaboration
|  | B.TE.030.1 | Perform Unit Test | Modification Testing Workshop AOC Development Testing Workshop CRM Development Testing Workshop XPI Testing Workshop
|  | B.TE.040.1 | Perform Integration Test | Modification Testing Workshop AOC Development Testing Workshop CRM Development Testing Workshop XPI Testing Workshop
B.ACT.PSTE Perform System Test – Elaboration
|  | B.TE.070.1 | Perform System Test | System Test Workshop*
| B.ACT.VUPE Validate Upgrade Process - Elaboration |  |  | Upgrade Planning Workshop Upgrade Workshop
|  | B.TE.072.1 | Test Pre-Upgrade Steps
|  | B.TE.073.1 | Test Packaged Software Upgrade
|  | B.TE.074.1 | Test Post-Upgrade Steps
|  | B.TE.075.1 | Perform Post-Upgrade Reconciliation Testing
|  | B.TE.076.1 | Review Upgrade Test Results
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy | High Availability Workshop
|  | B.PT.030 | Define Performance Testing Strategy
|  | B.PT.040 | Identify Performance Testing Models and Scenarios
|  | B.PT.050 | Design Performance Test Scripts and Programs
|  | B.PT.060 | Design Performance Test Data and Load Programs
B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration
|  | B.CV.025 | Define Data Acquisition and Conversion Standards | Data Conversion & Batch Interface Methodology Workshop
|  | B.RA.160 | Conduct Business Data Source Gap Analysis | Data Conversion & Batch Interface GAP Action Lab*
|  | B.CV.027.1 | Perform Data Mapping | Data Conversion & Batch Interface Workshop*
|  | B.RA.170.1 | Conduct Data Quality Assessment
|  | B.CV.035.1 | Define Manual Conversion Procedures (Initial Load) | Data Conversion & Batch Interface Workshop*
|  | B.CV.040.1 | Design Conversion Components (Initial Load) | Data Conversion & Batch Interface Workshop*
|  | B.CV.050.1 | Prepare Conversion Test Plans (Initial Load) | Data Conversion & Batch Interface Workshop*
|  | B.CV.060.1 | Perform Conversion Component Unit Test (Initial Load) | Data Conversion & Batch Interface Workshop*
|  | B.CV.062.1 | Perform Conversion Component Business Object Test (Initial Load) | Data Conversion & Batch Interface Workshop*
|  | B.CV.063.1 | Perform Conversion Component Validation Test (Initial Load) | Data Conversion & Batch Interface Workshop*
B.ACT.PBPII Prepare Business Process Impact Inventory
|  | B.OCM.160 | Prepare Business Process Impact Inventory
B.ACT.DCMRCCE Deploy Change Management Roadmap / Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap / Communication Campaign
|  | B.OCM.155.1 | Monitor Change Management Roadmap / Communication Campaign Effectiveness
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW)
|  | C.RD.130.2 | Develop Baseline Architecture Description
|  | C.RA.021.3 | Capture User Stories
|  | C.RA.023.3 | Develop Use Case Model
|  | C.RA.024.2 | Develop Use Case Details
|  | C.RA.025.3 | Identify Candidate Services
|  | C.RA.027.3 | Identify Candidate Business Rules
|  | C.RA.028.3 | Populate Business Rules Repository
|  | C.RA.180.2 | Review Use Case Model
C.ACT.AC Analyze - Construction
|  | C.AN.035.2 | Update Existing Analysis Specification
|  | C.AN.040.2 | Develop Analysis Architecture Description
|  | C.AN.050.2 | Analyze Data | Business Intelligence Workshop
|  | C.AN.060.2 | Analyze Behavior
|  | C.AN.070.2 | Analyze Business Rules
|  | C.AN.080.2 | Analyze Services
|  | C.AN.085.2 | Define Service
|  | C.RA.026.2 | Populate Services Repository
|  | C.AN.090.2 | Analyze User Interface | Presentation Layer Workshop*
|  | C.AN.100.2 | Prepare Analysis Specification
|  | C.AN.110.2 | Review Analysis Model
| C.ACT.DC Design - Construction |  |  | Modification Design Workshop
|  | C.DS.035.2 | Update Existing Design Specification
|  | C.DS.040.2 | Develop Design Architecture Description
|  | C.DS.080.2 | Design Software Components
|  | C.DS.090.2 | Design Data
|  | C.DS.100.2 | Design Behavior
|  | C.DS.110.2 | Design Business Rules
|  | C.DS.120.2 | Design Services
|  | C.DS.130.2 | Design User Interface
|  | C.DS.140.2 | Prepare Design Specification
|  | C.DS.150.2 | Develop Database Design
|  | C.DS.160.2 | Review Design Model
C.ACT.PTP Perform Test Planning
|  | C.TE.015.2 | Develop Integration Test Plan
|  | C.TE.050.2 | Develop System Test Plan
C.ACT.PEC Prepare Environments - Construction
|  | C.IM.007.2 | Prepare Development Environment | Installation Workshop*
|  | C.TE.018.2 | Prepare Static Test Data
|  | C.TE.038.2 | Prepare Integration Test Environment | Installation Workshop*
C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction
|  | C.TE.020.2 | Develop Unit Test Scripts
|  | C.TE.035.2 | Create Integration Test Scenarios
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios
| C.ACT.DSITS Develop Systems Integration Test Scenarios |  |  | Integration Workshop*
|  | C.TE.100 | Perform Systems Integration Test
C.ACT.ICC Implement Custom Components
|  | C.IM.040.2 | Implement Database
|  | C.IM.050 | Implement Components | CRM Custom Design & Code Workshop Modification Construction Workshop
|  | C.IM.053.2 | Register Services
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine)
|  | C.IM.060.2 | Perform Component Review
|  | C.IM.070 | Assemble Components
|  | C.IM.080 | Integrate Services
|  | C.IM.090 | Create Installation Routines
|  | C.TE.065 | Perform Installation Test
C.ACT.PCCTC Perform Custom Component Testing - Construction
|  | C.TE.030.2 | Perform Unit Test | Modification Testing Workshop CRM Development Testing Workshop AOC Development Testing Workshop XPI Testing Workshop
|  | C.TE.040.2 | Perform Integration Test
C.ACT.PST Prepare for System Test
|  | C.MC.050.2 | Define Application Setups | ERP Configurator Workshop (system code 32)..* Advanced Warehouse Workshop ..* Demand Forecasting Workshop..* Batch Processing Workshop* AOC Development Workshop Application Configuration Workshop* Advanced Transportation Workshop ..*
|  | C.TE.060.2 | Prepare System Test Environment | Installation Workshop*
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test | Integration Workshop*
|  | C.RA.055.2 | Document Business Procedures
|  | C.TE.019.1 | Collect, Assess and Refine KPI Measurements | Business Performance Measurement Workshop
| C.ACT.PSIT Prepare Systems Integration Test |  |  | Integration Workshop*
|  | C.TE.085 | Prepare Systems Integration Test Environment | Installation Workshop*
|  | C.TE.100 | Perform Systems Integration Test
| C.ACT.PPT Prepare for Performance Testing |  |  | Performance Tuning Workshop
|  | C.PT.070 | Build Performance Test Scripts and Programs
|  | C.PT.080 | Construct Performance Test Environment and Database
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal
| C.ACT.PT Prepare for Transition |  |  | Readiness Assessment Workshop
|  | C.TA.100 | Define System Management Procedures
|  | C.TA.110 | Define Operational Testing Plan
|  | C.TA.150 | Define Final Platform and Network Architecture
|  | C.TA.160 | Define System Capacity Plan
C.ACT.PCO Prepare for Cutover
|  | C.TS.020.2 | Define Cutover Strategy
|  | C.TS.030 | Develop Installation Plan
|  | C.TS.040 | Design Production Support Infrastructure | Solution Maintenance Workshop
C.ACT.TI Test Infrastructure
|  | C.TA.120 | Conduct Operational Testing
|  | C.TA.130 | Conduct Backup and Recovery Test
|  | C.TA.140 | Conduct Disaster Recovery Test
C.ACT.PACDC Prepare to Acquire and Convert Data - Construction
|  | C.CV.027.2 | Perform Data Mapping
|  | C.RA.170.2 | Conduct Data Quality Assessment
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load)
|  | C.CV.040.2 | Design Conversion Components (Initial Load)
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load)
| C.ACT.ACDC Acquire and Convert Data-Construction |  |  | Data Conversion and Batch Interface Workshops
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) | Installation Workshop*
|  | C.CV.055.2 | Implement Conversion Components (Initial Load)
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load)
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load)
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load)
|  | C.CV.064.1 | Install Conversion Components (Initial Load)
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) | Data Conversion & Batch Interface Data Validation Workshop*
|  | C.CV.068.1 | Clean Data | Data Conversion & Batch Interface Data Validation Workshop*
C.ACT.VUPC Validate Upgrade Process - Construction
|  | C.TE.072.2 | Test Pre-Upgrade Steps
|  | C.TE.073.2 | Test Packaged Software Upgrade
|  | C.TE.074.2 | Test Post-Upgrade Steps
|  | C.TE.075.2 | Perform Post-Upgrade Reconciliation Testing
|  | C.TE.076.2 | Review Upgrade Test Results
| C.ACT.PD Produce Documentation |  |  | UDT Development Workshop
|  | C.DO.060 | Publish User Reference Manual
|  | C.DO.070 | Publish User Guide
|  | C.DO.080 | Publish Technical Reference Material
|  | C.DO.100 | Produce Online Help
C.ACT.DCMRCCC Deploy Change Management Roadmap / Communication Campaign - Construction
|  | C.OCM.150.3 | Conduct Change Management Roadmap / Communication Campaign
|  | C.OCM.155.2 | Monitor Change Management Roadmap / Communication Campaign Effectiveness
C.ACT.CJIA Conduct Job Impact Analysis
|  | C.OCM.170 | Collect and Analyze Job Change Data
|  | C.OCM.180 | Determine Impact of Job Changes
|  | C.OCM.190 | Prepare HR Transition Plan
C.ACT.CMAWC Conduct Managers' Alignment Workshop - Construction
|  | C.OCM.200 | Design Managers' Unit / Department Impact Workshop
|  | C.OCM.210 | Conduct Managers' Unit / Department Impact Workshop
C.ACT.DEUT Design End-User Training
|  | C.TR.060 | Conduct User Learning Needs Analysis
|  | C.TR.070 | Develop User Learning Plan
C.ACT.BEUT Build End-User Training
|  | C.TR.080 | Develop User Learningware | AOC End User Documentation Workshop
|  | C.TR.090 | Prepare User Learning Environment
C.ACT.TEUC Train End Users - Construction
|  | C.TR.100.1 | Conduct User learning Events | UDT Train the End-User Workshop UDT Train the Trainer Workshop
C.ACT.IOCM Initial Operational Capability Milestone Summary
|  | C.PMC.IOCM | Initial Operational Capability Milestone
D Transition
D.ACT.SUAT Support User Acceptance Test
|  | D.TE.105 | Prepare Users for Testing
|  | D.TE.110 | Prepare Acceptance Test Environment
|  | D.TE.120 | Support Acceptance Test
D.ACT.CPTST Conduct Performance Test
|  | D.PT.100 | Execute Performance Test | Performance Tuning Workshop*
|  | D.PT.110 | Create Performance Test Report
D.ACT.PPE Prepare Production Environment
|  | D.TS.050 | Prepare Production Environment | Production Configuration Workshop* Platform Conversion Workshop Production Conversion Workshop
|  | D.TS.054 | Perform Pre-Upgrade Steps
|  | D.TS.055 | Upgrade Production Environment
|  | D.TS.056 | Perform Post-Upgrade Steps
|  | D.TS.057 | Revise Application Setups
D.ACT.CDT Convert Data - Transition
|  | D.CV.064.2 | Install Conversion Components (Initial Load)
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) | Data Conversion & Batch Interface Data Validation Workshop*
|  | D.CV.068.2 | Clean Data | Data Conversion & Batch Interface Data Validation Workshop*
D.ACT.DCMRCCT Deploy Change Management Roadmap / Communication Campaign - Transition
|  | D.OCM.150.4 | Conduct Change Management Roadmap / Communication Campaign
|  | D.OCM.155.3 | Monitor Change Management Roadmap / Communication Campaign Effectiveness
D.ACT.CITA Conduct IT Alignment
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups | Operations Support Workshop Operations Support Action Lab
|  | D.OCM.230 | Prepare IT Transition Plan | Operations Support Workshop Operations Support Action Lab
D.ACT.TEUT Train End Users - Transition
|  | D.TR.100.2 | Conduct User Learning Events
D.ACT.FD Finalize Documentation
|  | D.DO.110 | Finalize Documentation | AOC End User Documentation Workshop UDT Pilot & Test Workshop UDT Development Workshop (Core)
D.ACT.GP Go Production
|  | D.TS.052 | Implement Production Support Infrastructure | Solution Support Center Workshop Technology Support Center Workshop
|  | D.TS.058 | Verify Production Readiness | Readiness Assessment Workshop Transition Workshop
|  | D.TS.060 | Go Production
|  | D.TS.070 | Shut Down Legacy System
D.ACT.SIP System in Production Milestone Summary
|  | D.PMC.SIP | System in Production Milestone
E Production
E.ACT.MPSP Manage Production System Performance
|  | E.PT.120 | Conduct Production Performance Management | Performance Management Workshop
| E.ACT.EPS Evaluate Production System |  |  | Business Performance Review Workshop Process Optimization Workshop* Advanced Reporting Workshop - Optimize Phase
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements | Business Performance Measurement Workshop
|  | E.PS.010 | Audit System
| E.ACT.RPP Resolve Production Problems |  |  | Solution Maintenance Workshop
|  | E.PS.050 | Analyze Problems
|  | E.PS.060 | Monitor and Respond to System Problems
E.ACT.DCMRCCP Deploy Change Management Roadmap / Communication Campaign - Production
|  | E.OCM.150.5 | Conduct Change Management Roadmap / Communication Campaign
|  | E.OCM.155.4 | Monitor Change Management Roadmap / Communication Campaign Effectiveness
| E.ACT.PF Plan for Future |  |  | Gap Workshop - Optimize
|  | E.RD.160 | Convert Project Views to Reusable Viewpoints
|  | E.PS.135 | Determine Future Functional Enhancements
|  | E.PS.140 | Plan Enhancements
|  | E.OCM.250 | Measure Organizational Change Effectiveness
| E.ACT.DITTP Deploy IT Transition Plan |  |  | Transition Workshop
|  | E.OCM.260 | Implement IT Transition Plan
E.ACT.SO Sign Off Milestone Summary
|  | D.PMC.SO | Sign Off Milestone
Notes
Some OneMethology Activities in Column E are marked with an asterisk (*). This means that within OneMethodology there were several Tasks with this name, but from a Mapping perspective, they have been summarized into a single entry
For example, OneMethodology includes the following Activities, all of which map to the OUM RD.011.1 Future Process Model Task:
Detailed Process Modeling Workshop - Account and Report
Detailed Process Modeling Workshop - Process Payables
Detailed Process Modeling Workshop - Process Receivables
Detailed Process Modeling Workshop - Manage Assets
Detailed Process Modeling Workshop - Manage the Workforce
Detailed Process Modeling Workshop - Manage Projects
Detailed Process Modeling Workshop - Manage Property
Detailed Process Modeling Workshop - Manage Profitability
Detailed Process Modeling Workshop - Procure to Pay
Detailed Process Modeling Workshop - Campaign to Lead
Detailed Process Modeling Workshop - Lead to Order
Detailed Process Modeling Workshop - Order to Cash
Detailed Process Modeling Workshop - Consumption to Re-Order
Detailed Process Modeling Workshop - Manage Materials
Detailed Process Modeling Workshop - Design to Market
Detailed Process Modeling Workshop - Demand to Available