## Phase Mapping
OUM Phase Mapping to Siebel Results Roadmap (RR)
OUM Phases | Comparable Siebel RR Phases | Comments | Definitions:
Project Startup (Manage Focus Area) | Plan and Define Stages |  | Phase - A chronological grouping of tasks in an approach.
Inception (Implement Focus Area) | Plan and Define Stages | o Siebel Roadmap equivalent – Plan and Define (5% - same). o Objectives:  Scoping and high level requirements  To plan the project – understand costs, schedule, scope and risks  Identify key functionality o Milestone:  Lifecycle Objectives (LO) milestone at end of this phase – asks the question “can we proceed?”.
Elaboration (Implement Focus Area) | Discoverer and Design Stages | o Siebel Roadmap equivalent – Discover and Design (30% - same). o Objectives:  Often considered the most critical of the phases.  Complete the detailed analysis and design. o Milestone:  Lifecycle Architecture (LA) milestone end of this phase.  Are we clear of the solution to be able to commit more resource (cost) and time to this? Is the plan for the construction phase detailed enough and agreed?
Construction (Implement Focus Area) | Configure Stage | o Siebel Roadmap equivalent – Configure + SIT (45% if take configure as 25% + SIT 20% - approx same). o Objectives:  Complete iterative system development and unit, system and integration testing.  Develop beta version of system to provide to users.  Ready to move into user testing. o Milestone:  Initial Operational Capability (IOC) milestone at end of this phase – considers questions “are we ready to move to UAT?”
Transition (Implement Focus Area) | Validate and Deploy Stage | o Siebel Roadmap equivalent – UAT + Deploy (20% if take UAT as 5% + Deploy 15% - probably some of this should be in Production Phase). o Objectives:  Acceptance provided of the system by user community.  Acceptance of the project by client sponsor.  Users have been trained.  Documentation finalised.  Go Live. o Milestone:  System in Production (SP) milestone at end of this phase.
Production (Implement Focus Area) | Sustain Stage | o Siebel Roadmap equivalent - Sustain o Objectives:  Gain sign-off and close the contract.  Operate the newly developed system.  Manage production system.  Measure system performance.  Promote user acceptance and uptake. o Milestone:  Sign-off (SO) milestone at end of this phase.  Close contractual agreements and release project resources.

## OUM to Siebel RR Mapping
OUM to Results Roadmap Mapping Based on OUM 6.0 Requirements-Driven Application Implementation View WBS
PHASE | ACTIVITY | OUM TASK ID | OUM TASK NAME | Comparable Siebel RR Task ID | Comparable Siebel RR Task Name | Task Recommended for Siebel CRM Projects (Y/N) | Task Optional for Siebel CRM Projects (Y/N)
PS Project Startup
| PS.ACT.RBC Review Bid and Contract |  |  |  |  | Y
|  | BT.010 | Review and Analyze Bid Material |  |  | Y
|  | BT.020 | Review and Confirm Business Case |  |  | Y
|  | BT.030 | Identify Stakeholders |  |  | Y
|  | BT.040 | Review and Accept Project Budget |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Develop Draft SOW - Official SOW and Contract Developed - Contract Received from Legal | Y
|  | PS.RKM .020 | Conduct Baseline Risk Assessment |  | DEFINE Stage (Risk Assessment Workshop) - Prepare for RAW - Conduct the RAW | Y
PS.ACT.RPAC Review Project Assets with Customer
|  | BT.050 | Review Contract with Customer |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Client Signs Contract | Y
|  | BT.060 | Review Project Approach with Customer |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
|  | BT.070.1 | Create Project Management Plan |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Setup: - Determine Engagement Team - Determine Client Team - Document project in any tracking systems as required Establish Project Office: - Coordinate Space with Client - Determine Key Points of Contact | Y
| PS.ACT.VSSOS Validate Scope, Stakeholders and OCM Strategy |  |  |  |  | Y
|  | PS.SM.010 | Define and Confirm Scope |  | DEFINE Stage (Solution Scope DK) - Review Existing Documents (incl ePlan) - Review Prior Interviews / Conduct Additonal Interviews - Map Customer Process to Siebel Functions (Review Solution Blueprint, iGrafx Models) - Prepare/Update Solution Scope Document (leverage Strategy eRoadmap) - Conduct Solution Scope Review Meeting | Y
|  | PS.CMM.010 | Conduct Project Stakeholder Analysis |  |  | Y
|  | PS.OCHM.010 | Understand Customer's Organizational Change Management Strategy |  |  | Y
| PS.ACT.DW Develop Workplan |  |  |  |  | Y
|  | PS.WM.010 | Develop Baseline Project Workplan |  | DEFINE Stage (Project Startup DK) - Prepare/Revise Initial Project Plan - Prepare/Revise Project Control Document | Y
| PS.ACT.DSPB Develop Staff Plan and Budget |  |  |  |  | Y
|  | PS.FM.010 | Refine Project Budget |  |  | Y
|  | PS.STM.010 | Plan Resource Requirements |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Setup: - Determine Engagement Team | Y
|  | PS.STM.030 | Staff Project |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Setup: - Determine Engagement Team - Determine Client Team | Y
|  | PS.STM.040 | Prepare Orientation Guide(s) |  |  | Y
|  | PS.QM.030 | Conduct Project Team Quality Management Orientation |  | DEFINE Stage (PQR: Project Startup Review) - Deliver PQR Report - Closeout PQR Agreed Actions | Y
| PS.ACT.EG Establish Governance |  |  |  |  | Y
|  | PS.SM.020 | Develop Scope Change Management Processes
|  | PS.FM.020 | Develop Financial Management Plan |  |  | Y
|  | PS.WM.020 | Develop Work Management Execution and Control Processes and Policies |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Develop Draft SOW - Official SOW and Contract Developed | Y
|  | PS.RKM.010 | Develop Risk Management Plan |  | DEFINE Stage (Risk Assessment Workshop) - Develop the RAW Output | Y
|  | PS.IPM.010 | Develop Issue Management Strategy |  |  | Y
|  | PS.IPM.020 | Develop Problem Management Strategy |  |  | Y
|  | PS.STM.020 | Develop Staff Management Plan |  |  | Y
|  | PS.CMM.020 | Develop Project Team Communication Plan |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan | Y
|  | PS.QM.010 | Develop Quality Management Plan |  | DEFINE Stage (PQR: Project Startup Review) - Prepare for PQR - Conduct PQR | Y
|  | PS.QM.020 | Develop and Document Quality Control and Reporting Process |  | DEFINE Stage (PQR: Project Startup Review) - Develop PQR Report | Y
|  | PS.CM.010 | Develop Configuration Management Strategy and Processes |  |  | Y
|  | PS.CM.030 | Create Project Documentation Management Plan |  | DEFINE Stage (Project Documentation) - Prepare Initial Engagement Charter - Review Engagement Charter with Client - Revise Engagement Charter - Revise Project Details in Tracking System | Y
|  | PS.IFM.010 | Develop Infrastructure Management Plan |  |  | Y
|  | PS.PCM.010 | Develop Procurement Strategy and Process |  |  | Y
|  | PS.OCHM.020 | Identify Change Management Warning Signs |  |  | Y
|  | PS.BT.070.2 | Create Project Management Plan |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Setup: - Determine Engagement Team - Determine Client Team - Document project in any tracking systems as required Establish Project Office: - Coordinate Space with Client - Determine Key Points of Contact | Y
| PS.ACT.EPI Establish Project Infrastructure and Orientation Guides |  |  |  |  | Y
|  | PS.FM.030 | Set Up Time and Expense Tracking |  |  | Y
|  | PS.RKM.030 | Develop Risk Management System |  | DEFINE Stage (Risk Assessment Workshop) - Follow up on RAW results | Y
|  | PS.IPM.030 | Develop Issue and Problem Management System |  |  | Y
|  | PS.CM.020 | Obtain Configuration Management Tools |  |  | Y
|  | PS.IFM.020 | Establish Team Work Environment |  | DEFINE Stage (Project Startup DK) - Prepare Work Environment | Y
|  | PS.IFM.030 | Establish Technical Infrastructure |  | DEFINE Stage (Identify Ongoing Project Infrastructure Support Requirements) - Review/Update Database Admin Requirements - Review/Update Server Management Requirements - Review/Update Network Administration Requirements - Review/Update Desktop Environment Requirements - Review/Update Siebel Application Admininistration Requirements - Out of the box Siebel Installed for subsequent stages to build on | Y
|  | PS.PCM.020 | Procure Goods and Contracted Services |  |  | Y
PEC.ACT.PEC Project Execution and Control
PEC.ACT.MSAA Manage Scope, Acceptance and Approvals
|  | PEC.SM.030 | Manage Scope |  |  | Y
|  | PEC.SM.040 | Manage Acceptance |  |  | Y
PEC.ACT.MPF Manage Project Finances
|  | PEC.FM.040 | Manage Project Finances |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Budget Reporting | Y
PEC.ACT.MPW Manage Project Workplan
|  | PEC.WM.030 | Manage Project Workplan |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Plan and Actuals | Y
|  | PEC.WM.040 | Track Schedule Performance |  |  | Y
|  | PEC.WM.070 | Schedule Workshop(s)
PEC.ACT.MRIP Manage Risks, Issues and Problems
|  | PEC.RKM.040 | Manage Risk |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Risk/issue log maintenance | Y
|  | PEC.RKM.050 | Monitor and Control Risk |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Risk/issue log maintenance | Y
|  | PEC.IPM.040 | Manage Issues and Problems |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage day-to-day Issues and Meetings | Y
PEC.ACT.OMT Orient and Manage Team
|  | PEC.STM.050 | Conduct Team Orientation(s) |  |  | Y
|  | PEC.STM.060 | Manage Project Team |  |  | Y
PEC.ACT.MCOP Manage Communications and OCM Plans
|  | PEC.CMM.030 | Manage Project Team Communication |  |  | Y
|  | PEC.OCHM.030 | Execute Change and Communication Plan |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Status Reporting - Manage Change Control - Conduct Project Status Meetings | Y
PEC.ACT.MPQ Manage Project Quality
|  | PEC.QM.040 | Manage Quality Control |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Quality Review | Y
|  | PEC.QM.050 | Perform Quality Assurance |  | Ongoing Project Management DK Ongoing Project Management (Schedule in Discover through Deploy Stages) - Manage Project Quality Review | Y
PEC.ACT.CECRM Create and Execute Configuration and Release Management
|  | PEC.CM.040 | Create and Execute Software Configuration Management Plan |  |  | Y
|  | PEC.CM.050 | Create and Execute Software Release Management Plan |  |  | Y
|  | PEC.CM.060 | Create and Execute Environment and Patch Management Plan |  |  | Y
|  | PEC.CM.070 | Create and Execute Configuration Management Control Plan |  |  | Y
PEC.ACT.MMI Manage and Maintain Infrastructure
|  | PEC.IFM.040 | Manage and Maintain Infrastructure |  |  | Y
PEC.ACT.APGCS Administer Procurement of Goods and Contracted Services
|  | PEC.PCM.030 | Administer Procurement of Goods and Contracted Services |  |  | Y
A Inception
| A.ACT.GBRI Gather Business Requirements - Inception |  |  |  |  | Y
|  | A.RD.001 | Detail Business and System Objectives |  | DISCOVER Stage (Business Objectives) - Review Business Objectives - Adjust/Refine Business Objectives as required | Y
|  | A.RD.005 | Create System Context Diagram |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
|  | A.RD.011.1 | Develop Future Process Model |  | DEFINE Stage (Solution Scope DK) - Map Customer Process to Siebel Functions (Review Solution Blueprint, iGrafx Models) | Y
|  | A.RD.020 | Obtain High-Level Business Descriptions |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
|  | A.RA.015 | Develop Business Use Case Model |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
|  | A.RD.065 | Develop Domain Model (Business Entities) |  | DEFINE Stage (Solution Scope DK): - Prepare/Update Solution Scope Document (leverage Strategy eRoadmap) DISCOVER Stage (Business Scope Definition): - Review Business Scope - Adjust/Refine Business Scope as required | Y
|  | A.RD.012 | Document Present and Future Organization Structures |  | DISCOVER Stage: Review Business Units: - Adjust/Refine Business Units as required Business Process-Function: - Organization | Y
|  | A.RD.015 | Determine KPI Collection and Reporting Strategy |  |  |  | Y
A.ACT.ECBB Establish Current Business Baseline
|  | A.RD.030 | Develop Current Business Process Model |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Review/Update Existing Business Process-Function Requirements |  | Y
|  | A.RD.034 | Document Current Business Baseline Metrics |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Validate/Update Business Process Flow Diagrams (additional detail) |  | Y
A.ACT.GR Gather Solution Requirements
|  | A.RD.042.1 | Develop Glossary |  |  | Y
|  | A.RD.045.1 | Prioritize Requirements (MoSCoW) |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Conduct Business Process-Function Workshops (repeat for each) - Reporting - Workflow Integrate and Approve Requirements: - Review requirements and reconcile conflicts - Integrate requirements - Obtain sign-off on integrated requirements | Y
|  | A.RD.055 | Detail Supplemental Requirements |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Localization Operational Requirements (Schedule in Discover Stage): - Prepare for Operational Requirements Sessions - Facilitate Rollout Requirements Session - Review/Update Operational Requirements Security Requirements: - Identify System Access Security Requirements - Identify Data Access Security Requirements - Identify Business Function Access Security Requirements | Y
|  | A.RD.130.1 | Develop Baseline Architecture Description |  |  |  | Y
|  | A.RA.023.1 | Develop Use Case Model |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
|  | A.RA.027.1 | Identify Candidate Business Rules
|  | A.RA.028.1 | Populate Business Rules Repository
A.ACT.CR Consolidate Solution Requirements
|  | A.RD.140.1 | Create Requirements Specification |  | DISCOVER Stage (Business Requirements DK) Business Process-Function-Conduct Business Process-Function Workshops (repeat for each) Develop Solution Review Kits: - Determine Siebel Solution for each requirement - Prepare Solution Review Kit - User Verification of Solution Review Kit - Refine Solution Review Kit to reflect customer changes - Record Signoff of Area Solution Review Kit Consolidate Functional Requirements: - Create/Review Functional Requirements Matrix Integrate and Approve Requirements: - Integrate requirements |  | Y
|  | A.RD.150.1 | Review Requirements Specification |  | DISCOVER Stage (Business Requirements DK) Integrate and Approve Requirements: - Review requirements and reconcile conflicts - Obtain sign-off on integrated requirements |  | Y
A.ACT.CCPI Create Conceptual Prototype - Inception
|  | A.IM.005.1 | Develop Conceptual Prototype |  |  |  | Y
|  | A.RA.030.1 | Validate Conceptual Prototype |  |  |  | Y
A.ACT.GSP Gather Supporting Requirements
|  | A.CV.010 | Define Data Acquisition and Conversion Requirements |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Conversion/Interface Requirements: - Review/Update External Interfaces - Review/Update Data Conversions - Review/Update Interface Performance-Timing Requirements Data Requirements: - Document/Review Functional Data Requirements - Document/Review Interface Data Requirements - Develop/Review Integrated Data Requirements - Identify/Review Data Cleansing and Archival Requiements | Y
|  | A.TE.005.1 | Determine Testing Requirements |  | DISCOVER Stage (Business Requirements DK) Acceptance Criteria: - Define Acceptance Strategy - Define Acceptance Criteria - Obtain sign-off on Acceptance Criteria DESIGN Stage (Test Strategy DK) Test Requirements Definition: - Test Objectives & Scope Definition - Existing Test Cases Review - Test Requirements Definition & Prioritization | Y
|  | A.PT.010 | Conduct Performance Management Workshop |  |  |  | Y
|  | A.TA.010 | Conduct Technical Architecture Workshop |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Review/Update System Architecture Requirements - Review/Update Sizing Requirements - Conduct detailed sizing review with Siebel Expert Services | Y
|  | A.DO.010 | Define Documentation Requirements and Strategy |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Documentation: - Prepare Initial Engagement Charter - Review Engagement Charter with Client - Revise Engagement Charter - Revise Project Details in Tracking System DESIGN Stage (Deployment Design DK (Proposed)) Application Support Design: - Design End-User Documentation | Y
|  | A.RD.070 | Determine Audit and Control Requirements |  | DISCOVER Stage (Business Requirements DK) Operational Requirements (Schedule in Discover Stage): - Prepare for Operational Requirements Sessions - Facilitate Rollout Requirements Session - Review/Update Operational Requirements Security Requirements: - Identify System Access Security Requirements - Identify Data Access Security Requirements - Identify Business Function Access Security Requirements | Y
| A.ACT.SKSD Specify Key Structure Definition |  |  |  |  | Y
|  | A.MC.010.1 | Define Business Data Structures |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items | Y
|  | A.MC.020 | Define Business Data Structure Setups |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Define and document reference data (list of values) - Document Multi-National Formats and Localization Plan. | Y
| A.ACT.CMAHC Create and Manage Ad Hoc Communications | [5 empty] | Y
|  | A.OCM.010 | Create and Manage Ad Hoc Communications |  |  |  | Y
| A.ACT.CEAW Conduct Executive Alignment Workshop | [5 empty] | Y
|  | A.OCM.020 | Prepare for Executive Alignment Workshop |  |  |  | Y
|  | A.OCM.030 | Conduct Executive Alignment Workshop |  |  |  | Y
|  | A.OCM.040 | Build and Deploy Sponsorship Program |  |  |  | Y
| A.ACT.TPT Train Project Team | [5 empty] | Y
|  | A.TR.010.1 | Define Training Strategy |  |  |  | Y
|  | A.TR.020 | Prepare Project Team Learning Plan |  |  |  | Y
|  | A.TR.030 | Prepare Project Team Learning Environment |  |  |  | Y
|  | A.TR.040 | Develop Project Team Learningware |  |  |  | Y
|  | A.TR.050 | Conduct Project Team Learning Events |  |  |  | Y
| A.ACT.CAWI Conduct Alignment Workshops - Inception | [5 empty] | Y
|  | A.OCM.050 | Prepare for Team-Building Workshop |  | DEFINE Stage Project Setup: - Determine Engagement Team - Determine Client Team - Document project in any tracking systems as required |  | Y
|  | A.OCM.060 | Conduct Team-Building Workshop |  | DEFINE Stage (Project Startup DK) - Conduct Team Kickoff - Prepare Project Binder - Prepare Work Environment |  | Y
|  | A.OCM.070 | Design Managers Project Alignment Workshop |  |  |  | Y
|  | A.OCM.080 | Conduct Managers Project Alignment Workshop |  |  |  | Y
|  | A.OCM.090 | Design Change Agent Workshop |  |  |  | Y
|  | A.OCM.100 | Conduct Change Agent Workshop |  |  |  | Y
| A.ACT.CCRA Conduct Change Readiness Assessment | [5 empty] | Y
|  | A.OCM.110 | Develop Change Readiness Assessment Strategy and Tools |  |  |  | Y
|  | A.OCM.120 | Conduct Change Readiness Assessment and Analyze Data |  |  |  | Y
|  | A.OCM.130 | Build Communication Strategy and Change Management Roadmap |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan |  | Y
| A.ACT.DCMRCCI Deploy Change Management Roadmap and Communication Campaign - Inception | [5 empty] | Y
|  | A.OCM.140 | Develop Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan |  | Y
|  | A.OCM.150.1 | Conduct Change Management Roadmap and Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan |  | Y
| A.ACT.LCOB Lifecycle Objective Milestone Summary | [5 empty] | Y
|  | A.PMC.LCOB | Lifecycle Object Milestone |  | DEFINE Stage: PQR: Project Startup Review - Closeout PQR Agreed Actions - Complete Initial Siebel Assessment DISCOVER Stage: - Obtain sign-off on integrated requirements - Obtain sign-off on Acceptance Criteria | Y
B Elaboration
B.ACT.DPS Define Project Strategy
|  | B.DS.020 | Define Application Extension Strategy |  |  | Y
|  | B.TE.005.2 | Determine Testing Requirements |  | DESIGN Stage (Test Strategy DK) Test Requirements Definition: - Test Objectives & Scope Definition - Existing Test Cases Review - Test Requirements Definition & Prioritization | Y
|  | B.TE.010 | Develop Testing Strategy |  | DISCOVER Stage (Business Requirements DK) Acceptance Criteria: - Define Acceptance Strategy - Define Acceptance Criteria - Obtain sign-off on Acceptance Criteria | Y
|  | B.CV.020 | Define Data Acquisition, Conversion and Data Quality Strategy |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Conversion/Interface Requirements: - Review/Update External Interfaces - Review/Update Data Conversions - Review/Update Interface Performance-Timing Requirements Data Requirements: - Document/Review Functional Data Requirements - Document/Review Interface Data Requirements - Develop/Review Integrated Data Requirements - Identify/Review Data Cleansing and Archival Requiements | Y
|  | B.DO.020 | Define Documentation Standards and Procedures |  | DEFINE Stage (Project Contract Management DK (Proposed)) Project Documentation: - Prepare Initial Engagement Charter - Review Engagement Charter with Client - Revise Engagement Charter - Revise Project Details in Tracking System DESIGN Stage (Deployment Design DK (Proposed)) Application Support Design: - Design End-User Documentation | Y
|  | B.TR.010.2 | Define Training Strategy |  | DEFINE Stage: Project Startup DK: Identify Ongoing Project Infrastructure Support Requirements: - Identify/Review end user training strategy | Y
|  | B.TS.020.1 | Define Cutover Strategy |  | DESIGN Stage (Deployment Design DK (Proposed)) - Design/Plan Dev to Prod Migration | Y
B.ACT.DI Define Infrastructure
|  | B.TA.020 | Define Technical Architecture Requirements and Strategy |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Review/Update System Architecture Requirements - Review/Update Sizing Requirements - Conduct detailed sizing review with Siebel Expert Services | Y
|  | B.TA.030 | Define Integration Requirements and Strategy |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Conversion/Interface Requirements: - Review/Update External Interfaces - Review/Update Data Conversions - Review/Update Interface Performance-Timing Requirements | Y
|  | B.TA.040 | Define Reporting and Information Access Strategy |  | DISCOVER Stage (Business Requirements DK) Reporting - Prepare for Reporting Workshops - Conduct Workshop - Conduct Workshop Recap session - Prepare Process Review Kit - User Verfication of Process Review Kit - Update RMT by Process - Record Signoff of Process and Requirements | Y
|  | B.TA.050 | Define Disaster Recovery Strategy |  |  | Y
|  | B.TA.060 | Define System Operations and Management Strategy |  | DISCOVER Stage (Business Requirements DK) Operational Requirements (Schedule in Discover Stage): - Review/Update Operational Requirements DESIGN Stage (Deployment Design DK (Proposed) Application Support Design: -Define Help Desk Process -Design End-User Documentation -Design Run Book for Operations Staff | Y
|  | B.TA.070 | Define Initial Architecture and Application Mapping |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Review/Update System Architecture Requirements - Review/Update Sizing Requirements - Conduct detailed sizing review with Siebel Expert Services | Y
|  | B.TA.080 | Define Backup and Recovery Strategy |  |  | Y
|  | B.TA.090 | Develop Security and Control Strategy |  | DISCOVER Stage (Business Requirements DK) Security Requirements: - Identify System Access Security Requirements - Identify Data Access Security Requirements - Identify Business Function Access Security Requirements |  | Y
| B.ACT.PEE Prepare Environments-Elaboration |  |  |  |  | Y
|  | B.IM.007.1 | Prepare Development Environment |  | CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Create Development Environment - Build Development Database | Y
|  | B.TE.018.1 | Prepare Static Test Data |  | DESIGN Stage (Test Strategy DK) Data Model - Assist in developing data model for testing - Transfer Data Model | Y
|  | B.TE.038.1 | Prepare Integration Test Environment |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Create Development Environment | Y
|  | B.TE.060.1 | Prepare System Test Environment |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Create Development Environment | Y
|  | B.DO.040 | Prepare Documentation Environment |  | DEFINE Stage (Project Startup DK) - Prepare Project Binder | Y
| B.ACT.GBRE Gather Business Requirements - Elaboration |  |  |  |  | Y
|  | B.RD.011.2 | Develop Future Process Model |  | DEFINE Stage (Solution Scope DK) - Map Customer Process to Siebel Functions (Review Solution Blueprint, iGrafx Models) | Y
|  | B.RA.055.1 | Document Business Procedures |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: Conduct Business Process-Function Workshops (repeat for each) - Reporting - Workflow |  | Y
|  | B.MC.030 | Map Business Requirements |  | DISCOVER Stage (Gap Analysis DK) Prepare for Detailed Gap Analysis: - Review ePlan Solution Blueprint and associated reports - Review business requirements spreadsheet (business unit, requirements, Siebel function, etc) - Load client's purchased modules onto laptops - Review functionality and assess against Solution Blueprint findings Detailed Gap Identification-Compare requirements and process flows to application capability: - Review high-level business process to Siebel core product functions (from Solution Blueprint document) - Review the mappings to the business object layer - Map directly to the data object layer | Y
| B.ACT.DTP Develop Test Plans |  |  |  |  | Y
|  | B.TE.015.1 | Develop Integration Test Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Define Business Scenarios - Define Data requirements - Project Plan - High-level test cases - Test Plan | Y
|  | B.TE.050.1 | Develop System Test Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Define Business Scenarios - Define Data requirements - Project Plan - High-level test cases - Test Plan | Y
|  | B.TE.080 | Develop Systems Integration Test Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Define Business Scenarios - Define Data requirements - Project Plan - High-level test cases - Test Plan | Y
|  | B.TE.082 | Develop Acceptance Test Plan |  | DESIGN Stage (Test Strategy DK) Test Requirements Definition: - Test Objectives & Scope Definition - Existing Test Cases Review - Test Requirements Definition & Prioritization - Create Charter - Charter Approval | Y
| B.ACT.SSC Specify Software Configuration |  |  |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items
|  | B.MC.010.2 | Define Business Data Structures |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items | Y
|  | B.MC.040 | Gather Setup Information |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items
|  | B.MC.050.1 | Define Application Setups |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Define and document reference data (list of values) - Document Multi-National Formats and Localization Plan. | Y
|  | B.MC.060 | Document Functional Secruity |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items
B.ACT.PVC Prototype and Validate Configuration
|  | B.TE.025.1 | Create System Test Scenarios |  |  | Y
|  | B.MC.070 | Prepare Configuration Prototype Environment
|  | B.MC.080 | Conduct Configuration Prototyping Workshop
|  | B.MC.090.2 | Conduct Reporting Fit Analysis |  |  | Y
| B.ACT.PGA Perform Gap Analysis |  |  |  |  | Y
|  | B.MC.100 | Define and Estimate Application Extensions |  | DISCOVER Stage (Gap Analysis DK) Detailed Gap Identification-Determine Rating Scale: - Document list of potential detailed gaps - Review the appropriate rating scale to identify the complexity of the detailed gaps | Y
|  | B.MC.110 | Define Gap Resolutions |  | DISCOVER Stage (Gap Analysis DK) Detailed Gap Identification-Conduct User Review Sessions: - Prepare for User Review Session - Determine which gaps are "in scope" - Rank each gap using the Complexity scale - Determine Level of Effort for each gap - Prioritize the gaps - Finalize list of identified gaps - Deliverable: Gap Ranking & Priorization Detailed Gap Analysis: - Develop consolidated Gap Analysis document ranking information - Conduct internal review of gap analysis document - Revise and update gap analysis document - Present document to key users - Deliverable: Gap Analysis Document | Y
B.ACT.DUCM Develop Use Case Model
|  | B.RA.023.2 | Develop Use Case Model |  | DEFINE Stage (Project Contract Management DK (Proposed)) Legal Requirements: - Meet Client to Define/Refine High Level Requirements | Y
| C.ACT.CCPE Create Conceptual Prototype - Elaboration | [5 empty] | Y
|  | B.IM.005.2 | Develop Conceptual Prototype |  |  |  | Y
|  | B.RA.030.2 | Validate Conceptual Prototype |  |  |  | Y
B.ACT.CS Consolidate Specification
|  | B.RD.042.2 | Develop Glossary |  |  | Y
|  | B.RD.045.2 | Prioritize Requirements (MoSCoW) |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Conduct Business Process-Function Workshops (repeat for each) - Reporting - Workflow Integrate and Approve Requirements: - Review requirements and reconcile conflicts - Integrate requirements - Obtain sign-off on integrated requirements | Y
|  | B.RD.140.2 | Create Requirements Specification |  | DISCOVER Stage (Business Requirements DK) Business Process-Function-Conduct Business Process-Function Workshops (repeat for each) Develop Solution Review Kits: - Determine Siebel Solution for each requirement - Prepare Solution Review Kit - User Verification of Solution Review Kit - Refine Solution Review Kit to reflect customer changes - Record Signoff of Area Solution Review Kit Consolidate Functional Requirements: - Create/Review Functional Requirements Matrix Integrate and Approve Requirements: - Integrate requirements |  | Y
|  | B.RD.150.2 | Review Requirements Specification |  | DISCOVER Stage (Business Requirements DK) Integrate and Approve Requirements: - Review requirements and reconcile conflicts - Obtain sign-off on integrated requirements |  | Y
|  | B.RA.027.2 | Identify Candidate Business Rules |  |  |  | Y
|  | B.RA.028.2 | Populate Business Rules Repository |  |  |  | Y
|  | B.RA.180.1 | Review Use Case Model |  | DISCOVER Stage (Business Scope Definition): - Review Business Scope - Adjust/Refine Business Scope as required | Y
B.ACT.BSA Baseline Software Architecture
|  | B.RA.035 | Develop High-Level Software Architecture Description |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Review/Update System Architecture Requirements | Y
|  | B.AN.040.1 | Develop Analysis Architecture Description |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Review/Update Sizing Requirements | Y
|  | B.DS.040.1 | Develop Design Architecture Description |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Conduct detailed sizing review with Siebel Expert Services | Y
B.ACT.DUCD Develop Use Case Details
|  | B.RA.024.1 | Develop Use Case Details |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Validate/Update Business Process Flow Diagrams (additional detail) | Y
| B.ACT.AE Analyze - Elaboration |  |  |  |  | Y
|  | B.AN.050.1 | Analyze Data |  | DISCOVER Stage (Gap Analysis DK) Create Entity Relationship Diagrams: - Create logical ERD - Create physical ERD | Y
|  | B.AN.060.1 | Analyze Behavior |  |  | Y
|  | B.AN.070.1 | Analyze Business Rules |  | DESIGN Stage: Application Design: - Design VB/COM Business Rules Workflow/Business Rule Design: - Design Workflow Manager Policies/Rules - Prepare for Workflow Manager Design Review - Design State Models - Design Assignment Objects, Rules - Conduct Assignment Manager Design Review | Y
|  | B.AN.090.1 | Analyze User Interface |  | DESIGN Stage: Application Design: - Design User Interface | Y
|  | B.AN.100.1 | Prepare Analysis Specification |  | DESIGN Stage: Application Design: - Prepare for Configuration Design Review with Siebel Expert Services |  | Y
|  | B.AN.110.1 | Review Analysis Model |  | DESIGN Stage (Test Strategy DK) Business & Systems Review: - Architecture & Application Review - High-Level Process & Data Flow Review | Y
| B.ACT.DE Design - Elaboration |  |  |  |  | Y
|  | B.DS.050 | Determine Design and Build Standards |  |  | Y
|  | B.DS.060 | Define Business Rules Implementation Strategy |  | DESIGN Stage: Application Design: - Design VB/COM Business Rules | Y
|  | B.DS.080.1 | Design Software Components |  |  | Y
|  | B.DS.090.1 | Design Data |  | DESIGN Stage: Data Mapping: - Document User Interface/Business Object Data Mapping - Review Data Mapping Application Design: - Prepare for Configuration Kickoff - Map Physical Data Model - Design Report Definitions | Y
|  | B.DS.100.1 | Design Behavior |  |  | Y
|  | B.DS.110.1 | Design Business Rules |  | DESIGN Stage: Application Design: - Design VB/COM Business Rules Workflow/Business Rule Design: - Design Workflow Manager Policies/Rules - Prepare for Workflow Manager Design Review - Design State Models - Design Assignment Objects, Rules - Conduct Assignment Manager Design Review | Y
|  | B.DS.130.1 | Design User Interface |  | DESIGN Stage: Application Design: - Design User Interface | Y
|  | B.DS.140.1 | Prepare Design Specification |  | DESIGN Stage: Application Design: - Prepare for Configuration Design Review with Siebel Expert Services | Y
|  | B.DS.150.1 | Develop Database Design |  | DESIGN Stage (Interface Design) Review Interface Requirements: - Design Recurring Data Interfaces - Document EIM mappings - Review mappings with application design team - Document EIM Processing Design - Design Archival Strategy and Interfaces - Prepare for EIM Mapping and Design Processing Review | Y
|  | B.DS.160.1 | Review Design Model |  | DESIGN Stage: Conduct Design Review with Expert Services | Y
| B.ACT.DCCTSE Develop Custom Component Test Scripts - Elaboration |  |  |  |  | Y
|  | B.TE.020.1 | Develop Unit Test Scripts |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
|  | B.TE.035.1 | Create Integration Test Scenarios |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
| B.ACT.DSTSE Develop System Test Scenarios – Elaboration |  |  |  |  | Y
|  | B.TE.025.2 | Create System Test Scenarios |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
| B.ACT.DVCSP Develop and Validate Custom Software Prototypes |  |  |  |  | Y
|  | B.IM.010 | Develop Functional Prototype |  |  | Y
|  | B.RA.085 | Validate Functional Prototype |  |  | Y
|  | B.IM.020 | Develop Architectural Foundation |  |  |  | Y
|  | B.IM.085 | Develop User Interface Standards Prototype |  |  |  | Y
|  | B.RA.095 | Validate User Interface Standards Prototype |  |  | Y
|  | B.IM.040.1 | Implement Database |  |  |  | Y
|  | B.IM.055.1 | Perform Business Rules Implementation (Rules Engine) |  |  |  | Y
|  | B.IM.060.1 | Perform Component Review |  |  | Y
| B.ACT.PCCTE Perform Custom Component Testing - Elaboration |  |  |  |  | Y
|  | B.TE.030.1 | Perform Unit Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop X (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
|  | B.TE.040.1 | Perform Integration Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop X (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
| B.ACT.PSTE Perform System Test – Elaboration |  |  |  |  | Y
|  | B.TE.070.1 | Perform System Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop X (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
B.ACT.PPM Plan Performance Management
|  | B.PT.020 | Define Performance Management Requirements and Strategy |  |  | Y
|  | B.PT.030 | Define Performance Testing Strategy |  |  | Y
|  | B.PT.040 | Identify Performance Testing Models and Scenarios |  | VALIDATE Stage (Performance Testing DK) - Configure\Validate Performance Test Environment - Detail Test Case Development | Y
|  | B.PT.050 | Design Performance Test Scripts and Programs |  | VALIDATE Stage (Performance Testing DK) - Create Test scripts - Sign-off on scripts Performance Test: - PT Modify & run script - PT Analyze Test Results - PT results report Stress Test: - ST Modify & run script - ST Analyze Test Results - ST results report Longevity Test: - LT Modify & run script - LT Analyze Test Results - LT results report Testing Sign-off: - Transfer of test scripts - Customer Sign-off | Y
|  | B.PT.060 | Design Performance Test Data and Load Programs |  | VALIDATE Stage (Performance Testing DK) - Create Test scripts - Sign-off on scripts Performance Test: - PT Modify & run script - PT Analyze Test Results - PT results report Stress Test: - ST Modify & run script - ST Analyze Test Results - ST results report Longevity Test: - LT Modify & run script - LT Analyze Test Results - LT results report Testing Sign-off: - Transfer of test scripts - Customer Sign-off | Y
| B.ACT.PACDE Prepare to Acquire and Convert Data - Elaboration |  |  |  |  | Y
|  | B.CV.025 | Define Data Acquisition and Conversion Standards |  | DESIGN STAGE (Solution Design DK): Conversion Design: - Create Data Conversion Plan - Define Data Cleansing Plan - Design Initial Data Load - Document EIM Mappings - Review Mappings with Application Design Team - Document EIM Processing Design | Y
|  | B.RA.160 | Conduct Business Data Source Gap Analysis |  |  | Y
B.ACT.PBPII Prepare Business Process Impact Inventory
|  | B.OCM.160 | Prepare Business Process Impact Inventory |  |  | Y
B.ACT.DCMRCCE Deploy Change Management Roadmap and Communication Campaign - Elaboration
|  | B.OCM.150.2 | Conduct Change Management Roadmap and Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan | Y
|  | B.OCM.155.1 | Monitor Change Management Roadmap and Communication Campaign Effectiveness |  | Ongoing Project Management DK (All stages) Ongoing Project Management (Schedule in Discover through Deploy Stages): - Manage Change Control - Manage Project Risk/issue log maintenance - Conduct Project Status Meetings - Manage day-to-day Issues and Meetings | Y
B.ACT.LCAR Lifecycle Architecture Milestone Summary
|  | B.PMC.LCAR | Lifecycle Architecture Milestone |  | DESIGN Stage: - Conduct Design Review with Expert Services CONFIGURE Stage: Setup Development Environment (Discover Stage) - Create Development Environment - Build Development Database DISCOVER Stage (Business Requirements DK) Identify System Capacity and Architecture Requirements: - Conduct detailed sizing review with Siebel Expert Services | Y
C Construction
C.ACT.FR Finalize Requirements
|  | C.RD.042.3 | Develop Glossary |  |  | Y
|  | C.RD.045.3 | Prioritize Requirements (MoSCoW) |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Conduct Business Process-Function Workshops (repeat for each) - Reporting - Workflow Integrate and Approve Requirements: - Review requirements and reconcile conflicts - Integrate requirements - Obtain sign-off on integrated requirements | Y
|  | C.RD.130.2 | Develop Baseline Architecture Description |  |  |  | Y
|  | C.RA.023.3 | Develop Use Case Model |  | DISCOVER Stage (Business Requirements DK) Business Process-Function-Conduct Business Process-Function Workshops (repeat for each) - User Verfication of Business Process Review Kit - Prepare Business Process Review Kit | Y
|  | C.RA.024.2 | Develop Use Case Details |  | DISCOVER Stage (Business Requirements DK) Business Process-Function: - Validate/Update Business Process Flow Diagrams (additional detail) | Y
|  | C.RA.027.3 | Identify Candidate Business Rules
|  | C.RA.028.3 | Populate Business Rules Repository
|  | C.RA.180.2 | Review Use Case Model |  | DISCOVER Stage (Business Scope Definition): - Review Business Scope - Adjust/Refine Business Scope as required | Y
C.ACT.AC Analyze - Construction
|  | C.AN.040.2 | Develop Analysis Architecture Description |  | DISCOVER Stage (Business Requirements DK) Identify System Capacity and Architecture Requirements: - Review/Update System Architecture Requirements - Review/Update Sizing Requirements - Conduct detailed sizing review with Siebel Expert Services | Y
|  | C.AN.050.2 | Analyze Data |  | DISCOVER Stage (Gap Analysis DK) Create Entity Relationship Diagrams: - Create logical ERD - Create physical ERD | Y
|  | C.AN.060.2 | Analyze Behavior |  |  | Y
|  | C.AN.070.2 | Analyze Business Rules |  | DESIGN Stage: Application Design: - Design VB/COM Business Rules Workflow/Business Rule Design: - Design Workflow Manager Policies/Rules - Prepare for Workflow Manager Design Review - Design State Models - Design Assignment Objects, Rules - Conduct Assignment Manager Design Review | Y
|  | C.AN.090.2 | Analyze User Interface |  | DESIGN Stage: Application Design: - Design User Interface | Y
|  | C.AN.100.2 | Prepare Analysis Specification |  | DESIGN Stage: Application Design: - Prepare for Configuration Design Review with Siebel Expert Services |  | Y
|  | C.AN.110.2 | Review Analysis Specification |  | DESIGN Stage (Test Strategy DK) Business & Systems Review: - Architecture & Application Review - High-Level Process & Data Flow Review | Y
C.ACT.DC Design - Construction
|  | C.DS.040.2 | Develop Design Architecture Description |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Conduct detailed sizing review with Siebel Expert Services | Y
|  | C.DS.080.2 | Design Software Components |  |  | Y
|  | C.DS.090.2 | Design Data |  | DESIGN Stage: Data Mapping: - Document User Interface/Business Object Data Mapping - Review Data Mapping Application Design: - Prepare for Configuration Kickoff - Map Physical Data Model - Design Report Definitions | Y
|  | C.DS.100.2 | Design Behavior |  |  | Y
|  | C.DS.110.2 | Design Business Rules |  | DESIGN Stage: Application Design: - Design VB/COM Business Rules Workflow/Business Rule Design: - Design Workflow Manager Policies/Rules - Prepare for Workflow Manager Design Review - Design State Models - Design Assignment Objects, Rules - Conduct Assignment Manager Design Review | Y
|  | C.DS.130.2 | Design User Interface |  | DESIGN Stage: Application Design: - Design User Interface | Y
|  | C.DS.140.2 | Prepare Design Specification |  | DESIGN Stage: Application Design: - Prepare for Configuration Design Review with Siebel Expert Services | Y
|  | C.DS.150.2 | Develop Database Design |  | DESIGN Stage (Interface Design) Review Interface Requirements: - Design Recurring Data Interfaces - Document EIM mappings - Review mappings with application design team - Document EIM Processing Design - Design Archival Strategy and Interfaces - Prepare for EIM Mapping and Design Processing Review | Y
|  | C.DS.160.2 | Review Design Model |  | DESIGN Stage: Conduct Design Review with Expert Services | Y
| C.ACT.PTP Perform Test Planning |  |  |  |  | Y
|  | C.TE.015.2 | Develop Integration Test Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Define Business Scenarios - Define Data requirements - Project Plan - High-level test cases - Test Plan | Y
|  | C.TE.050.2 | Develop System Test Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Define Business Scenarios - Define Data requirements - Project Plan - High-level test cases - Test Plan | Y
| C.ACT.PEC Prepare Environments - Construction |  |  |  |  | Y
|  | C.IM.007.2 | Prepare Development Environment |  | CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Create Development Environment - Build Development Database | Y
|  | C.TE.018.2 | Prepare Static Test Data |  | DESIGN Stage (Test Strategy DK) Data Model - Assist in developing data model for testing - Transfer Data Model | Y
|  | C.TE.038.2 | Prepare Integration Test Environment |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Functional Testing DK) - Configure\Validate Functional Test Environment | Y
| C.ACT.DCCTSC Develop Custom Component Test Scripts - Construction |  |  |  |  | Y
|  | C.TE.020.2 | Develop Unit Test Scripts |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
|  | C.TE.035.2 | Create Integration Test Scenarios |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
C.ACT.DSTSC Develop System Test Scenarios - Construction
|  | C.TE.025.3 | Create System Test Scenarios |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment - Detail Test Case Development - Sign-off on test cases | Y
| C.ACT.DSITS Develop Systems Integration Test Scenarios |  |  |  |  | Y
|  | C.TE.090 | Develop Systems Integration Test Scenarios |  | CONFIGURE Stage (Functional Testing DK) SIT: - Modify & run script | Y
| C.ACT.ICC Implement Custom Components |  |  |  |  | Y
|  | C.IM.040.2 | Implement Database |  | CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Build Development Database Solution Configuration-Customized Physical Database: - Implement Database Extensions to User Tables - Create EIM IF Table Extensions and Related Mappings | Y
|  | C.IM.050 | Implement Components |  | CONFIGURE Stage (Solution Configuration) Configured Application and Reports: - Configure Application and Reports for User Review Session 1 (URS) - Conduct URS 1 - Obtain and Document User Feedback - Refine Application and Reports - Conduct Final URS - Obtain User Sign Off on Application and Reports for Final URS | Y
|  | C.IM.055.2 | Perform Business Rules Implementation (Rules Engine) |  | CONFIGURE Stage (Solution Configuration) Assignment Manager Rules: - Review and set object parameters - Set up/Review Organization/Position hierarchies - Create Assignment Rules/Criteria Workflow Manager Rules: - Review/configure Workflow objects in Tools - Modify/create Programs in Tools (if needed) - Create Workflow Manager Policies | Y
|  | C.IM.060.2 | Perform Component Review |  | CONFIGURE Stage - Conduct Workflow Manager Implementation Review - Conduct EIM Configuration & Performance Review - Review configuration with expert services | Y
|  | C.IM.070 | Assemble Components |  | CONFIGURE Stage (Solution Configuration) Remote Synchronization: - Set Remote Synchronization System Preferences - Customize Remote Synchronization Rules If Necessary Interface Development (Recurring Interfaces): - Obtain sample data set from source locations - Create Program to Load Interface Tables - Create IFB Control Files for Import/Update Interfaces - Create IFB Control Files for Export Interfaces - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
|  | C.IM.080 | Integrate Services |  | CONFIGURE Stage (Solution Configuration) Remote Synchronization: - Set Remote Synchronization System Preferences - Customize Remote Synchronization Rules If Necessary Interface Development (Recurring Interfaces): - Obtain sample data set from source locations - Create Program to Load Interface Tables - Create IFB Control Files for Import/Update Interfaces - Create IFB Control Files for Export Interfaces - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
|  | C.IM.090 | Create Installation Routines |  | CONFIGURE Stage (Solution Configuration) Remote Synchronization: - Set Remote Synchronization System Preferences - Customize Remote Synchronization Rules If Necessary Interface Development (Recurring Interfaces): - Obtain sample data set from source locations - Create Program to Load Interface Tables - Create IFB Control Files for Import/Update Interfaces - Create IFB Control Files for Export Interfaces - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
|  | C.TE.065 | Perform Installation Test |  | CONFIGURE Stage (Solution Configuration) Functional Testing DK - Configure\Validate Functional Test Environment | Y
| C.ACT.PCCTC Perform Custom Component Testing - Construction |  |  |  |  | Y
|  | C.TE.030.2 | Perform Unit Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop X (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
|  | C.TE.040.2 | Perform Integration Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop X (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
| C.ACT.PST Prepare for System Test |  |  |  |  | Y
|  | C.MC.050.2 | Define Application Setups |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Review Siebel administration screens to identify appropriate reference data - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items - Define and document reference data (list of values) - Document Multi-National Formats and Localization Plan. CONFIGURE Stage (Solution Configuration) Data Administration: - Create Reference Data from Design - Create required Marketing Admin Data - Create Required Mobile Client Admin Data - Create and Set up Literature Files and Correspondence Templates on File Server - Create Application Meta-Data for In-Scope Siebel Modules | Y
|  | C.TE.060.2 | Prepare System Test Environment |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Functional Testing DK) - Configure\Validate Functional Test Environment | Y
C.ACT.PSTC Perform System Test - Construction
|  | C.TE.070.2 | Perform System Test |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... N:F330 - Modify & run script - Analyze Test Results - Report results of test | Y
|  | C.RA.055.2 | Document Business Procedures |  |  |  | Y
|  | C.TE.019.2 | Collect, Assess and Refine KPI Measurements |  |  |  | Y
| C.ACT.PSIT Perform Systems Integration Test |  |  |  |  | Y
|  | C.TE.085 | Prepare Systems Integration Test Environment |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Solution Configuration) Setup Development Environment (Discover Stage): - Create Development Environment | Y
|  | C.TE.100 | Perform Systems Integration Test |  | CONFIGURE Stage (Functional Testing DK) SIT: - Analyze Test Results - Report results of test | Y
| C.ACT.PPT Prepare for Performance Testing |  |  |  |  | Y
|  | C.PT.070 | Build Performance Test Scripts and Programs |  | VALIDATE Stage (Performance Testing DK) Configure\Validate Performance Test Environment: - Detail Test Case Development - Create Test scripts - Sign-off on scripts | Y
|  | C.PT.080 | Construct Performance Test Environment and Database |  | VALIDATE Stage (Performance Testing DK) - Configure\Validate Performance Test Environment | Y
|  | C.PT.090 | Conduct Performance Test Dress Rehearsal
C.ACT.PT Prepare for Transition
|  | C.TA.100 | Define System Management Procedures |  | DESIGN Stage Application Support Design: - Define Help Desk Process - Design End-User Documentation - Design Run Book for Operations Staff | Y
|  | C.TA.110 | Define Operational Testing Plan |  | DESIGN Stage (Test Strategy DK) Test Plan Build: - Test Plan | Y
|  | C.TA.150 | Define Final Platform and Network Architecture |  | DISCOVER Stage (Interface, Data, and Architecture Requirements) Identify System Capacity and Architecture Requirements: - Conduct detailed sizing review with Siebel Expert Services | Y
|  | C.TA.160 | Define System Capacity Plan |  | VALIDATE Stage (Performance Testing DK) Performance Test: - PT results report Stress Test - ST results report Longevity Test - LT results report | Y
| C.ACT.PCO Prepare for Cutover |  |  |  |  | Y
|  | C.TS.020.2 | Define Cutover Strategy |  | CONFIGURE Stage (Deployment DK (Deployment Preparation)) Deployment Plans: - Develop Deployment Plan - Identify Resources Required for Deployment - Sign off Deployment Plan DESIGN Stage (Deployment Design DK (Proposed)) Application Data Administration: - Siebel Reporting Hierarchy (Positions and Divisions, MultiOrg) - Define Application Users - Identify Literature Items - Define and document reference data (list of values) - Document Multi-National Formats and Localization Plan. - Review Siebel administration screens to identify appropriate reference data | Y
|  | C.TS.030 | Develop Installation Plan |  | DESIGN Stage (Deployment Design DK (Proposed)) - Design/Plan Dev to Prod Migration | Y
|  | C.TS.040 | Design Production Support Infrastructure |  | Ongoing Project Infrastructure Support (Schedule in Discover through Deploy Stages) - Administer Database - Administer Server - Administer Network - Support Desktop Environment - Administer Application | Y
| C.ACT.TI Test Infrastructure |  |  |  |  | Y
|  | C.TA.120 | Conduct Operational Testing |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
|  | C.TA.130 | Conduct Backup and Recovery Test |  |  | Y
|  | C.TA.140 | Conduct Disaster Recovery Test |  |  | Y
| C.ACT.PACDC Prepare to Acquire and Convert Data - Construction |  |  |  |  | Y
|  | C.CV.027.2 | Perform Data Mapping |  | DESIGN Stage (Interface Design) - Document EIM mappings | Y
|  | C.RA.170.2 | Conduct Data Quality Assessment |  | DESIGN Stage (Solution Design DK) Conversion Design: - Define Data Cleansing Plan CONFIGURE Stage (Solution Configuration) Interface Development (Recurring Interfaces) - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
|  | C.CV.035.2 | Define Manual Conversion Procedures (Initial Load) |  |  |  | Y
|  | C.CV.040.2 | Design Conversion Components (Initial Load) |  | DESIGN Stage (Solution Design DK) Conversion Design: - Design Initial Data Load - Review Mappings with Application Design Team - Document EIM Processing Design | Y
|  | C.CV.050.2 | Prepare Conversion Test Plans (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... N: - Modify & run script - Analyze Test Results - Report results of test | Y
| C.ACT.ACDC Acquire and Convert Data-Construction |  |  |  |  | Y
|  | C.CV.030.2 | Prepare Conversion Environment (Initial Load) |  | DESIGN Stage (Test Strategy DK) Software & Hardware Requirements: - Test Environment review CONFIGURE Stage (Functional Testing DK) - Configure\Validate Functional Test Environment | Y
|  | C.CV.055.2 | Implement Conversion Components (Initial Load) |  | CONFIGURE Stage (Solution Configuration) Conversion Development: - Create Extract Program(s) - Consolidate Data from Disparate Systems If Desired - Perform Pre-processing of Data as Required - Create IFB Control Files for Conversions - Adjust Conversion Programs Based on Unit Test Results | Y
|  | C.CV.060.2 | Perform Conversion Component Unit Test (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script - Analyze Test Results - Report results of test | Y
|  | C.CV.062.2 | Perform Conversion Component Business Object Test (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script | Y
|  | C.CV.063.2 | Perform Conversion Component Validation Test (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script | Y
|  | C.CV.064.1 | Install Conversion Components (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script | Y
|  | C.CV.065.1 | Convert and Verify Data (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Analyze Test Results - Report results of test | Y
|  | C.CV.068.1 | Clean Data |  | CONFIGURE Stage (Solution Configuration) Interface Development (Recurring Interfaces) - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
| C.ACT.PD Produce Documentation |  |  |  |  | Y
|  | C.DO.060 | Publish User Reference Manual |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Support Design: - Define Help Desk Process | Y
|  | C.DO.070 | Publish User Guide |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Support Design: - Design End-User Documentation | Y
|  | C.DO.080 | Publish Technical Reference Material |  | DESIGN Stage (Deployment Design DK (Proposed)) Application Support Design: - Design Run Book for Operations Staff | Y
|  | C.DO.100 | Produce Online Help |  |  |  | Y
| C.ACT.DCMRCCC Deploy Change Management Roadmap and Communication Campaign - Construction |  |  |  |  | Y
|  | C.OCM.150.3 | Conduct Change Management Roadmap and Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan | Y
|  | C.OCM.155.2 | Monitor Change Management Roadmap and Communication Campaign Effectiveness |  | Ongoing Project Management DK (All stages) Ongoing Project Management (Schedule in Discover through Deploy Stages): - Manage Change Control - Manage Project Risk/issue log maintenance - Conduct Project Status Meetings - Manage day-to-day Issues and Meetings | Y
| C.ACT.CJIA Conduct Job Impact Analysis |  |  |  |  | Y
|  | C.OCM.170 | Collect and Analyze Job Change Data |  |  |  | Y
|  | C.OCM.180 | Determine Impact of Job Changes |  | DISCOVER Stage (Business Requirements DK) Business Process-Function-Conduct Business Process-Function Workshops (repeat for each) Develop Solution Review Kits: - Review Solutions for Impact Analysis |  | Y
|  | C.OCM.190 | Prepare HR Transition Plan |  |  |  | Y
| C.ACT.CMAWC Conduct Managers Alignment Workshop - Construction | [5 empty] | Y
|  | C.OCM.200 | Design Managers Unit and Department Impact Workshop |  |  |  | Y
|  | C.OCM.210 | Conduct Managers Unit and Department Impact Workshop |  | DISCOVER Stage (Business Requirements DK) Business Process-Function-Conduct Business Process-Function Workshops (repeat for each) Develop Solution Review Kits: - Review Solutions for Impact Analysis |  | Y
| C.ACT.DEUT Design End-User Training |  |  |  |  | Y
|  | C.TR.060 | Conduct User Learning Needs Analysis |  |  | Y
|  | C.TR.070 | Develop User Learning Plan |  | CONFIGURE STAGE (End User Training Development (SEE)) - Develop Training Modules | Y
| C.ACT.BEUT Build End-User Training |  |  |  |  | Y
|  | C.TR.080 | Develop User Learningware |  | CONFIGURE STAGE (End User Training Development (SEE)) - Develop Training Exercises - Insert Screen Shots - Review Training Materials - Walk Through Training Materials - Adjust Training Materials - Insert Training Notes - Walk through finalized training material - Sign off Training course and materials | Y
|  | C.TR.090 | Prepare User Learning Environment |  | CONFIGURE STAGE (End User Training Development (SEE)) - Create Training Database - Create Training Installation Kit | Y
| C.ACT.IOCM Initial Operational Capability Milestone Summary |  |  |  |  | Y
|  | C.PMC.IOCM | Initial Operational Capability Milestone |  | CONFIGURE STAGE (End User Training Development (SEE)) - Sign off Training course and materials VALIDATE Stage Testing Sign-off: - Customer Sign-off Deployment DK (Deployment Preparation)-Deployment Plans -Sign off Deployment Plan | Y
D Transition
| D.ACT.SUAT Support User Acceptance Test |  |  |  |  | Y
|  | D.TE.105 | Prepare Users for Testing |  |  | Y
|  | D.TE.110 | Prepare Acceptance Test Environment |  | VALIDATE Stage (UAT Testing (Functional Test DK)) - Configure\Validate UAT Test Environment | Y
|  | D.TE.120 | Support Acceptance Test |  | VALIDATE Stage (Performance Testing DK) Testing Sign-off_ - Transfer of test scripts - Customer Sign-off | Y
| D.ACT.CPTST Conduct Performance Test |  |  |  |  | Y
|  | D.PT.100 | Execute Performance Test |  | VALIDATE Stage (Performance Testing DK) Performance Test - PT Modify & run script - PT Analyze Test Results Stress Test - ST Modify & run script - ST Analyze Test Results Longevity Test - LT Modify & run script - LT Analyze Test Results | Y
|  | D.PT.110 | Create Performance Test Report |  | VALIDATE Stage (Performance Testing DK) Performance Test - PT results report Stress Test - ST results report Longevity Test - LT results report Testing Sign-off - Transfer of test scripts - Customer Sign-off | Y
| D.ACT.PPE Prepare Production Environment |  |  |  |  | Y
|  | D.TS.050 | Prepare Production Environment |  | VALIDATE Stage (Deployment DK (Deployment Preparation)) Set Up Production Environment (Hardware and Software) - Build Production Database - Install Siebel Software in Production Environment Prepare for Production Pilot - Migrate Repository into Production Environment - Customize Physical Database - Convert Data for Production Pilot - Configure Servers and Client Machines - Create Setup Data in Production Environment Remote Synchronization: - Set Remote Synchronization System Preferences - Customize Remote Synchronization Rules If Necessary - Unit Test Remote Synchronization Rule Changes - Generate Triggers in Production Environment - Run Assignment Manager for Initial Assignments | Y
| D.ACT.CDT Convert Data - Transition |  |  |  |  | Y
|  | D.CV.064.2 | Install Conversion Components (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Modify & run script | Y
|  | D.CV.065.2 | Convert and Verify Data (Initial Load) |  | CONFIGURE Stage (Functional Testing DK) Configure\Validate Functional Test Environment-Drop 1, 2, 3, ... (for each development) - Analyze Test Results - Report results of test | Y
|  | D.CV.068.2 | Clean Data |  | CONFIGURE Stage (Solution Configuration) Interface Development (Recurring Interfaces) - Review/Adjust Data Cleansing Plan Based on Interface Unit Test Results | Y
| D.ACT.DCMRCCT Deploy Change Management Roadmap and Communication Campaign - Transition |  |  |  |  | Y
|  | D.OCM.150.4 | Conduct Change Management Roadmap and Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan | Y
|  | D.OCM.155.3 | Monitor Change Management Roadmap and Communication Campaign Effectiveness |  | Ongoing Project Management DK (All stages) Ongoing Project Management (Schedule in Discover through Deploy Stages): - Manage Change Control - Manage Project Risk/issue log maintenance - Conduct Project Status Meetings - Manage day-to-day Issues and Meetings | Y
| D.ACT.CITA Conduct IT Alignment | [5 empty] | Y
|  | D.OCM.220 | Prepare Assessment of Impact on IT Groups |  |  |  | Y
|  | D.OCM.230 | Prepare IT Transition Plan |  |  |  | Y
| D.ACT.TEUT Train End Users - Transition |  |  |  |  | Y
|  | D.TR.100.2 | Conduct User Learning Events |  | CONFIGURE STAGE (End User Training Development (SEE)) - Sign off Training course and materials | Y
| D.ACT.FD Finalize Documentation |  |  |  |  | Y
|  | D.DO.110 | Finalize Documentation |  |  | Y
| D.ACT.GP Go Production |  |  |  |  | Y
|  | D.TS.052 | Implement Production Support Infrastructure |  | VALIDATE Stage (Deployment DK (Deployment Preparation)) Data Administration: - Create Reference Data from Design - Create required Marketing Admin Data - Create Required Mobile Client Admin Data - Create and Set up Literature Files and Correspondence Templates on File Server - Create Application Meta-Data for In-Scope Siebel Modules | Y
|  | D.TS.058 | Verify Production Readiness |  | VALIDATE Stage (Deployment DK (Deployment Preparation)) Prepare for Production Pilot: - Perform Production Readiness Review with Siebel Expert Services - Review Cut over and System Usage - Review Production Readiness with Expert Services - Obtain Customer Signoff to Begin Pilot | Y
|  | D.TS.060 | Go Production |  | DEPLOY Stage (Production Pilot DK) Begin Production Pilot - Update Converted Production Data If Necessary - Train Pilot Users - Install/Update Software on Pilot User Machines | Y
|  | D.TS.070 | Shut Down Legacy System |  |  | Y
| D.ACT.SIP System in Production Milestone Summary |  |  |  |  | Y
|  | D.PMC.SIP | System in Production Milestone |  | VALIDATE Stage (Deployment DK (Deployment Preparation)) - Implementation Readiness Review | Y
E Production | [5 empty] | Y
| E.ACT.MPSP Manage Production System Performance |  |  |  |  | Y
|  | E.PT.120 | Conduct Production Performance Management |  | DEPLOY Stage (Production Pilot DK) Support Production Pilot: - Monitor System | Y
| E.ACT.EPS Evaluate Production System |  |  |  |  | Y
|  | E.TE.019.2 | Collect, Assess and Refine KPI Measurements |  |  | Y
|  | E.PS.010 | Audit System |  | Implementation Effectiveness Review DK (Proposed) - Implementation Effectiveness Diagnostic | Y
| E.ACT.RPP Resolve Production Problems |  |  |  |  | Y
|  | E.PS.050 | Analyze Problems |  | Implementation Effectiveness Review DK (Proposed) - Implementation Effectiveness Review | Y
|  | E.PS.060 | Monitor and Respond to System Problems |  | DEPLOY Stage (Production Pilot DK) Support Production Pilot: - Monitor System - Support End Users - Review System Usage and Problem Reports - Conduct Pilot Review Sessions with End Users - Document end user feedback and prioritize change requests - Make system changes as required. | Y
| E.ACT.DCMRCCP Deploy Change Management Roadmap and Communication Campaign - Production |  |  |  |  | Y
|  | E.OCM.150.5 | Conduct Change Management Roadmap and Communication Campaign |  | DEFINE Stage (Project Startup DK) - Develop Client Communications Plan | Y
|  | E.OCM.155.4 | Monitor Change Management Roadmap and Communication Campaign Effectiveness |  | Ongoing Project Management DK (All stages) Ongoing Project Management (Schedule in Discover through Deploy Stages): - Manage Change Control - Manage Project Risk/issue log maintenance - Conduct Project Status Meetings - Manage day-to-day Issues and Meetings | Y
| E.ACT.PF Plan for Future | [5 empty] | Y
|  | E.PS.135 | Determine Future Functional Enhancements |  |  |  | Y
|  | E.PS.140 | Plan Enhancements |  |  |  | Y
|  | E.OCM.250 | Measure Organizational Change Effectiveness |  | Implementation Effectiveness Review DK (Proposed) - Implementation Effectiveness Review |  | Y
| E.ACT.DITTP Deploy IT Transition Plan | [5 empty] | Y
|  | E.OCM.260 | Implement IT Transition Plan |  |  |  | Y
| E.ACT.SO Sign Off Milestone Summary |  |  |  |  | Y
|  | D.PMC.SO | Sign Off Milestone |  |  | Y
PC Project Closure
| PC.ACT.GA Gain Acceptance |  |  |  |  | Y
|  | PC.SM.050 | Gain Acceptance |  | DEPLOY Stage (Project Closeout DK) - Prepare Project Closeout Checklist - Survey End User Satisfaction - Final Customer Signoff | Y
| PC.ACT.CPC Close Processes and Contract |  |  |  |  | Y
|  | PC.SM.060 | Close Scope Management |  |  | Y
|  | PC.SM.070 | Identify Future System Enhancements |  |  | Y
|  | PC.FM.050 | Close Project Financials |  |  | Y
|  | PC.WM.060 | Close Work Management |  |  | Y
|  | PC.RKM.060 | Conduct Post-Production Risk Assessment |  |  | Y
|  | PC.IPM.050 | Produce Final Issue and Problem Report and Close Log(s) |  |  | Y
|  | PC.STM.070 | Release Staff |  |  | Y
|  | PC.QM.060 | Conduct Post-Production Quality Review |  |  | Y
|  | PC.CM.080 | Close Configuration Management |  |  | Y
|  | PC.IFM.050 | Close Infrastructure |  |  | Y
|  | PC.PCM.040 | Close Contract |  |  | Y
|  | PC.OCHM.040 | Establish Follow-Up Process |  |  | Y
| PC.ACT.DLLAP Document Lessons Learned and Archive Project |  |  |  |  | Y
|  | PC.CMM.040 | Document Lessons Learned |  |  |  | Y
|  | PC.CMM.050 | Turn Over Project Documentation (Project Archives) |  | DEPLOY Stage (Project Closeout DK) - Archive Project Files | Y
|  | PC.CMM.060 | Submit Final Reports |  | DEPLOY Stage (Project Closeout DK) - Write Project Profile Report | Y
PGM Program Management
| PGM.ACT.PGM Perform Program Management |  |  |  |  | Y
|  | PGM.PMC.PGMSUM1 | Perform Program Management Activities |  |  | Y