## RACI
RACI (Responsible, Accountable, Consulted, Informed)
# | Task | Project Steering Board | Technical Architects | Business Analysts / Product Specialists | Ambassador Users | Comments
Inception
| Gather Business Requirements - Inception | I | R/A | R | C
| Detail Business and System Objectives | A | C | C | R | Project Steering Committee will work with Ambassador Users to finalize.
| Prioritize Requirements (MoSCow) | R/A | C | C | A | Steering Committee will maintain master list of priorities. Ambassador Users will be familiar with and validate the requirements throughout the life of the project.
| Develop Conceptual Prototype (BRD) | C/A | C | R | R | Business Analysts and Product Specialists will work on the Conceptual Prototypes.
| Validate Conceptual Prototype (BRD) | I | C | R | C | PM will schedule and conduct reviews of BRD after Product Specialists have prepared for prototypes.
Elaboration
| Analyze - Elaboration | I | R/A | R/A | C
| Design - Elaboration | I | R/A | R/A | C
Note on B2: This can be any task, topic, activity or process, for which you want to designate a level of responsibility.
Note on C2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on D2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on E2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on C4: R,A,C, or I: See Definitions in the second sheet in this workbook.

## DEFINITIONS
DEFINITIONS
R = | Responsible. Those who perform or support the task; person(s) that 'own' the task or activity or solution and are responsible for its completion.
A = | Accountable. Those who are ultimately accountable for the correct and thorough completion of the task or activity; person(s) to whom "R" is accountable (there can be only one "A" per task or activity)
C = | Consulted. Those who have information necessary to complete the work; person(s) whose opinions are sought (two-way communication).
I = | Informed. Those who are notified of the results but need not be consulted; the person(s) who are kept up to date on progress (one-way communication).