## RACI
RACI (Responsible, Accountable, Consulted, Informed)
# | Task | Purchasing Dept. | Accounting Dept | Warehouse Manager | Ambassador Users | Comments
Inception
| Detail Business and System Objectives | R/A | C | C | A | Purchasing will represent the global business for the functionality of the SuD.
| Prioritize Requirements (MoSCoW) | R/A | C | C | A | Purchasing will maintain master list of priorities.
| Develop Conceptual Prototype (BRD) | C/A | C | C | R | Ambassador Users will create BRDs with help from Oracle Team.
| Validate Conceptual Prototype (BFD) | A | A | A/C | R | Ambassador Users will schedule and conduct reviews of BRD.
Elaboration
| Analyze - Elaboration | C | R/A | R/A | C
| Design - Elaboration | C | R/A | R/A | C
| Develop Functional Prototype (Functional Specs.) | I | R/A | R/A | I
| Validate Functional Prototype (Functional Specs.) | C | R/A | R/A | C
Construction
| Analyze - Construction | C | R/A | R/A | C
| Design - Construction | C | R/A | R/A | C
| Build | I | R/A | R/A | I
| Perform Unit Test | I | R/A | R/A | I
| Perform System Test | C | R/A | R/A | C
| Implement System | I | R/A | R/A | I
Transition
| Prepare for UAT | A/C | A/C | A/C | R | Oracle will prepare UAT environment working with Ambassador Users.
| Execute UAT | C | C/A | C/A | R | Ambassador Users will execute UAT scripts. Oracle will ensure there is a thorough testing.
| Build End-User Training | C/A | C | C | R | Ambassador Users will facilitate development of training.
| Build Global Communications | C | R/A | R/A | I | Ambassador Users will build global message.
| Execute Global Communications | I | I | I | R/A
| Disseminate Communications | I | I | I | R/A | Ambassador Users will send communications to their respective groups.
| Support Transition | C | C | C | R/A | Ambassador Users will serve as local experts for their respective groups.
Production
| Support Production System | I | R/A | R/A | I
Note on B2: This can be any task, topic, activity or process, for which you want to designate a level of responsibility.
Note on C2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on D2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on E2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on C4: R,A,C, or I: See Definitions in the second sheet in this workbook.

## DEFINITIONS
DEFINITIONS
R = | Responsible. Those who perform or support the task; person(s) that 'own' the task or activity or solution and are responsible for its completion.
A = | Accountable. Those who are ultimately accountable for the correct and thorough completion of the task or activity; person(s) to whom "R" is accountable (there can be only one "A" per task or activity)
C = | Consulted. Those who have information necessary to complete the work; person(s) whose opinions are sought (two-way communication).
I = | Informed. Those who are notified of the results but need not be consulted; the person(s) who are kept up to date on progress (one-way communication).