## RACI
RACI (Responsible, Accountable, Consulted, Informed)
# | Task | SOA Steering Board | Architecture Review Board | SOA Enablement Contract | Shared Services Department | Comments
Inception
| Detail Business and System Objectives | R/A | C | C | C | Department Heads will represent the global business.
| Prioritize Requirements (MoSCow) | R/A | C | C | C | Project Manager will maintain master list of priorities.
| Develop Conceptual Prototype (BRD) | C/A | C | C | R | Individual Departments will create BRDs with help from Oracle.
| Validate Conceptual Prototype (BRD) | R/A | C | C | C | PM will schedule & conduct reviews of BRD.
Elaboration
| Analyze - Elaboration | C | R/A | R/A | C
| Design - Elaboration | C | R/A | R/A | C
| Develop Functional Prototype (Functional Specs.) | I | R/A | R/A | I
| Identify New Service Opportunities | A | I | R | C | Recorded by Oracle OEA specializing in SOA.
| Develop Service Usage Plan | C | A | R | C
| Define Service Scope |  | R/A | R/A | C
| Define Service Specification | I | R/A | R/A | I
| Conduct Service Design Review | I | R/A | R/A | I
| Conduct SOA Project Review | C | R/A | R/A | C
| Conduct Service Design Review | I | R/A | R/A | I
| Conduct SOA Project Review | C | R/A | R/A | I
| Conduct Service Code Review | C | C/A | C/A | R
| Production Readiness Review | C/A | C | C | R
| Support Production System | I | R/A | R/A | I
Note on B2: This can be any task, topic, activity or process, for which you want to designate a level of responsibility.
Note on C2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on D2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on E2: Group: This can be any group who is either Responsible, Accountable, needs to be Consulted, or needs to be Informed. It can be a department, a specific group of users, or a specific group of key stakeholders.
Note on C4: R,A,C, or I: See Definitions in the second sheet in this workbook.

## DEFINITIONS
DEFINITIONS
R = | Responsible. Those who perform or support the task; person(s) that 'own' the task or activity or solution and are responsible for its completion.
A = | Accountable. Those who are ultimately accountable for the correct and thorough completion of the task or activity; person(s) to whom "R" is accountable (there can be only one "A" per task or activity)
C = | Consulted. Those who have information necessary to complete the work; person(s) whose opinions are sought (two-way communication).
I = | Informed. Those who are notified of the results but need not be consulted; the person(s) who are kept up to date on progress (one-way communication).