## Tracking
FM.030 Expense Tracking Spreadsheet
[10 empty] | 2009 | 2010 | [11 empty] | 2010 | 2011 | [11 empty] | 2011 | 2012 | 2013 | 2014 | Total
<Project Name> |  | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Total | Total | Total | Total | All Years
Expense
1 | Budget (Plan) |  | 30 | 30 | 30 | 30 | 20 | 10 |  | 150 | [12 empty] | 0 | [12 empty] | 0 | 0 | 0 | 0 | 150
2 | Actual to date |  | 28 | 27 | [5 empty] | 55 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 55
3 | Estimate to Complete (Outlook) |  |  |  | 30 | 30 | 20 | 10 |  | 90 | [12 empty] | 0 | [12 empty] | 0 |  |  |  | 90
4 | Estimate at Completion (2+3) | [38 empty] | 145
5 | Variance at completion (1-4) | [38 empty] | 5

## Metric
Budget Variance Metric
$000 | Budget | Actual | ETC | EAC | VAC
Cummulative Expenses | 150 | 55 | 90 | 145 | 5
Note on B2: Total Budget
Note on C2: Actual to Date
Note on D2: Estimate to Complete
Note on E2: Estimate at Completion
Note on F2: Variance at Completion