## Time Sheet
<Project Name> Weekly Time Sheet
<Team Member>
For Week Ending:
Planned Activities |  | Hours Expended | [7 empty] | Task Status
WBS Task ID | WBS Task | Mon | Tue | Wed | Thur | Fri | Sat | Sun | Week Tot Actual Hrs | Plan EAC Hrs | Plan Actual Hrs To Date | Rev Tot Hrs to Date | ETC Hrs | Rev EAC Hrs | % Comp | Hrs Var | Actual Start | EAC Finish | Actual Finish
1.00.01 | Task 1 | 4 | [6 empty] | 4 | 75 | 60 | 64 | 16 | 80 | 80% | -5 | 2008-12-15 | 2009-01-22
2.00.01 | Task 2 |  | 8 |  | 8 |  |  |  | 16 | 60 | 40 | 56 | 8 | 64 | 87.5% | -4 | 2008-12-15 | 2009-01-22
3.00.01 | Task 3 |  |  | 2 |  |  |  |  | 2 | 60 | 40 | 42 | 0 | 42 | 100% | 18 | 2008-12-15 | 2009-01-12 | 2009-01-12
4.00.01 | Task 4 |  |  | 4 |  |  |  |  | 4 | 30 | 40 | 44 | 0 | 44 | 100% | -14 | 2008-12-15 | 2009-01-12 | 2009-01-12
5.00.01 | Task 5 |  |  | 2 |  |  |  |  | 2 | 40 | 20 | 22 | 18 | 40 | 55% | 0 | 2008-12-19 | 2009-01-12 | 2009-01-12
6.00.01 | Task 6 |  |  |  |  | 8 |  |  | 8 | 16 | 4 | 12 | 4 | 16 | 75% | 0 | 2008-12-10 | 2009-01-29
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
[9 empty] | 0 |  |  | 0 |  | 0 | #DIV/0! | 0
Unplanned Activities
Approved (Y/N) | Description | Status
Y | Unplanned activity | 4 | [6 empty] | 4 | [7 empty] | 2009-01-16 |  | 2009-01-16
0
0
0
0
Total Labor Hours for the Week |  | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 40

## Instructions
Project Team Member
On a weekly basis, enter time spent on both planned (per the project's workplan) and unplanned activities.
Planned activities: 1. Enter all tasks and their IDs that you worked on during the week - use the project workplan's task name and ID. Enter time spent each day on the task - totals for the task, the day and the week will be calculated. From the workplan view provided by the project manager, enter the Planned Hrs and Hrs to Date. Enter your ETC Hrs if different than provided in the workplan view - otherwise, enter this amount from the workplan view. The Tot Hrs to Date and EAC Hrs will be calculated. 2. Enter your Actual Start Date if the task started this week; otherwise enter the Actual Start Date from the view provided by the project manager. If the task is completed, enter the Actual Finish Date; otherwise leave this blank. If your finish date differs from Planned Finish Date given in the view, enter the new date in the EAC Finish Date.
Unplanned activities: Enter whether the unplanned activity was approved, a brief one sentence description, the time expended and the actual date and actual finish date. Note: All unplanned activities are considered 100% complete the week they are reported (as they are unplanned).
Project Manager
On a weekly basis, provide a two week at a glance view of the project workplan to the team and capture time spent on both planned (per the project's workplan) and unplanned activities.
Planned Activities: 1. On a weekly basis, provide a project workplan view to the team member(s) giving a two week at a glance of planned activities and their tasks. This needs to include at a minimum: Planned Start, Planned Finish, Planned Hours, Hours to Date, ETC Hours and EAC Hours. It is also recommended to include baseline information: Baseline Start, Baseline Finish, and Baseline Hours in the view for the team member(s)' information even though this will not be included in the weekly time sheet. This view would typically be distributed at the start of the week after the project workplan had been updated. 2. At the end of the week, collect the completed weekly time sheet, review and approve it and then enter updates to the project workplan - Actual Hrs, ETC Hrs, Actual Start, Planned Finish (based on EAC Finish) and Actual Finish. If you do not approve any of the entries, return the time sheet to the submitter for correction and then enter the corrections. If there is an Actual Finish Date, the task should be considered 100% complete and all Remaining Hours should be removed. Note: updates to the ETC hours and Actual Start, EAC Finish and Actual Finish dates may impact the critical path. Critical path should be reviewed weekly.
Unplanned Activities: Enter the unplanned activity in the Unplanned Activities section of the project workplan. Use the description for the task's name, Actual Hrs, Actual Start Date and Actual Finish Date. Note: all unplanned activities are considered 100% complete the week they are reported. If additional work is required on the activity, this task should be considered planned and added to the project workplan where appropriate.
On a monthly basis, audit the weekly time sheets against time entered in Project Accounting and make adjustments where applicable.
Password for both sheets is timesheet.