## Compass to Manage
Compass |  |  |  |  | OUM Manage
Phase | Activity | Step | WBS | Thread | Phase | Task Name
Stra
Stra | Pre-Qualify | Assess Customer Qualification |  | PS
Stra
Stra | Qualify | Conduct Initial Conversation/Contact with Customer |  | PS
Stra | Discovery | Conduct Customer Survey/Develop PS Account Strategy (PSC Only) |  | PS
Stra
Stra | Lead and Control | Execute Strategy Workshops |  | PS
Stra | Lead and Control | Estimate Client Return on Investment and Total Cost of Ownership (PSC only)
Stra | Lead and Control | Estimate Project (PSC only) |  |  | A | FM.010 Refine Project Budget
Stra | Lead and Control | Estimate PeopleSoft Consulting Financial Return (PSC only) |  |  | A | FM.010 Refine Project Budget
Stra | Lead and Control | Develop Proposal (PSC only)
Stra
Stra | Selection | Present Proposal to Client |  | PS
Stra
Stra | Negotiation | Create and Administer Contracts |  | PS
Stra
Stra | (Sales) Close and Transition | Create and Administer Work Orders, and Internal Systems (PSC only)
Stra | (Sales) Close and Transition | Transition Information and Knowledge to Delivery |  |  | A | BT.010 Review and Analyze Bid Material
[5 empty] | A | BT.050 Review Contract with Customer
[5 empty] | A | BT.060 Review Project Approach with Customer
Plan
Plan | Execute Multi-Site Model Company Planning | Prepare for Multi-Site Model Company Planning |  | MS
Plan | Execute Multi-Site Model Company Planning | Gather Location Site Information
Plan | Execute Multi-Site Model Company Planning | Conduct Multi-Site Model Company Planning
Plan | Execute Multi-Site Model Company Planning | Document Multi-Site Model Company Planning Results
Plan | Execute Multi-Site Model Company Planning | Execute Multi-Site Model Company Complete
Plan
Plan | Execute Implementation Planning Workshop | Communicate, Coordinate, and Schedule Implementation Planning Workshop |  | PM
Plan | Execute Implementation Planning Workshop | Conduct Implementation Planning Workshop |  |  | A | BT.020 Review and Confirm Business Case
[5 empty] | A | BT.030 Identify Stakeholders
[5 empty] | A | BT.070 Create Project Management Plan
Plan | Execute Implementation Planning Workshop | Finalize and Distribute Implementation Planning Workshop Charter
Plan | Execute Implementation Planning Workshop | Execute Implementation Planning Workshop Complete
Plan
Plan | Execute Technology Assessment Workshop | Communicate, Coordinate, and Schedule Technology Assessment Workshop |  | TI
Plan | Execute Technology Assessment Workshop | Conduct Technology Assessment Workshop
Plan | Execute Technology Assessment Workshop | Finalize and Distribute Technology Assessment Report
Plan | Execute Technology Assessment Workshop | Execute Technology Assessment Workshop Complete
Plan
Plan | Close Planning Phase | Close Planning Phase |  | PM
Str
Str | Perform New Customer Launch | Conduct Administrative Setup | 1.1.1.1 | PM
Str | Perform New Customer Launch | Order Application Software | 1.1.1.2
Str | Perform New Customer Launch | Initiate Launch Meeting Preparation | 1.1.1.3
Str | Perform New Customer Launch | Perform PeopleSoft University Process | 1.1.1.4
Str | Perform New Customer Launch | Review Installation Requirements | 1.1.1.5
Str | Perform New Customer Launch | Conduct Launch Meeting | 1.1.1.6
Str | Perform New Customer Launch | Conduct Launch Termination | 1.1.1.7
Str | Perform New Customer Launch | Perform New Customer Launch Complete | 1.1.1.8
Str |  |  | 1.1.2
Str | Define Mission, Objectives, and Performance Measures | Define Project Mission Statement |  | PM
Str | Define Mission, Objectives, and Performance Measures | Define Project Objectives and Performance Measures
Str | Define Mission, Objectives, and Performance Measures | Define Mission, Objectives, and Performance Measures Complete
Str |  |  | 1.1.3
Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Assumptions |  | PM
Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Constraints
Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Risks |  |  | A | RKM.010 Develop Risk Management Plan
[5 empty] | A | RKM.020 Conduct Baseline Risk Assessment
Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Other Critical Path Projects
Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Assumptions, Constraints, Risks, and Other Critical Path Projects Complete
Str |  |  | 1.1.4
Str | Create Project Team | Validate Resource Requirements |  | PM | A | STM.010 Plan Resource Requirements
Str | Create Project Team | Define Roles and Responsibilities for Project |  |  | A | STM.010 Plan Resource Requirements
Str | Create Project Team | Assemble Project Team Members |  |  | A | STM.030 Staff the Project
Str | Create Project Team | Prepare for Project Team Kickoff Meetings |  |  | A | STM.040 Prepare Orientation Guide
Str | Create Project Team | Conduct Project Team Kickoff Meetings |  |  | BB | STM.050 Conduct Team Orientation
Str | Create Project Team | Create Project Team Complete
Str |  |  | 1.1.5
Str | Define Project Standards and Administration | Acquire Team Work Location |  | PM
Str | Define Project Standards and Administration | Install Implementation Tools
Str | Define Project Standards and Administration | Create Project Diary |  |  | A | CM.030 Create Project Documentation Management Plan
Str | Define Project Standards and Administration | Create Project Administration Guidelines |  |  | A | STM.020 Develop Staff Management Plan
Str | Define Project Standards and Administration | Define Issue Resolution Procedures |  |  | A | IPM.010 Develop Issue Management Strategy
[5 empty] | A | IPM.020 Develop Problem Management Strategy
[5 empty] | A | IPM.020 Develop Issue and Problem Management System
Str | Define Project Standards and Administration | Define Project Plan Maintenance Procedures |  |  | A | WM.020 Develop Work Management Execution and Control Processes and Policies
Str | Define Project Standards and Administration | Define Operating Agreements
Str | Define Project Standards and Administration | Define Technical Project Standards
Str | Define Project Standards and Administration | Define Project Standards and Administration Complete
Str |  |  | 1.1.6
Str | Create Quality Plan | Draft Quality Plan |  | PM | A | QM.010 Develop Quality Management Plan
Str | Create Quality Plan | Determine the Quality Review Process |  |  | A | QM.020 Develop and Document Quality Control and Reporting Process
Str | Create Quality Plan | Determine Quality Needs, Establish Quality Standards, and Design Quality Control Processes |  |  | A | QM.020 Develop and Document Quality Control and Reporting Process
Str | Create Quality Plan | Finalize Quality Plan |  |  | A | QM.010 Develop Quality Management Plan
Str | Create Quality Plan | Create Quality Plan Complete
Str |  |  | 1.1.7
Str | Create Organization and Business Process Change Management Plan | Define Organization Change Management Approach |  | PM | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str | Create Organization and Business Process Change Management Plan | Define Business Process Change Management Approach |  |  | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str | Create Organization and Business Process Change Management Plan | Establish Organization Change Management Procedures |  |  | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str | Create Organization and Business Process Change Management Plan | Establish Business Process Change Management Procedures |  |  | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str | Create Organization and Business Process Change Management Plan | Finalize and Document Organization and Business Process Change Management Plan |  |  | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str | Create Organization and Business Process Change Management Plan | Create Organization and Business Process Change Management Plan Complete |  |  | A | OCHM.010 Understand Customer's Organizational Change Management Strategy
Str |  |  | 1.1.8
Str | Create Functional Configuration and Scope Change Management Plan | Define Functional Configuration Change Management Approach |  | PM | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str | Create Functional Configuration and Scope Change Management Plan | Define Scope Change Management Approach |  |  | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str | Create Functional Configuration and Scope Change Management Plan | Establish Functional Configuration Change Management Procedures |  |  | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str | Create Functional Configuration and Scope Change Management Plan | Establish Scope Change Management Procedures |  |  | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str | Create Functional Configuration and Scope Change Management Plan | Finalize and Document Functional Configuration and Scope Change Management Plan |  |  | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str | Create Functional Configuration and Scope Change Management Plan | Create Functional Configuration and Scope Change Management Plan Complete |  |  | A | SM.020 Develop Scope Change Management Processes
[5 empty] | A | CM.010 Develop Configuration Management Strategy and Processes
Str |  |  | 1.1.9
Str | Create Software Configuration Management Plan for Project | Define Software Configuration Management Approach for Project |  | TA | A | CM.040 Create and Execute Software Configuration Management Plan
Str | Create Software Configuration Management Plan for Project | Establish Software Configuration Management Procedures for Project |  |  | A | CM.040 Create and Execute Software Configuration Management Plan
Str | Create Software Configuration Management Plan for Project | Finalize and Document Software Configuration Management Plan for Project |  |  | A | CM.040 Create and Execute Software Configuration Management Plan
Str | Create Software Configuration Management Plan for Project | Create Software Configuration Management Plan for Project Complete |  |  | A | CM.040 Create and Execute Software Configuration Management Plan
Str |  |  | 1.1.10
Str | Create Project Team Communication Plan | Assess Project Team Communication Requirements |  | PM | A | CMM.020 Develop Project Team Communication Plan
Str | Create Project Team Communication Plan | Develop Project Team Communication Tools |  |  | A | CMM.020 Develop Project Team Communication Plan
Str | Create Project Team Communication Plan | Develop Project Team Communication Plan |  |  | A | CMM.020 Develop Project Team Communication Plan
Str | Create Project Team Communication Plan | Create Project Team Communication Plan Complete |  |  | A | CMM.020 Develop Project Team Communication Plan
Str |  |  | 1.1.11
Str | Establish Technical Architecture Performance Requirements | Define Overall Technical Architecture Performance Requirements |  | TI
Str | Establish Technical Architecture Performance Requirements | Define Database Performance Requirements
Str | Establish Technical Architecture Performance Requirements | Define Network Performance Requirements
Str | Establish Technical Architecture Performance Requirements | Define Server and Workstation Performance Requirements
Str | Establish Technical Architecture Performance Requirements | Establish Technical Architecture Performance Requirements Complete
Str |  |  | 1.1.12
Str | Create Organization Communication Plan | Assess Organization Communication Requirements |  | PM | B | OCHM.030 Execute Change and Communication Plan
Str | Create Organization Communication Plan | Develop Organization Communication Tools |  |  | B | OCHM.030 Execute Change and Communication Plan
Str | Create Organization Communication Plan | Develop Organization Communication Plan |  |  | B | OCHM.030 Execute Change and Communication Plan
Str | Create Organization Communication Plan | Create Organization Communication Plan Complete |  |  | B | OCHM.030 Execute Change and Communication Plan
Str |  |  | 1.1.13
Str | Create External Communication Plan | Assess External Communication Requirements |  | PM | B | OCHM.030 Execute Change and Communication Plan
Str | Create External Communication Plan | Develop External Communication Tools |  |  | B | OCHM.030 Execute Change and Communication Plan
Str | Create External Communication Plan | Develop External Communication Plan |  |  | B | OCHM.030 Execute Change and Communication Plan
Str | Create External Communication Plan | Create External Communication Plan Complete |  |  | B | OCHM.030 Execute Change and Communication Plan
Str |  |  | 1.1.14
Str | Create Marketing Communication Plan | Assess Marketing Communication Requirements |  | PM
Str | Create Marketing Communication Plan | Develop Marketing Communication Tools
Str | Create Marketing Communication Plan | Develop Marketing Communication Plan
Str | Create Marketing Communication Plan | Create Marketing Communication Plan Complete
Str |  |  | 1.1.15
Str | Assess Business Needs and Impact | Obtain and Review Application Architecture |  | BP
Str | Assess Business Needs and Impact | Obtain Organization Business Process Models
Str | Assess Business Needs and Impact | Prepare for Needs Assessment Sessions
Str | Assess Business Needs and Impact | Conduct Needs Assessment Sessions
Str | Assess Business Needs and Impact | Document and Analyze Needs Assessment Results
Str | Assess Business Needs and Impact | Identify Potential Customization Requirements
Str | Assess Business Needs and Impact | Assess Business Needs and Impact Complete
Str |  |  | 1.1.16
Str | Perform Business Process Integration Modeling | Prepare for Business Process Integration Modeling Sessions |  | BP
Str | Perform Business Process Integration Modeling | Conduct Business Process Integration Sessions
Str | Perform Business Process Integration Modeling | Confirm and Finalize Business Process Integration Models
Str | Perform Business Process Integration Modeling | Document and Analyze Business Process Integration Modeling Results
Str | Perform Business Process Integration Modeling | Perform Business Process Integration Modeling Complete
Str |  |  | 1.1.17
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Multi-Site Model Company |  | PM
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Localizations
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Functional Applications
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Customizations
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Conversion
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Interfaces
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Reporting
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Workflow
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Graphical Style for Web
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Content Management
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Information Architecture
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Web Integration
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Application Security
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for System Security
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Project Team Training
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for End-User Training
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Communications
Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Testing
Str | Define Project Strategies and Plan Project Scope | Define Project Strategies and Plan Project Scope Complete
Str |  |  | 1.1.18
Str | Define Project Approaches | Define Help Desk/Knowledge Base Approach |  | PM
Str | Define Project Approaches | Define Go-Live Contingency Approach
Str | Define Project Approaches | Define Development Support Approach |  |  | A | IFM.010 Develop Infrastructure Management Plan
Str | Define Project Approaches | Define Production Support Approach
Str | Define Project Approaches | Define Cutover Approach
Str | Define Project Approaches | Define Disaster Recovery Approach
Str | Define Project Approaches | Define PeopleSoft Upgrade Approach
Str | Define Project Approaches | Define Project Approaches Complete
Str |  |  | 1.1.19
Str | Assess and Define Software Configuration Management Requirements and Impact | Identify Software Configuration Management Requirements |  | TI | B | CM.040 Create and Execute Software Configuration Management Plan
Str | Assess and Define Software Configuration Management Requirements and Impact | Assess Software Configuration Management Tools |  |  | B | CM.040 Create and Execute Software Configuration Management Plan
Str | Assess and Define Software Configuration Management Requirements and Impact | Document and Analyze Requirements and Current Environment Findings |  |  | B | CM.040 Create and Execute Software Configuration Management Plan
Str | Assess and Define Software Configuration Management Requirements and Impact | Identify Potential Upgrades and/or Changes to Software Configuration Management Processes |  |  | B | CM.040 Create and Execute Software Configuration Management Plan
Str | Assess and Define Software Configuration Management Requirements and Impact | Define Software Configuration Management Strategy |  |  | B | CM.040 Create and Execute Software Configuration Management Plan
Str | Assess and Define Software Configuration Management Requirements and Impact | Assess and Define Software Configuration Management Requirements and Impact Complete |  |  | B | CM.040 Create and Execute Software Configuration Management Plan
Str |  |  | 1.1.20
Str | Assess and Define Database Requirements and Impact | Identify Database Requirements |  | TI
Str | Assess and Define Database Requirements and Impact | Assess Existing Database
Str | Assess and Define Database Requirements and Impact | Document and Analyze Requirements and Current Environment Findings
Str | Assess and Define Database Requirements and Impact | Identify Potential Database Upgrades
Str | Assess and Define Database Requirements and Impact | Define Database Strategy
Str | Assess and Define Database Requirements and Impact | Assess and Define Database Requirements and Impact Complete
Str | Assess and Define Database Requirements and Impact |  | 1.1.21
Str | Assess and Define Network Requirements and Impact | Identify Network Requirements |  | TI
Str | Assess and Define Network Requirements and Impact | Assess Existing Network
Str | Assess and Define Network Requirements and Impact | Document and Analyze Requirements and Current Environment Findings
Str | Assess and Define Network Requirements and Impact | Identify Potential Network Upgrades
Str | Assess and Define Network Requirements and Impact | Define Network Strategy
Str | Assess and Define Network Requirements and Impact | Assess and Define Network Requirements and Impact Complete
Str |  |  | 1.1.22
Str | Assess and Define Server and Workstation Requirements and Impact | Identify All Impacted Server and Workstation Components |  | TI
Str | Assess and Define Server and Workstation Requirements and Impact | Identify Server and Workstation Requirements
Str | Assess and Define Server and Workstation Requirements and Impact | Assess Existing Server and Workstation Environment
Str | Assess and Define Server and Workstation Requirements and Impact | Document and Analyze Requirements and Current Server and Workstation Environment Findings
Str | Assess and Define Server and Workstation Requirements and Impact | Identify Potential Server and Workstation Upgrades
Str | Assess and Define Server and Workstation Requirements and Impact | Define Server and Workstation Strategy
Str | Assess and Define Server and Workstation Requirements and Impact | Assess and Define Server and Workstation Requirements and Impact Complete
Str |  |  | 1.1.23
Str | Assess and Define Performance Monitoring Requirements and Impact | Identify Infrastructure Components Included in Monitoring |  | TI
Str | Assess and Define Performance Monitoring Requirements and Impact | Identify Performance Monitoring Requirements
Str | Assess and Define Performance Monitoring Requirements and Impact | Determine and Publish Enterprise Environment Variables
Str | Assess and Define Performance Monitoring Requirements and Impact | Assess Existing Performance Monitoring Environment
Str | Assess and Define Performance Monitoring Requirements and Impact | Document and Analyze Requirements and Current Environment Findings
Str | Assess and Define Performance Monitoring Requirements and Impact | Identify Potential Performance Monitoring Upgrades
Str | Assess and Define Performance Monitoring Requirements and Impact | Define Performance Monitoring Strategy
Str | Assess and Define Performance Monitoring Requirements and Impact | Assess and Define Performance Monitoring Requirements and Impact Complete
Str |  |  | 1.1.24
Str | Consolidate Comprehensive Technical Architecture Strategy and Scope | Define Preliminary Comprehensive Technical Architecture Strategy and Scope |  | TI
Str | Consolidate Comprehensive Technical Architecture Strategy and Scope | Define Comprehensive Technical Architecture Maintenance Strategy
Str | Consolidate Comprehensive Technical Architecture Strategy and Scope | Finalize Comprehensive Technical Architecture Upgrades
Str | Consolidate Comprehensive Technical Architecture Strategy and Scope | Create Comprehensive Technical Architecture Strategy and Scope Document
Str | Consolidate Comprehensive Technical Architecture Strategy and Scope | Consolidate Comprehensive Technical Architecture Strategy and Scope Complete
Str |  |  | 1.1.25
Str | Consolidate Overall Scope Plan | Consolidate and Reconcile Project Scope |  | PM | A | SM.010 Define and Confirm Scope
Str | Consolidate Overall Scope Plan | Identify Future Project Considerations |  |  | A | SM.010 Define and Confirm Scope
Str | Consolidate Overall Scope Plan | Review Project Scope and Future Project Considerations with Project Sponsor |  |  | A | SM.010 Define and Confirm Scope
Str | Consolidate Overall Scope Plan | Consolidate Overall Scope Plan Complete |  |  | A | SM.010 Define and Confirm Scope
Str |  |  | 1.1.26
Str | Create High-Level Project Plan | Develop High-Level Project Plan |  | PM
Str | Create High-Level Project Plan | Create High-Level Project Plan Complete
Str |  |  | 1.1.27
Str | Publish Project Charter | Assemble Deliverables Included in Charter |  | PM
Str | Publish Project Charter | Distribute Charter to Steering Committee
Str | Publish Project Charter | Publish Project Charter Complete
Str |  |  | 1.1.28
Str | Quality Review Checkpoint - Planning and Project Charter | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Str | Quality Review Checkpoint - Planning and Project Charter | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Str | Quality Review Checkpoint - Planning and Project Charter | Review Project Processes
Str | Quality Review Checkpoint - Planning and Project Charter | Review Statement of Service and Current Scope
Str | Quality Review Checkpoint - Planning and Project Charter | Document Project Review Findings
Str | Quality Review Checkpoint - Planning and Project Charter | Quality Review Checkpoint Complete
Str |  |  | 1.2.1
Str | Create Project Environments | Procure Hardware, Software, and Services |  | TI | A | PCM.050 Order Goods as Applicable
Str | Create Project Environments | Review Install Options
Str | Create Project Environments | Prepare Environments |  |  | A | IFM.030 Establish Team Work Environment
Str | Create Project Environments | Perform Certified Installation of the PeopleSoft System
Str | Create Project Environments | Order Architecture Jumpstart
Str | Create Project Environments | Install the PeopleSoft System PeopleSoft Install
Str | Create Project Environments | Customer Self-Install
Str | Create Project Environments | Implementation Center Install
Str | Create Project Environments | Apply Updates and Fixes
Str | Create Project Environments | Create Database Environments
Str | Create Project Environments | Provide Remote Access
Str | Create Project Environments | Create Project Environments Complete
Str |  |  | 1.2.2
Str | Train Project Team | Review the Project Team Training Strategy and Scope |  | TR
Str | Train Project Team | Identify Project Team Training Requirements
Str | Train Project Team | Create Project Team Training Plan and Schedule
Str | Train Project Team | Attend Training Sessions
Str | Train Project Team | Train Project Team Complete
Str |  |  | 1.2.3
Str | Create Development Support Plan | Review the Development Support Approach and the Software Configuration Management Plan for Project |  | TI | A | IFM.010 Develop Infrastructure Management Plan
Str | Create Development Support Plan | Determine Development Support Requirements |  |  | A | IFM.010 Develop Infrastructure Management Plan
Str | Create Development Support Plan | Draft New Development Support Plan |  |  | A | IFM.010 Develop Infrastructure Management Plan
Str | Create Development Support Plan | Finalize and Document Development Support Plan |  |  | A | IFM.010 Develop Infrastructure Management Plan
Str | Create Development Support Plan | Create Development Support Plan Complete |  |  | A | IFM.010 Develop Infrastructure Management Plan
Str |  |  | 1.2.4
Str | Perform Detailed Business Process Modeling | Review Business Needs and Process Integration Results, and Draft Business Process Modeling Schedule |  | BP
Str | Perform Detailed Business Process Modeling | Define Roles, Business Events and Scenarios for Business Process Modeling
Str | Perform Detailed Business Process Modeling | Finalize Business Process Modeling Schedule
Str | Perform Detailed Business Process Modeling | Draft Business Process Models
Str | Perform Detailed Business Process Modeling | Confirm and Finalize Business Process Models, and Identify Potential Business Process Gaps
Str | Perform Detailed Business Process Modeling | Document and Analyze Potential Business Process Gaps
Str | Perform Detailed Business Process Modeling | Determine Potential Business Process Gap Solution Recommendations
Str | Perform Detailed Business Process Modeling | Present and Confirm Business Process Gap Solution Recommendations
Str | Perform Detailed Business Process Modeling | Document and Analyze Business Process Modeling Results
Str | Perform Detailed Business Process Modeling | Perform Detailed Business Process Modeling Complete
Str |  |  | 1.2.5
Str | Perform Fit/Gap Analysis | Define Technical Environment for Fit/Gap |  | BP
Str | Perform Fit/Gap Analysis | Review Functional Business Needs, and Draft Fit/Gap Schedule
Str | Perform Fit/Gap Analysis | Review Business Process Modeling Results
Str | Perform Fit/Gap Analysis | Define Business Events and Scenarios for Fit/Gap
Str | Perform Fit/Gap Analysis | Model Logical Data for Analytics
Str | Perform Fit/Gap Analysis | Configure and Set Up Functional Environment for Fit/Gap
Str | Perform Fit/Gap Analysis | Review and Customize Necessary Objects for Fit/Gap
Str | Perform Fit/Gap Analysis | Finalize Fit/Gap Schedule
Str | Perform Fit/Gap Analysis | Perform Fit/Gap Sessions
Str | Perform Fit/Gap Analysis | Document Initial Functional Specifications
Str | Perform Fit/Gap Analysis | Finalize Fit/Gap Document
Str | Perform Fit/Gap Analysis | Validate Potential Customization Requirements
Str | Perform Fit/Gap Analysis | Perform Fit/Gap Analysis Complete
Str |  |  | 1.2.6
Str | Perform Configuration Test | Review Configuration and Set Up Base Tables for Configuration Test |  | BP
Str | Perform Configuration Test | Create Configuration Test Plan
Str | Perform Configuration Test | Create Configuration Test Scripts
Str | Perform Configuration Test | Execute Configuration Test
Str | Perform Configuration Test | Resolve Configuration Test Issues
Str | Perform Configuration Test | Create Base Table Configuration and Setup Document
Str | Perform Configuration Test | Validate Potential Customization Requirements
Str | Perform Configuration Test | Perform Configuration Test Complete
Str |  |  | 1.2.7
Str | Define Gap Solutions and Functional Specifications | Review Process and Functional Gap Alternatives and Solutions |  | BP
Str | Define Gap Solutions and Functional Specifications | Determine Alternatives and Solutions
Str | Define Gap Solutions and Functional Specifications | Define High-Level Estimates
Str | Define Gap Solutions and Functional Specifications | Finalize and Document Gap Solutions and Functional Specifications
Str | Define Gap Solutions and Functional Specifications | Prioritize Gap Solutions and Functional Specifications
Str | Define Gap Solutions and Functional Specifications | Define Gap Solutions and Functional Specifications Complete
Str |  |  | 1.2.8
Str | Finalize Project Scope | Finalize Project Scope |  | PM | A | SM.010 Define and Confirm Scope
Str | Finalize Project Scope | Finalize Project Scope Complete
Str |  |  | 1.2.9
Str | Create Draft Project Plan | Create Draft Project Plan |  | PM
Str | Create Draft Project Plan | Create Draft Project Plan Complete
Str |  |  | 1.2.10
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Review Project Processes
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Review Statement of Service and Current Scope
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Document Project Review Findings
Str | Quality Review Checkpoint - Fit/Gap Functional Requirements and Specifications | Quality Review Checkpoint Complete
Str |  |  | 1.3
Str | Close Structure Phase | Close Structure Phase |  | PM
Cons
Cons | Design Software Configuration Management for Production | Review/Update Software Configuration Management Requirements for Production |  | TI
Cons | Design Software Configuration Management for Production | Develop Plan for Software Configuration Management for Production
Cons | Design Software Configuration Management for Production | Create Design for Software Configuration Management for Production
Cons | Design Software Configuration Management for Production | Design Software Configuration Management for Production Complete
Cons |  |  | 2.1.2
Cons | Design Production Database | Review/Update Production Database Requirements |  | TI
Cons | Design Production Database | Develop Plan for Production Database Upgrade and Maintenance
Cons | Design Production Database | Create Production Database Design
Cons | Design Production Database | Design Production Database Complete
Cons |  |  | 2.1.3
Cons | Design Network | Review/Update Network Requirements |  | TI
Cons | Design Network | Develop Plan for Network Upgrade and Maintenance
Cons | Design Network | Create Network Design
Cons | Design Network | Design Network Complete
Cons |  |  | 2.1.4
Cons | Design Server and Workstation | Review/Update Server and Workstation Requirements |  | TI
Cons | Design Server and Workstation | Develop Plan for Server and Workstation Upgrade and Maintenance
Cons | Design Server and Workstation | Create Server and Workstation Design
Cons | Design Server and Workstation | Design Server and Workstation Complete
Cons |  |  | 2.1.5
Cons | Design Performance Monitoring | Review/Update Performance Monitoring Requirements |  | TI
Cons | Design Performance Monitoring | Develop Plan for Performance Monitoring Upgrade and Maintenance
Cons | Design Performance Monitoring | Create Design for Performance Monitoring
Cons | Design Performance Monitoring | Design Performance Monitoring Complete
Cons |  |  | 2.1.6
Cons | Design Technical Architecture | Incorporate Component Designs into Comprehensive Technical Architecture Design |  | TI
Cons | Design Technical Architecture | Define Comprehensive Technical Architecture Detail for Project Plan
Cons | Design Technical Architecture | Design Technical Architecture Complete
Cons |  |  | 2.1.7
Cons | Gather and Document Business Data Elements | Review Base Table Configuration and Setup Document |  | TA
Cons | Gather and Document Business Data Elements | Prepare for Business Data Element Sessions
Cons | Gather and Document Business Data Elements | Review and Clarify Responses
Cons | Gather and Document Business Data Elements | Conduct Business Data Element Sessions
Cons | Gather and Document Business Data Elements | Update Base Table Configuration and Setup Document
Cons | Gather and Document Business Data Elements | Gather and Document Business Data Elements Complete
Cons |  |  | 2.1.8
Cons | Design Customizations | Review/Update Functional Specifications for Customizations |  | TA
Cons | Design Customizations | Define Customization Detail for Project Plan
Cons | Design Customizations | Create Technical Specifications for Customizations
Cons | Design Customizations | Design Customizations Complete
Cons |  |  | 2.1.9
Cons | Design Conversions | Review/Update Functional Specifications for Conversions |  | TA
Cons | Design Conversions | Define Conversion Detail for Project Plan
Cons | Design Conversions | Perform Data Mapping for Conversions
Cons | Design Conversions | Create Technical Specifications for Conversions
Cons | Design Conversions | Design Conversions Complete
Cons |  |  | 2.1.10
Cons | Design Interfaces | Review/Update Functional Specifications for Interfaces |  | TA
Cons | Design Interfaces | Define Interface Detail for Project Plan
Cons | Design Interfaces | Perform Data Mapping for Interfaces
Cons | Design Interfaces | Create Technical Specifications for Interfaces
Cons | Design Interfaces | Design Interfaces Complete
Cons |  |  | 2.1.11
Cons | Design Reports | Review/Update Functional Specifications for Reports |  | TA
Cons | Design Reports | Define Report Detail for Project Plan
Cons | Design Reports | Create Technical Specifications for Reports
Cons | Design Reports | Design Reports Complete
Cons |  |  | 2.1.12
Cons | Design Workflow | Review/Update Functional Specifications for Workflow |  | TA
Cons | Design Workflow | Define Workflow Detail for Project Plan
Cons | Design Workflow | Create Technical Specifications for Workflow
Cons | Design Workflow | Design Workflow Complete
Cons |  |  | 2.1.13
Cons | Design Application Security | Review/Update Functional Specifications for Application Security |  | TA
Cons | Design Application Security | Define Application Security Detail for Project Plan
Cons | Design Application Security | Create Detailed Specifications for Application Security
Cons | Design Application Security | Design Application Security Complete
Cons |  |  | 2.1.14
Cons | Design Content Management Process | Define Content Management Process Detail for Project Plan |  | TI
Cons | Design Content Management Process | Create Detailed Specifications for Content Management Process
Cons | Design Content Management Process | Design Content Management Process Complete
Cons |  |  | 2.1.15
Cons | Design Graphical Style for Web | Brainstorm Design Ideas |  | TI
Cons | Design Graphical Style for Web | Prepare Design Elements
Cons | Design Graphical Style for Web | Rank and Select Design Elements
Cons | Design Graphical Style for Web | Design Graphical Style for Web Complete
Cons |  |  | 2.1.16
Cons | Design Information Architecture | Review/Update Functional Specifications for Information Architecture |  | TI
Cons | Design Information Architecture | Define Information Architecture Detail for Project Plan
Cons | Design Information Architecture | Create Detailed Specifications for Information Architecture
Cons | Design Information Architecture | Design Information Architecture Complete
Cons |  |  | 2.1.17
Cons | Design Web Integration | Review/Update Functional Specifications for Web Integration |  | TI
Cons | Design Web Integration | Define Web Integration Detail for Project Plan
Cons | Design Web Integration | Create Technical Specifications for Web Integration
Cons | Design Web Integration | Design Web Integration Complete
Cons |  |  | 2.1.18
Cons | Design System Security | Review/Update Functional Specifications for System Security |  | TI
Cons | Design System Security | Define System Security Detail for Project Plan
Cons | Design System Security | Create Detailed Specifications for System Security
Cons | Design System Security | Design System Security Complete
Cons |  |  | 2.1.19
Cons | Perform Rapid Design and Build | Review/Update Functional Specifications |  | TA
Cons | Perform Rapid Design and Build | Draft Rapid Design and Build Session Schedule
Cons | Perform Rapid Design and Build | Define Rapid Design and Build Detail for Project Plan
Cons | Perform Rapid Design and Build | Prepare for Rapid Design and Build Sessions
Cons | Perform Rapid Design and Build | Unit Test Rapid Design and Build Environment
Cons | Perform Rapid Design and Build | Finalize Rapid Design and Build Schedule
Cons | Perform Rapid Design and Build | Conduct Rapid Design and Build Sessions
Cons | Perform Rapid Design and Build | Create Technical Specifications Documentation
Cons | Perform Rapid Design and Build | Perform Rapid Design and Build Complete
Cons |  |  | 2.1.20
Cons | Create Help Desk / Knowledge Base Plan | Review Help Desk / Knowledge Base Approach |  | TI
Cons | Create Help Desk / Knowledge Base Plan | Determine Help Desk / Knowledge Base Requirements
Cons | Create Help Desk / Knowledge Base Plan | Draft Help Desk / Knowledge Base Plan
Cons | Create Help Desk / Knowledge Base Plan | Finalize and Document Help Desk / Knowledge Base Plan
Cons | Create Help Desk / Knowledge Base Plan | Create Help Desk / Knowledge Base Plan Complete
Cons |  |  | 2.1.21
Cons | Create Test Plans | Create Unit Test Plan |  | TI
Cons | Create Test Plans | Create Integration Test Plan
Cons | Create Test Plans | Create System Test Plan
Cons | Create Test Plans | Create User Test Plan
Cons | Create Test Plans | Create Parallel Test Plan
Cons | Create Test Plans | Create Performance Test Plan
Cons | Create Test Plans | Create Benchmark Test Plan
Cons | Create Test Plans | Create Regression Test Plan
Cons | Create Test Plans | Create Usability Test Plan
Cons | Create Test Plans | Create Stress / Load Test Plan
Cons | Create Test Plans | Create Technical Architecture Test Plan
Cons | Create Test Plans | Create Test Plans Complete
Cons |  |  | 2.1.22
Cons | Design End-User Training | Review/Update Functional Specifications for End-User Training |  | TR
Cons | Design End-User Training | Define End-User Training Detail for Project Plan
Cons | Design End-User Training | Create Detailed Specifications for End-User Training
Cons | Design End-User Training | Design End-User Training Complete
Cons |  |  | 2.1.23
Cons | Create Baseline Project Plan | Develop Baseline Project Plan |  | PM | A | WM.010 Develop Baseline Project Work Plan
Cons | Create Baseline Project Plan | Create Baseline Project Plan Complete
Cons |  |  | 2.1.24
Cons | Quality Review Checkpoint - Design | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Cons | Quality Review Checkpoint - Design | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Cons | Quality Review Checkpoint - Design | Review Project Processes
Cons | Quality Review Checkpoint - Design | Review Statement of Service and Current Scope
Cons | Quality Review Checkpoint - Design | Document Project Review Findings
Cons | Quality Review Checkpoint - Design | Quality Review Checkpoint Complete
Cons |  |  | 2.1.25
Cons | Configure and Set Up Base Tables | Review Configuration Decisions |  | BP
Cons | Configure and Set Up Base Tables | Configure and Set Up Base Tables
Cons | Configure and Set Up Base Tables | Update Base Table Configuration and Setup Document
Cons | Configure and Set Up Base Tables | Configure and Set Up Base Tables Complete
Cons |  |  | 2.2.1
Cons | Build Comprehensive Technical Architecture | Implement Production Database |  | TI | A | IFM.030 Establish Technical Infrastructure
Cons | Build Comprehensive Technical Architecture | Install Network Upgrades |  |  | A | IFM.030 Establish Technical Infrastructure
Cons | Build Comprehensive Technical Architecture | Install Server and Workstation Upgrades |  |  | A | IFM.030 Establish Technical Infrastructure
Cons | Build Comprehensive Technical Architecture | Implement Software Configuration Management |  |  | A | IFM.030 Establish Technical Infrastructure
Cons | Build Comprehensive Technical Architecture | Implement Performance Monitoring Upgrades |  |  | A | IFM.030 Establish Technical Infrastructure
Cons | Build Comprehensive Technical Architecture | Build Comprehensive Technical Architecture Complete |  |  | A | IFM.030 Establish Technical Infrastructure
Cons |  |  | 2.2.2
Cons | Build Customizations | Build Customizations |  | TA
Cons | Build Customizations | Unit Test Customizations
Cons | Build Customizations | Build Customizations Complete
Cons |  |  | 2.2.3
Cons | Build Conversions | Build Conversions |  | TA
Cons | Build Conversions | Unit Test Conversions
Cons | Build Conversions | Build Conversions Complete
Cons |  |  | 2.2.4
Cons | Build Interfaces | Build Interfaces |  | TA
Cons | Build Interfaces | Unit Test Interfaces
Cons | Build Interfaces | Build Interfaces Complete
Cons |  |  | 2.2.5
Cons | Build Reports | Build Reports |  | TA
Cons | Build Reports | Unit Test Reports
Cons | Build Reports | Build Reports Complete
Cons |  |  | 2.2.6
Cons | Build Workflow | Build Workflow |  | TA
Cons | Build Workflow | Unit Test Workflow
Cons | Build Workflow | Build Workflow Complete
Cons |  |  | 2.2.7
Cons | Build Application Security | Build Application Security |  | TI
Cons | Build Application Security | Unit Test Application Security
Cons | Build Application Security | Build Application Security Complete
Cons |  |  | 2.2.8
Cons | Build Content Management Process | Build Content Management Process |  | TI
Cons | Build Content Management Process | Audit Content Management Process
Cons | Build Content Management Process | Build Content Management Process Complete
Cons |  |  | 2.2.9
Cons | Build Graphical Style for Web | Prepare Final Graphic Elements |  | TI
Cons | Build Graphical Style for Web | Build Graphical Style for Web Complete
Cons |  |  | 2.2.10
Cons | Build Information Architecture | Build Information Architecture |  | TI
Cons | Build Information Architecture | Unit Test Information Architecture
Cons | Build Information Architecture | Build Information Architecture Complete
Cons |  |  | 2.2.11
Cons | Build Web Integration | Build Site Integration |  | TI
Cons | Build Web Integration | Build Web Integration
Cons | Build Web Integration | Unit Test Web Integration
Cons | Build Web Integration | Build Web Integration Complete
Cons |  |  | 2.2.12
Cons | Build System Security | Build System Security |  | TI
Cons | Build System Security | Unit Test System Security
Cons | Build System Security | Build System Security Complete
Cons |  |  | 2.2.13
Cons | Perform Integration Test | Create Integration Test Scripts |  | TA
Cons | Perform Integration Test | Execute Integration Test
Cons | Perform Integration Test | Resolve Issues
Cons | Perform Integration Test | Perform Integration Test Complete
Cons |  |  | 2.2.14
Cons | Create Process and Procedure Documentation | Create User Process and Procedure Documentation |  | BP
Cons | Create Process and Procedure Documentation | Create System Test Scripts for Process Change
Cons | Create Process and Procedure Documentation | Create Process and Procedure Documentation Complete
Cons |  |  | 2.2.15
Cons | Create Production Support Plan | Review Production Support Approach |  | TI
Cons | Create Production Support Plan | Determine Production Support Requirements for the New System
Cons | Create Production Support Plan | Draft New Production Support Plan
Cons | Create Production Support Plan | Finalize and Document New Production Support Plan
Cons | Create Production Support Plan | Create Production Support Plan Complete
Cons |  |  | 2.2.16
Cons | Create Disaster Recovery Plan | Review Disaster Recovery Approach |  | TI
Cons | Create Disaster Recovery Plan | Determine Disaster Recovery Requirements for the New System
Cons | Create Disaster Recovery Plan | Draft New Disaster Recovery Plan
Cons | Create Disaster Recovery Plan | Finalize and Document New Disaster Recovery Plan
Cons | Create Disaster Recovery Plan | Create Disaster Recovery Plan Complete
Cons |  |  | 2.2.17
Cons | Create Go-Live Contingency Plan | Review Go-Live Contingency Approach |  | PM
Cons | Create Go-Live Contingency Plan | Determine Go-Live Contingency Plan Requirements
Cons | Create Go-Live Contingency Plan | Determine Go-Live Acceptance Criteria
Cons | Create Go-Live Contingency Plan | Draft Go-Live Contingency Plan
Cons | Create Go-Live Contingency Plan | Finalize and Document Go-Live Contingency Plan
Cons | Create Go-Live Contingency Plan | Create Go-Live Contingency Plan Complete
Cons |  |  | 2.2.18
Cons | Quality Review Checkpoint - Build and Test | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Cons | Quality Review Checkpoint - Build and Test | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Cons | Quality Review Checkpoint - Build and Test | Review Project Processes
Cons | Quality Review Checkpoint - Build and Test | Review Statement of Service and Current Scope
Cons | Quality Review Checkpoint - Build and Test | Document Project Review Findings
Cons | Quality Review Checkpoint - Build and Test | Quality Review Checkpoint Complete
Cons |  |  | 2.3
Cons | Close Construct Phase | Close Construct Phase |  | PM
Trans
Trans | Update and Finalize Configuration and Setup of Base Tables | Update and Finalize Configuration and Setup of Base Tables |  | BP
Trans | Update and Finalize Configuration and Setup of Base Tables | Update and Finalize Base Table Configuration and Setup Document
Trans | Update and Finalize Configuration and Setup of Base Tables | Freeze Base Table Setup and Configuration
Trans | Update and Finalize Configuration and Setup of Base Tables | Update and Finalize Configuration and Setup of Base Tables Complete
Trans
Trans | Load Data and Execute Conversions - Preliminary | Clean Data |  | TA
Trans | Load Data and Execute Conversions - Preliminary | Load Data
Trans | Load Data and Execute Conversions - Preliminary | Reconcile Results
Trans | Load Data and Execute Conversions - Preliminary | Load Data and Execute Conversions - Preliminary Complete
Trans
Trans | Build End-User Training | Build Training Environments |  | TR
Trans | Build End-User Training | Build Training Materials
Trans | Build End-User Training | Prepare for Training Sessions
Trans | Build End-User Training | Unit Test End-User Training
Trans | Build End-User Training | Build End-User Training Complete
Trans
Trans | Perform System Test | Review/Update System Test Scripts |  | TI
Trans | Perform System Test | Identify and Train Users to Participate in System Test
Trans | Perform System Test | Execute System Test
Trans | Perform System Test | Resolve System Test Issues
Trans | Perform System Test | Perform System Test Complete
Trans
Trans | Quality Review Checkpoint - System Test | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Trans | Quality Review Checkpoint - System Test | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Trans | Quality Review Checkpoint - System Test | Review Project Processes
Trans | Quality Review Checkpoint - System Test | Review Statement of Service and Current Scope
Trans | Quality Review Checkpoint - System Test | Document Project Review Findings
Trans | Quality Review Checkpoint - System Test | Quality Review Checkpoint Complete
Trans
Trans | Create Cutover Plan | Review Cutover Approach |  | PM
Trans | Create Cutover Plan | Determine Cutover Requirements
Trans | Create Cutover Plan | Draft Cutover Plan
Trans | Create Cutover Plan | Document and Finalize Cutover Plan
Trans | Create Cutover Plan | Create Cutover Plan Complete
Trans
Trans | Perform User Test | Review/Update User Test Scripts |  | TI
Trans | Perform User Test | Identify and Train Users to Participate in User Test
Trans | Perform User Test | Execute User Test
Trans | Perform User Test | Resolve User Test Issues
Trans | Perform User Test | Perform User Test Complete
Trans
Trans | Perform Parallel Test | Review/Update Parallel Test Scripts |  | TI
Trans | Perform Parallel Test | Identify and Train End Users to Participate in Parallel Test
Trans | Perform Parallel Test | Prepare Environment for Parallel Test
Trans | Perform Parallel Test | Execute Parallel Test
Trans | Perform Parallel Test | Resolve Parallel Test Issues
Trans | Perform Parallel Test | Perform Parallel Test Complete
Trans
Trans | Perform Stress/Load Test | Create Stress/Load Test Scripts |  | TI
Trans | Perform Stress/Load Test | Identify and Train End Users to Participate in Stress/Load Test
Trans | Perform Stress/Load Test | Execute Stress/Load Test
Trans | Perform Stress/Load Test | Resolve Stress/Load Test Issues
Trans | Perform Stress/Load Test | Perform Stress/Load Test Complete
Trans
Trans | Test Disaster Recovery Plan | Create Disaster Recovery Scenarios |  | TI
Trans | Test Disaster Recovery Plan | Identify and Train Users to Participate in Disaster Recovery Test
Trans | Test Disaster Recovery Plan | Test Disaster Recovery Plan
Trans | Test Disaster Recovery Plan | Resolve Issues
Trans | Test Disaster Recovery Plan | Test Disaster Recovery Plan Complete
Trans
Trans | Perform Benchmark Test | Create Benchmark Test Scripts |  | TI
Trans | Perform Benchmark Test | Execute Benchmark Test
Trans | Perform Benchmark Test | Resolve Benchmark Test Issues
Trans | Perform Benchmark Test | Perform Benchmark Test Complete
Trans
Trans | Perform Performance Test | Create Performance Test Scripts |  | TI
Trans | Perform Performance Test | Execute Performance Test
Trans | Perform Performance Test | Resolve Performance Test Issues
Trans | Perform Performance Test | Perform Performance Test Complete
Trans
Trans | Perform Technical Architecture Test | Create Technical Architecture Test Scripts |  | TI
Trans | Perform Technical Architecture Test | Execute Technical Architecture Test
Trans | Perform Technical Architecture Test | Resolve Technical Architecture Test Issues
Trans | Perform Technical Architecture Test | Perform Technical Architecture Test Complete
Trans
Trans | Perform Usability Test | Create Usability Test Scripts |  | TI
Trans | Perform Usability Test | Execute Usability Test
Trans | Perform Usability Test | Resolve Usability Test Issues
Trans | Perform Usability Test | Perform Usability Test Complete
Trans
Trans | Test Cutover Plan | Test Cutover Plan |  | PM
Trans | Test Cutover Plan | Resolve Cutover Plan Test Issues
Trans | Test Cutover Plan | Test Cutover Plan Complete
Trans
Trans | Prepare Production Environment | Finalize Production Data and Conversions |  | TI
Trans | Prepare Production Environment | Establish Production Environment
Trans | Prepare Production Environment | Migrate DB Objects
Trans | Prepare Production Environment | Establish Backup and Restore Processes
Trans | Prepare Production Environment | Migrate/Establish Processing Schedules
Trans | Prepare Production Environment | Migrate/Set Up Security
Trans | Prepare Production Environment | Migrate Workflow
Trans | Prepare Production Environment | Initiate Help Desk / Knowledge Base
Trans | Prepare Production Environment | Evaluate Production Environment Readiness
Trans | Prepare Production Environment | Prepare Production Environment Complete
Trans
Trans | Evaluate Readiness | Revisit and Evaluate Go-Live Acceptance Criteria |  | PM
Trans | Evaluate Readiness | Evaluate Customer Readiness
Trans | Evaluate Readiness | Assess Decision to Go Live
Trans | Evaluate Readiness | Evaluate Readiness Complete
Trans
Trans | Quality Review Checkpoint - Production Readiness | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Trans | Quality Review Checkpoint - Production Readiness | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Trans | Quality Review Checkpoint - Production Readiness | Review Project Processes
Trans | Quality Review Checkpoint - Production Readiness | Review Statement of Service and Current Scope
Trans | Quality Review Checkpoint - Production Readiness | Document Project Review Findings
Trans | Quality Review Checkpoint - Production Readiness | Quality Review Checkpoint Complete
Trans
Trans | Close Transition Phase | Close Transition Phase |  | PM
Depl
Depl | Train End Users | Conduct Training Sessions |  | TR
Depl | Train End Users | Evaluate User Proficiency
Depl | Train End Users | Train End Users Complete
Depl
Depl | Perform Cutover | Execute Cutover Plan |  | PM
Depl | Perform Cutover | Perform Cutover Complete
Depl
Depl | Provide Post-Project Support | Provide End-User Support |  | TI
Depl | Provide Post-Project Support | Provide Technical Support
Depl | Provide Post-Project Support | Conduct Project Transition Meeting
Depl | Provide Post-Project Support | Provide Post-Project Support Complete
Depl
Depl | Archive Project Diary | Review Project Documentation Deliverables |  | PM
Depl | Archive Project Diary | Finalize Project Documentation Deliverables
Depl | Archive Project Diary | Archive Project Documentation Deliverables
Depl | Archive Project Diary | Archive Project Diary Complete
Depl
Depl | Conduct Project Acceptance Review | Review Objectives of Project |  | PM
Depl | Conduct Project Acceptance Review | Identify Outstanding Business Issues
Depl | Conduct Project Acceptance Review | Create Project Acceptance Review
Depl | Conduct Project Acceptance Review | Review / Adjust Model Company
Depl | Conduct Project Acceptance Review | Conduct Project Acceptance Review
Depl | Conduct Project Acceptance Review | Certify System
Depl | Conduct Project Acceptance Review | Conduct Project Acceptance Review Complete
Depl
Depl | Quality Review Checkpoint - Deploy | Review Project Deliverables |  | PM | B | QM.050 Perform Quality Assurance
Depl | Quality Review Checkpoint - Deploy | Review Project Plan and Resources |  |  | B | QM.040 Manage Quality Control
Depl | Quality Review Checkpoint - Deploy | Review Project Processes
Depl | Quality Review Checkpoint - Deploy | Review Statement of Service and Current Scope
Depl | Quality Review Checkpoint - Deploy | Document Project Review Findings
Depl | Quality Review Checkpoint - Deploy | Quality Review Checkpoint Complete
Depl
Depl | Close Deploy Phase | Close Deploy Phase |  | PM
PS = Pre-Sales
PM = Project Management
TI = Technology (Infrastructure)
TA = Technical (Apps)
BP = Business Process
TR = Training

## Manage to Compass
OUM Manage |  | Compass
Phase | Task Name | Phase | Activity | Step | Comments
Bid Transition
A | BT.010 Review and Analyze Bid Material | Stra | (Sales) Close and Transition | Transition Information and Knowledge to Delivery
A | BT.020 Review and Confirm Business Case | Str | Define Mission, Objectives, and Performance Measures | Implementation Planning Workshop (IPW)
A | BT.030 Identify Project Stakeholders |  |  | Implementation Planning Workshop (IPW)
A | BT.040 Review and Accept Project Budget
A | BT.050 Review Contract with Customer | Stra | (Sales) Close and Transition | Transition Information and Knowledge to Delivery
A | BT.060 Review Project Approach with Customer | Stra | (Sales) Close and Transition | Transition Information and Knowledge to Delivery
A | BT.070 Create Project Management Plan | Stra |  | Implementation Planning Workshop (IPW)
Scope Management
A | SM.010 Define and Confirm Scope | Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects |  | Activity with many steps.
|  | Str | Consolidate Overall Scope Plan |  | Activity with many steps.
A | SM.020 Develop Scope Change Management Processes | Stru | Create Functional Configuration and Scope Change Management Plan |  | Multiple Steps in activity
B | SM.030 Manage Scope |  |  |  | PM Handbook Ch. 3 (Scope Management)
B | SM.040 Manage Acceptance |  |  |  | Each activity ends with an acceptance step in Compass.
C | SM.050 Gain Acceptance |  |  |  | Each activity ends with an acceptance step in Compass.
C | SM.060 Close Scope Management
Financial Management
A | FM.010 Refine Project Budget | Stra | Lead and Control | Estimate Project (PSC only) | PM Handbook Ch. 5 Covers Cost Management. There is content in this chapter that applies to this process.
|  | Stra | Lead and Control | Estimate PeopleSoft Consulting Financial Return (PSC only)
A | FM.020 Develop Financial Management Plan |  |  |  | PM Handbook Ch. 5
A | FM.030 Set up Time and Expense Tracking |  |  |  | PM Handbook Ch. 5
B | FM.040 Manage Project Finances |  |  |  | PM Handbook Ch. 5
C | FM.050 Close Project Financials |  |  |  | PM Handbook Ch. 5
Work Management
PM Handbook Ch. 4 covers Time Management.
A | WM.010 Develop Baseline Project Work Plan | Cons | Create Baseline Project Plan | Develop Baseline Project Plan
A | WM.020 Develop Work Management Execution and Control Processes and Policies | Str | Define Project Standards and Administration | Define Project Plan Maintenance Procedures
B | WM.030 Manage Project Work Plan |  |  |  | PM Handbook Ch. 4. Also Appendices A, B & C on Project Plans
B | WM.040 Track Schedule Performance |  |  |  | PM Handbook Ch. 4
B | WM.070 Schedule Workshop(s)
C | WM.060 Close Work Management
Issue and Problem Management
A | IPM.010 Develop Issue Management Strategy | Str | Define Project Standards and Administration | Define Issue Resolution Procedures
A | IPM.020 Develop Problem Management Strategy | Str | Define Project Standards and Administration | Define Issue Resolution Procedures
A | IPM.020 Develop Issue and Problem Management System | Str | Define Project Standards and Administration | Define Issue Resolution Procedures | See also Publish Project Charter
B | IPM.040 Manage Issues and Problems |  |  |  | PM Handbook section on Escalation Problems & Issues (Chapter 2)
C | IPM.040 Produce Final Issue and Problem Report and Close Log
Risk Management
A | RKM.010 Develop Risk Management Plan | Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Risks | PM Handbook Ch. 9 covers Risk Management.
A | RKM.020 Conduct Baseline Risk Assessment | Str | Define Assumptions, Constraints, Risks, and Other Critical Path Projects | Define Risks
A | RKM.030 Develop Risk Management System |  |  |  | PM Handbook Ch. 9 & Eagle Database
B | RKM.040 Manage Risk |  |  |  | PM Handbook Ch. 9 covers Risk Management
B | RKM.050 Monitor and Control Risk |  |  |  | PM Handbook Ch. 9 covers Risk Management
C | RKM.060 Conduct Post-Production Risk Assessment
Staff Management
A | STM.010 Plan Resource Requirements | Str | Create Project Team | Validate Resource Requirements
|  | Str | Create Project Team | Define Roles and Responsibilities for Project
A | STM.020 Develop Staff Management Plan | Str | Define Project Standards and Administration | Create Project Administration Guidelines
A | STM.030 Staff the Project | Str | Create Project Team | Assemble Project Team Members
A | STM.040 Prepare Orientation Guide | Str | Create Project Team | Prepare for Project Team Kickoff Meetings | Also Prepare For and Conduct Project Kickoff
B | STM.050 Conduct Team Orientation | Str | Create Project Team | Conduct Project Team Kickoff Meetings | Also Prepare For and Conduct Project Kickoff
B | STM.060 Manage Project Team |  |  |  | PM Handbook Ch. 7
C | STM.070 Release Staff |  |  |  | PM Handbook Ch. 7
Communication Management
A | CMM.010 Conduct Project Stakeholder Analysis |  |  | Implementation Planning Workshop (IPW) | Done as part of the Implementation Planning Workshop (IPW)
A | CMM.020 Develop Project Team Communication Plan | Str | Create Project Team Communication Plan |  | Activity with many steps
|  | Str | Create Organization Communication Plan |  | Activity with many steps
|  | Str | Create External Communication Plan |  | Activity with many steps
|  | Str | Define Project Strategies and Plan Project Scope | Define Strategy and Plan Scope for Communications
B | CMM.030 Manage Project Team Communication |  |  |  | PM Handbook Ch. 8 (Communications Management)
C | CMM.040 Document Lesson Learned |  |  |  | PM Handbook Ch. 2 (Knowledge Transfer Topic)
C | CMM.050 Turn Over Project Documentation
C | CMM.060 Submit Final Reports
Quality Management
A | QM.010 Develop Quality Management Plan | Str | Create Quality Plan | Draft Quality Plan | Activity with steps. Field Guide. PM Handbook Ch. 6. (Quality Management)
Finalize Quality Plan
A | QM.020 Develop and Document Quality Control and Reporting Process |  | Create Quality Plan | Determine Quality Needs, Establish Quality Standards, and Design Quality Control Processes
|  |  | Create Quality Plan | Determine the Quality Review Process
A | QM.030 Conduct Project Team Quality Management Orientation
B | QM.040 Manage Quality Control |  | Quality Review Checkpoints |  | Activity includes some review of specific results. PM Handbook Ch. 6
|  |  | Activity Complete Steps |  | Review and acceptance of deliverables from each activity.
B | QM.050 Perform Quality Assurance | Str | Quality Review Checkpoints |  | Activity includes some review of specific results. PM Handbook Ch. 6
C | QM.060 Conduct Post Production Quality Review
Configuration Management
A | CM.010 Develop Configuration Management Strategy and Processes | Str | Create Functional Configuration and Scope Change Management Plan |  | Activtity with steps. Addresses functional and scope change management.
PM Handbook Ch. Configuration Management Section
A | CM.020 Obtain Configuration Management Tools
A | CM.030 Create Project Documentation Management Plan |  | Define Project Standards and Administration | Create Project Diary | See Project Diary in PM Handbook
B | CM.040 Create and Execute Software Configuration Management Plan | Str | Create Software Configuration Management Plan for Project |  | Activtity with steps. Addresses software changes. Document changes not addressed.
|  | Str | Assess and Define Software Configuration Management Requirements and Impact |  | Activity with many steps related to analyzing requirements, selecting tool and planning necessary changes to environment.
B | CM.050 Create and Execute Software Release Management Plan
B | CM.060 Create and Execute Environment and Patch Management Plan
B | CM.070 Create and Execute Configuration Control Plan
C | CM.080 Close Configuration Management
Infrastructure Management
A | IFM.010 Develop Infrastructure Management Plan | Str | Define Project Approaches | Define Development Support Approach | Activity with many steps. Detailed planning for management of the development enviornment.
A | IFM.020 Establish Team Work Environment | Str | Create Project Environments |  | Activity with many steps
A | IFM.030 Establish Technical Infrastructure | Str | Build Comprehensive Technical Architecture |  | Activity with many steps
B | IFM.040 Manage and Maintain Infrastructure
C | IFM.060 Close Infrastructure
Procurement Management
A | PCM.010 Develop Procurement Strategy and Process |  |  |  | Procurement Management covered in PM Handbook Ch. 11
A | PCM.020 Procure Goods and Contracted Services
B | PCM.030 Administer Procurement of Goods and Contracted Services
C | PCM.040 Close Contract
Organizational Change Management
A | OCHM.010 Understand Organizational Change Management Strategy | Stra | Lead and Control |  | Execute Strategy Workshops
|  | Str | Create Organization and Business Process Change Management Plan
A | OCHM.020 Identify Change Management Warning Signs
B | OCHM.030 Execute Change and Communication Plan | Str | Create Organization Communication Plan |  | Activity with many steps
|  | Str | Create External Communication Plan |  | Activity with many steps
C | OCHM.040 Establish Follow-up Process