## Sheet1
| Scrum Activity | Maps to OUM Task | OUM Phase | Product Owner | ScrumMaster | Scrum Team | Stakeholders Ambassador Users | Objective | Tools/Techniques
1 | Conduct Project Kickoff Meeting | WM.010 Develop Baseline Project Workplan (Project Plan) STM.010 Plan Resource Requirements STM.050 Conduct Team Orientation RA.021 Capture User Stories RD.045 Prioritize Requirements (MoSCoW) | Project Execution and Control | __Reviews main User Stories to be considered for the project (Initial Product Backlog RD.045) | __Determines role assignments for ScrumMaster, Product Owner and Team members __Discusses Sprint Plan (Iteration plan) | __Participates by reviewing the requirements being provided | __Participates by providing high-level information regarding the requirements, as needed | Orient team to project. | __ Initial Product Backlog (High-Level MoSCoW list from Envision) ER.130 MoSCoW Improvement List __RD045.MoSCoW List (Product Backlog sheet) __RA.021 User Story
2a | Product Backlog Grooming (sometimes referred to as "Prepare for Sprint Planning Meeting" | RD.045 Prioritized Requirements (MoSCoW) | Inception/Elaboration | __Reviews main User Stories coming up in the priority list to develop initial understanding (two Sprints after the current Sprint) | __Facilitates meeting (watch clock, Manage Meeting Goals) __Participates in order to understand high-level requirements __Determines high-level capacity of Scrum team based on previous Sprints | Team Members attend based on assignments (optional) | __Helps write User Story name __discusses the high-level requirements __Adjusts priority in the Product Backlog (BEFORE this meeting) | Prepare/Review organize the Product Backlog in preparation for the next several sprints. | __RD.045 MoSCoW list (Product Backlog sheet) __RA.021 User Story
3A | Sprint Planning Meeting (Part 1) | WM.030 Manage Project Workplan (Iteration Plan) RA.021 Capture User Stories | Elaboration/Construction | __ Provides highest priority backlog Items to the team __ Provides details as needed during the conversation | __Facilitates meeting (watch clock, Manage Meeting Goals) __Organizes Story Estimation Session | __ Selects items from the Product Backlog that the team believes they can complete in the Sprint __ Asks for information as needed __Provides estimates at story level using Planning techniques (Poker, Fruit Size Game) | __Participates as needed | 4 hours long aimed at selecting items from the Backlog that the Scrum team can commit to completing in the next Sprint | __Poker Game Technique __Fruit Size Game __Estimation Cards __RA.021 User Story template (simple form)
3B | Sprint Planning Meeting (Part 2) | RA.024 Develop Use Case Details RA.021 Capture User Stories | Elaboration/Construction | __ Comes to the meeting with a prepared Backlog __Provides details about stories as needed during the conversation | __Facilitates meeting (watch clock, Manage Meeting Goals) __Records estimates on User Story Steps or Sprint Backlog Sheet | __Details User Story using Steps __Revises story as needed with appropriate detail __Creates task estimates | __Participates as needed for individual User Story, then leaves meeting (no observers) | 4 hours long aimed at preparing the Sprint Backlog details __Task Breakdown Session __Create Sprint Backlog __Determine Sprint Capacity | __RA.021 User Story template (detail form)
| Sprint Progress updates (1st Sprint) | WM.030 Manage Project Workplan | Elaboration/Construction | Receives updates on progress as needed by seeing Team Status Wall in work area. Does not change scope of Sprint. | __Revises a Sprint Backlog based on incoming task-level actuals vs. estimates __ Create a Burndown Chart and places in team work area __Maintains Sprint Backlog for what is designated to be completed this sprint (line in Backlog indicates original scope of Sprint) | __ MUST attend meeting (otherwise report through another team member, or by phone) __ BE PROMPT __Updates status on Sprint Backlog based on actuals of work in progress tasks __ Provides estimate of remaining time needed to ScrumMaster (for incomplete tasks) | Receives updates on progress as needed by seeing Team Status Wall in work area. Does not change scope of Sprint. | Update progress on Sprint Plan | __Burndown Chart __RD.045 MoSCoW List (Sprint Backlog sheet)
4 | Daily Scrum Meeting | WM.040 Track Schedule Performance STM.060 Manage Project Team | Elaboration/Construction | __Tracks issues needing product owner information __Works with ScrumMaster to resolve AFTER meeting | Facilitates session __Maintains timebox __Reviews Burndown comment on overall Status __Get answers to three Standup meeting questions per team member __Follows up on open issues AFTER the meeting is over | Three questions to be answered by each team member: __1. What have I done since last Stand-up meeting? __2. What do I plan to do today? __3. What problems (if any) are slowing my progress? | Not present at Daily Scrum. After meeting, may be asked to assist product owner in providing more detail to requirements. | Time Limit: 15 minutes. Status with Scrum Team, one Scrum team member talking at a time, no side bars | __RD.045 MoSCoW List Sprint Backlog (item status) Or Use __RA.021 User Story (detail form with task steps for each story)
5A | Measure progress of Sprint (Each work day) | WM.040 Track Schedule Performance | Elaboration/Construction | __Answers questions and clarifies requirements for the Scrum team | __Revises Sprint Backlog based on incoming task-level actuals vs. estimates __ Maintains Burndown Chart in Team work area __Maintains Sprint Backlog for what is designated to be completed this sprint (line in backlog indicates original scope of Sprint) | Works on User Stories __Works one story at a time collaborate to complete in rank order, using available Scrum team members regardless of specialty __No one moves forward to start new Story until the previous one is completed and checked by Product Owner __Updates User Story tasks and status as each one is completed | Is provided with information about progress | Gather information about actual performance to the Sprint backlog | __Burndown Chart (Flip Charts or lined paper that can be hung up to be visible to all) __ Sprint Backlog (RD.045 template maybe made into wall chart)
5B | Update Burndown Chart | WM.040 Track Schedule Performance | Elaboration/Construction |  |  | __Updates Burndown Chart - Draw line for total hours spent vs estimated for tasks not completed up until this point | __Updates status on Sprint Backlog based on actuals of work in progress tasks __ Provides estimate of remaining time needed to ScrumMaster (for incomplete tasks) | Capture information about actual performance to the Sprint Backlog | __Burndown Chart (Flip Charts or lined paper that can be hung up to be visible to all) __ Sprint Backlog (RD.045 template maybe made into wall chart)
6 | Sprint Review | WM.030 Manage Project Workplan (Iteration End Report) | Elaboration/Construction | __Confirms that deliverables meet expectations of stakeholders __Records any issues for follow up | __Facilitates session __Maintains Scrum principles as needed | __ Reviews delivered functionality with the team, main stakeholders, ScrumMaster and product owner __Demonstrates result of each User Story | __Verifies that the results meet the requirements as intended by the User Story __ Accepts results (or report defects) | Demonstrate working software components, review and approval from product owner and stakeholders | OUM Manage misc templates for __Meeting Agenda __Meeting Minutes
7 | Sprint Retrospective | IPM.040 Manage Issues and Problems | Elaboration/Construction | Attendance is optional | __Facilitates session __Maintains Scrum principles as needed | Each person answers three questions: __1. What went well, that we should do again? __2. What needs to be improved? __3. What Specific improvements should we make in the next Sprint? | Not present | Overall improvement of process and removal of obstacles | __IPM.030 Issue Log and Problem Log